## Governance Model
Governance & Stakeholder Management
Version 1.0 ¦ Phase: All ¦ Tasks 9.1, 9.2 ¦ Requirements 9.1-9.8
Section 1 — Governance Structure
Steering Committee
Role | Name | Organization | Decision Authority | Email | Phone | Notes
Executive Sponsor |  |  | Budget, strategic direction
Program Director |  |  | Program scope, timeline
Cloud Architect Lead |  |  | Technical decisions
Finance Lead |  |  | Financial approvals
Security/Compliance Lead |  |  | Security & compliance decisions
Business Owner(s) |  |  | Business requirements, priorities
Meeting Cadence |  | Quorum (members)
Working Groups
Working Group | Lead | Members | Focus Area | Meeting Cadence | Channel | Notes
Technical Assessment |  |  | App profiling, scoring, architecture | Weekly
Financial Analysis |  |  | TCO, ROI, business case | Weekly
Security & Compliance |  |  | Risk, compliance, security controls | Bi-weekly
Migration Planning |  |  | Wave planning, dependencies, roadmap | Weekly
Section 2 — RACI Matrix (R = Responsible, A = Accountable, C = Consulted, I = Informed)
Activity | Executive Sponsor | Program Director | Cloud Architect | Business Owner | Security Lead | Finance Lead
Assessment scope approval | A | R | C | C | I | C
Application discovery | I | A | R | C | I | I
Readiness scoring | I | A | R | C | C | I
Business case development | A | R | C | C | I | R
Risk assessment | I | A | C | I | R | I
Migration wave planning | I | A | R | C | C | I
Hyperscaler recommendation | A | R | R | C | C | C
Final report approval | A | R | C | C | C | C
Section 3 — Scope Management
Scope Statement
Element | Description
In Scope
Out of Scope
Assumptions
Constraints
Change Control
Step | Activity | Owner | SLA | Approver | Trigger | Notes
1 | Change request submitted | Requestor | —
2 | Impact assessment | Program Director | 2 business days
3 | Steering committee review | Steering Committee | Next meeting
4 | Decision communicated | Program Director | 1 business day
5 | Implementation (if approved) | Assigned owner | Per plan
Section 4 — Stakeholder Engagement Plan
Stakeholder Group | Interest Level | Influence Level | Engagement Strategy | Communication Channel | Frequency | Owner
Executive Leadership | High | High | Steering committee updates | Email + Meeting | Monthly
IT Leadership | High | High | Working group participation | Teams + Meeting | Weekly
Application Owners | Medium | Medium | Interviews, validation | Email + Meeting | As needed
Finance | Medium | High | Business case review | Email + Meeting | Bi-weekly
Security/Compliance | High | High | Risk review, compliance validation | Email + Meeting | Bi-weekly
End Users | Low | Low | Change communication | Email | Monthly
Section 5 — Status Reporting (Weekly Status Report Template)
Section | Content
Period (Week of)
Overall Status (Green/Amber/Red)
Phase
% Complete
Key Accomplishments
Planned Next Week
Issues
Risks
Decisions Needed
Section 6 — Escalation Procedures
Level | Escalation To | Trigger | Response SLA | Channel | Owner | Notes
1 | Working Group Lead | Task blocked, data discrepancy | 4 hours
2 | Program Director | Cross-team conflict, scope issue | 1 business day
3 | Steering Committee | Budget impact, timeline impact, strategic decision | 2 business days
4 | Executive Sponsor | Program-level risk, organizational conflict | 3 business days
Template Version 1.0 — Cloud Readiness Accelerator Framework