DMG Cloud Readiness Assessment Part 1

Rebaslined Objectives & Plan

10 April 2026

Agreed between delivery and sales on 10 April 2026. This is the single reference for what we deliver, how, by whom, and by when. It serves two purposes: controlling delivery in the three weeks remaining and giving everyone involved the confidence to progress this deal.

# WHAT DMG WALKS AWAY WITH

- An evidence-based recommendation for a primary cloud platform.

- A defensible TCO comparison they can take to their board, with the on-prem status quo alongside it.

- A concrete view of CRA Part 2 - what it looks like, what it costs, and what happens next if they proceed. An indicative view of full migration.

- Confidence that the assessment was independent and rigorous.

Everything below serves these four outcomes. If it doesn't, it's not in scope.

# SCOPE CONTEXT

All original SOW caps (applications, VMs, databases, network segments, storage) were significantly exceeded during discovery. Leadership absorbed the commercial impact. The assessment proceeds against the full discovered estate.

The SOW includes a conditional investment clause tied to the customer signing a migration SOW by an agreed date. Noted as context. Does not change the approach.

# COMPLETED

Phases 0-3 complete: mobilisation, kick-off, strategy assessment, infrastructure discovery. Data frozen. All mappings produced. Selection criteria finalised. Application workshops majority complete, one remaining (SAAS, booked 21 April).

# WHAT WE ARE DELIVERING

Three deliverables are critical path for the engagement and the deal: the TCO, the Hyperscaler recommendation, and the Part 2 entry point. Then this is synthesised into the final report with a structured narrative which gives DMG a clear justification to decide to proceed to the next stage.

# PRIMARY DELIVERABLES

## 1. TCO Analysis

Layers built sequentially. Optimised and L4L must complete first. Everything else derives from them.

### a) Like-for-like baseline between cloud providers - completed

Owner: Lead Architect (approach and assignment across Platform Architects). Due: 18 April.

Required to reconcile against Hyperscaler-provided L4L costings. Automated approach. Needs to start immediately. Lead Architect to ensure effort is properly balanced among the team.

### b) Optimised TCO - in progress

Owner: Platform Architects (Azure Architect, GCP Architect, AWS Architect). Due: 16 April.

Rightsized pricing, all three clouds, PAYG and 3-year RI. Normalised via AI SKU audit and pricing APIs. Azure/GCP largely done. AWS outstanding (2 regions), completing on AWS Architect's return.

### c) Delta (optimised vs L4L) - derived from (a) and (b)

Owner: Lead Architect. Due: 22 April.

Quantifies the value of rightsizing per cloud.

### d) Licensing overlay - in progress

Owner: Lead Architect. Due: 18 April.

Optimal licence posture per cloud based on actual data. SQL/SA provided. Oracle data expected shortly from Customer (EA). Default BYOL where supported.

Oracle: significant cost, core to the estate, complex licensing. Addressed at high level in TCO, Hyperscaler selection, and Part 2. Not a deep dive. Explore Hyperscaler willingness to fund modernisation but understand that this may be a huge exercise and not within customer appetite.

### e) Status quo - blocked

Owner: PM (chase Customer). Lead Architect (modelling when data arrives). Due: 22 April if data received.

Customer template provided but appears undercooked (hardware showing fully amortised). Broadcom/VMware – perpetual licenses purchased, but risk of no support / future requirement to upgrade not captures or costed.

Action: PM/Sales to challenge with Customer (EA) and potentially Customer (CTO) by 16 April.

Fallback: present cloud TCO with explicit caveats. Business case flagged as provisional.

### f) Year 1 forecast - not started

Owner: Lead Architect. Due: 22 April.

SOW deliverable. 12-month forward view: dual-running during ramp-up, then ongoing on 3-year RI.

Lead Architect to confirm capacity to deliver this alongside other items by Tue 15.

### g) Commercial layer - not started

Owner: PM (engagement via Sales Exec). Sales Exec to engage specific Hyperscaler partner leads. Due: 22 April.

Partner discounts, credits, incentives. Sales Exec or pre-sales to coordinate with the relevant AWS, Azure, and GCP partner leads internally. PM to request via Pre-sales by 10 April, input by 18 April.

Fallback: omitted and noted as "to follow." Does not block playback.

## 2. Hyperscaler Recommendation - in progress

Owner: Lead Architect (consolidation and recommendation). Platform Architects (individual scoring). Due: scoring inputs 16 April. Recommendation 22 April.

Estate-level scoring against weighted criteria produces a ranking across the three Hyperscalers. The primary recommendation will be a single Hyperscaler for the in-scope on-premises estate. Once the recommendation is made, we validate whether there are specific applications that cannot or should not move to the recommended platform due to licensing constraints, technical dependencies, or other factors. If a small number of exceptions exist, the recommendation becomes the primary platform with a Multi-Cloud element for those specific workloads. If a substantial number of exceptions emerge, we revisit the primary recommendation.

At a headline level, we will also apply a 7Rs view across the estate to identify applications that cannot move as-is or would clearly benefit from modernisation or replacement with a SaaS alternative. This is not detailed app-by-app architectural work. It is intended to flag areas of value and complexity that should be investigated further in Part 2.

## 3. Part 2 Entry Point

Owner: PM (integration). Pre-Sales Architect (content). Due: first draft 18 April. Final 24 April.

This is what enables the customer to act. What does Part 2 look like? Indicative cost ranges, phases, timelines, Hyperscaler funding (MAP, credits). Broad app priority groupings. Focus areas for non-lift-and-shift (including Oracle). Indicative migration costings through to completion.

Concrete enough to progress the deal. Not a fully scoped proposal. Clear immediate next step: if the client signs tomorrow, what does that engagement look like?

Pre-Sales Architect must confirm commitment by Mon 13 April. If not, PM escalates to Delivery Director. This cannot be left as an open request.

# SUPPORTING DELIVERABLES

## 4. Cloud Maturity, Gap Analysis, Risk Assessment

Owner: PM (booking with Customer). Lead Architect (delivery). Due: workshops 17 April. Write-up 22 April.

MVP workshops only. Book immediately, condensed format.

Fallback: desk-based assessment using discovery data if Customer can't do w/c 14 April.

## 5. Executive Report and Presentation

Owner: Lead Architect (report, executive narrative, presentation). Practice Lead (review and sense-check of final deliverables, presentation steering). Due: report 23 April. Issued 24 April.

Reflects everything in this charter. Evidence before recommendation. CSP matrix in the body. Executive narrative extractable for the DMG CTO to extract for his board.

## 6. Infrastructure Discovery Summary

Owner: Lead Architect. Due: 21 April.

Data exists. Writing task into the report body.

# NOT DELIVERING

Part 2 or excluded by agreement:

App-by-app cost rollup (agreed to exclude)

Exact workload split per Hyperscaler (Part 2)

Detailed migration wave planning (Part 2)

Application modernisation analysis, exact migration cost analysis, landing zone design (SOW 4.6D/F/K)

Full network dependency mapping (Part 2, full breakdown not achieved)

Detailed 7Rs or per-app platform recommendations (Part 2)

# HYPERSCALER HANDLING

We present first. Always. Our independence is what differentiates us from the Hyperscaler selling directly. That perception must be protected.

Their pricing and scoring: not in our report. We sense-check against it. They present their own view after our recommendation lands.

Our scoring: primary assessment. Their self-scores are input we reviewed, not endorsed.

Funding and incentives: we present our view on what's available and how it maps to workstreams.

# CUSTOMER DEPENDENCIES

Each has a deadline and a fallback. No dependency blocks the playback. It may limit what we can say.

Broadcom/VMware pricing: outstanding. Status quo caveated if not by 18 April. Chase: PM with Customer (EA).

Oracle licensing: expected shortly. Best-estimate default if not by 14 April. Chase: PM with Customer (EA).

On-prem cost challenge: PM to engage Customer (EA) and potentially Customer (CTO) by 16 April. Proceed caveated if no improvement by 18 April.

SAAS workshop: 21 April. Customer SME availability confirmed. Findings incorporated as available. Report not held.

Cloud maturity workshops: w/c 14 April. Customer SME availability required. Desk-based fallback if Customer can't accommodate. Booking: PM.

# GOVERNANCE

Daily stand-up (15 min): PM, Lead Architect, Platform Architects.

Weekly sales alignment: PM + Sales Exec. Fridays (18 and 25 April).

Delivery escalation: PM to Delivery Director. Anything threatening playback, SOW deliverables, or customer confidence.

Technical escalation: Practice Lead to Architect Director. Technical quality or architectural concerns.

Advisory: Practice Lead available for sense-checking, review of final deliverables, and presentation steering. Not an action owner.

Trade-offs: PM can drop supporting deliverables without approval. SOW or customer-facing items need Delivery Director sign-off.

Scope is locked. We've agreed what we're delivering and protecting that scope is how we deliver it well. No additions without PM + Delivery Director agreement.

# TIMELINE AND PLAYBACK

The SOW 11-week window ends w/c 27 April.

inputs complete by Fri 17. Full writing week (w/c 20 April). Proper internal review, revisions, and sign-off the following week. Report issued Fri 1 May. Playback Thu 7 May. Runs approximately one week past the SOW window. Justification is grounded in issues relating to technical discovery and increased scope. This option gives us the time to produce a report we can stand behind.

## SHARED: WEEK 1 - STABILISE AND ALIGN (Mon 13 - Fri 17 April)

Tue 14 is the critical day. Lead Architect returns.

PM walks team through plan. PM. Mon 13.

Brief Lead Architect: this plan, agreed scope, TCO layers, delivery plan. PM. Tue 14.

Start L4L TCO baseline. Lead Architect to assign across Platform Architects. Tue 14.

Complete AWS TCO modelling (2 remaining regions). AWS Architect. By Wed 15.

All optimised TCO modelling complete (all three clouds, all regions). Platform Architects. By Wed 15.

All Hyperscaler scoring complete (non-cost categories). Platform Architects. By Wed 15.

Challenge on-prem cost baseline with Customer (EA). PM. By Wed 15.

AI SKU audit and pricing validation complete. Lead Architect. By Thu 16.

MVP cloud maturity and risk workshops delivered. Lead Architect. By Thu 16.

Customer call: confirm playback date. PM. Thu 16.

L4L TCO baseline complete. Platform Architects (led by Lead Architect). By Fri 17.

Licensing analysis complete (SQL/SA applied, Oracle at high level). Lead Architect. By Fri 17.

Report drafts started (TCO, CSP evaluation, infrastructure summary, maturity/gap). Lead Architect. By Fri 17.

Executive narrative first draft. PM + Lead Architect. By Fri 17.

Pre-sales first draft (Part 2 scope and indicative pricing). Pre-Sales Architect. By Fri 17.

Sales alignment call. PM + Sales Exec. Fri 17.

Week 2 - Write and Consolidate (Mon 20 - Fri 24 April)

- Report writing. Lead Architect. Mon 20.

- SAAS workshop. Lead Architect + Customer SME. Tue 21. Report not held.

- TCO consolidated: all layers assembled, delta calculated, status quo positioned. Lead Architect. By Tue 21.

- Year 1 financial forecast complete. Lead Architect. By Tue 21.

- Hyperscaler recommendation finalised. Lead Architect. By Wed 22.

- Part 2 section finalised and integrated. PM + Pre-Sales Architect. By Thu 23.

- Executive presentation drafted. PM. By Thu 23.

- Report complete (all sections). Lead Architect. By Fri 24.

- Sales alignment call. PM + Sales Exec. Fri 24.

Week 3 - Review, Sign-off, and Issue (Mon 27 - Fri 1 May)

- Report complete. Mon 27.

- Internal review. PM. Tue 28.

- Revisions. Lead Architect + PM. Wed 29.

- Revisions. Lead Architect + PM. Thu 30.

- Sign-off (PM + Delivery Director). Report and presentation issued to customer. Fri 1 May.

- Playback week (w/c 5 May)

- Mon 4 May: bank holiday.

- Customer review. Tue 5, Wed 6 May.

- PLAYBACK. Thu 7 May.

# KEY RISKS AGAINST THIS TIMELINE

- Lead Architect is a single point of failure for weeks 1 and 2. Scoring consolidation, TCO consolidation, workshops, report writing. Mitigation: PM to take infrastructure discovery summary write-up and executive narrative first draft. Escalate to Delivery Director if Lead Architect flags capacity issues on Tue 14.

- L4L baseline has 4 working days to complete (Tue 14 to Fri 17). If the automated approach doesn't work or Platform Architects are struggling for capacity, this slips first. Mitigation: PM to confirm approach with Practice Lead on Mon 13. Escalate issues to Delivery Director immediately.

- SAAS workshop on Tuesday 21 is early in the writing week. Mitigation: report not held for SAAS. Findings added as available or noted as addendum.

- Pre-Sales Architect dependency. If Pre-Sales Architect cannot commit by Mon 13, the Part 2 section will be generic. Mitigation: PM sends the request today. Escalate to Delivery Director on Monday if no response.

- Customer data (Broadcom, on-prem challenge). If no improvement by Fri 17, proceed caveated. Known risk, not a blocker. The report is honest about what's missing.

- Playback date may run past the SOW 11-week window (Option B). Deliberate decision: a credible, reviewed report that lands once is worth more than hitting the SOW date with gaps. Communicate proactively. Justification is grounded in issues relating to technical discovery and increased scope.

# PRINCIPLES

Evidence-based. The data makes the case.

Primary platform, then exceptions. Not 39 separate decisions.

Cloud costs in context. L4L, optimised, delta, status quo. Never in isolation.

On-prem baseline must be realistic or the business case fails.

Oracle addressed across TCO, selection, and Part 2. Not a deep dive but not ignored.

Part 2 concrete enough to progress the deal.

Hyperscaler outputs are reference, not our deliverables.

We present first. Always.

Evidence before recommendation.

Where data is incomplete, caveat honestly. Caveated is credible. Silent gaps are not.

# Appendix A - Timeline View

Week 13 – 17 April – Finalise analysis inc TCO & Hyperscaler selection

Week 20 – 24 April – Report writing

Week 27 April – 01 May – Internal report review & presentation run throughs

Week 05 May – 07 May – Customer playback week

| Day | Date | Steps |
| --- | --- | --- |
| Friday | 10-Apr-26 | PM actions: emails and bookings out |
| Saturday | 11-Apr-26 | Weekend |
| Sunday | 12-Apr-26 | Weekend |
| Monday | 13-Apr-26 | PM walks team through plan |
| Tuesday | 14-Apr-26 | Lead Architect returns. Briefed. |
| Wednesday | 15-Apr-26 | PM out. Optimised TCO and scoring complete. |
| Thursday | 16-Apr-26 | Customer call: confirm playback date. Workshops delivered. |
| Friday | 17-Apr-26 | L4L complete. Report drafts started. Pre-Sales first draft. |
| Saturday | 18-Apr-26 | Weekend |
| Sunday | 19-Apr-26 | Weekend |
| Monday | 20-Apr-26 | Report writing |
| Tuesday | 21-Apr-26 | SAAS workshop. TCO consolidated. |
| Wednesday | 22-Apr-26 | Recommendation finalised. |
| Thursday | 23-Apr-26 | Part 2 integrated. Word report ready for review. Presentation drafted. *note sada playbacks on workspace in this week |
| Friday | 24-Apr-26 | Review Reccomendations with Delivery Director & Delivery Lead 10 Am PM & lead architect Pre-sales to provide final funding / credit numbers by 12pm UK for inclusion Final draft activity - Report complete & Presentation complete – issue to wider team by 4pm UK for review |
| Saturday | 25-Apr-26 | Weekend |
| Sunday | 26-Apr-26 | Weekend |
| Monday | 27-Apr-26 | Internal review – PM – Call with internal leaders to walk through findings & recommendations & part 2 approach |
| Tuesday | 28-Apr-26 | Revisions – review key recommendations with Customer enterprise architect only (1-2-1) – 1030 – 1130 UK teams call |
| Wednesday | 29-Apr-26 | Presentation walk through – add calendar invite - PM |
| Thursday | 30-Apr-26 | 2nd presentation walk through – add calendar invite – PM Sign-off. Report issued to customer close of play. |
| Friday | 01-May-26 | DACH public holiday |
| Saturday | 02-May-26 | Weekend |
| Sunday | 03-May-26 | Weekend |
| Monday | 04-May-26 | BANK HOLIDAY |
| Tuesday | 05-May-26 | RACKSPACE PRESENTATION – 0930 to 1330 BST DMGT Office + Zoom |
| Wednesday | 06-May-26 |  |
| Thursday | 07-May-26 |  |
| Friday | 08-May-26 |  |
| Saturday | 09-May-26 |  |
| Sunday | 10-May-26 |  |
| Monday | 11-May-26 |  |
| Tuesday | 12-May-26 | MICROSOFT PRESENTATION – 1400 to 1600 BST DMGT Office + Zoom |
| Wednesday | 13-May-26 | GOOGLE PRESENTATION – 1100 to 1300 BST DMGT Office + Zoom |
| Thursday | 14-May-26 |  |
| Friday | 15-May-26 |  |
| Saturday | 16-May-26 |  |
| Sunday | 17-May-26 |  |
| Monday | 18-May-26 | AWS PRESENTATION – 0930 to 1330 AWS Office + Zoom |
| Tuesday | 19-May-26 |  |
| Wednesday | 20-May-26 |  |
| Thursday | 21-May-26 |  |
| Friday | 22-May-26 |  |
| Saturday | 23-May-26 |  |
| Sunday | 24-May-26 |  |