# DMG Media

# Cloud Readiness Assessment

Part 1: Strategy, Discovery and TCO Analysis

Prepared by: Rackspace Technology

Professional Services
Rackspace Europe, Middle East, Africa (EMEA)

Table of Contents

Document Control	2

Section 1: Executive Summary	3

Section 2: About This Assessment	6

Section 3: Why Cloud, Why Now	9

Section 4: Your Estate	12

Section 5: Cost Comparison	17

Section 6: Business and Application Fit	26

Section 7: Hyperscaler Recommendation	30

Section 8: How Ready Is DMG Media	34

Section 9: Challenges	38

Section 10: Opportunities	42

Section 11: Moving Forward and Phase 2	45

Appendices	50

Appendix A: TCO Methodology and Detail	50

Appendix B: Scoring Methodology and Detail	51

Appendix C: Attached Workbooks	51

Appendix D: Open Items	51

Appendix E: Glossary	52

# Document Control

## Distribution List

| Organization | Department, Role | Name | Email |
| --- | --- | --- | --- |
| [Client Name] | Chief Technology Officer | Neil Finalyson |  |
| [Client Name] | Enterprise Architect | Tristan |  |
| [Client Name] |  | Carl |  |
| [Client Name] |  | Chris |  |
| [Client Name] |  | Mark |  |

## Document Version History

| Version Number | Version Date | Revised By | Description |
| --- | --- | --- | --- |
| V0.1 | 08/04/2026 | Rishabh Dogra | Initial Draft |
| V0.2 | 22/04/2026 | Rishabh Dogra | Second Draft |

# Section 1: Executive Summary

## What This Report Delivers

This is the Phase 1 Cloud Readiness Assessment for [Client Name]. Rackspace spent eleven weeks between February and April 2026 assessing [Client]'s UK and Sydney datacentre estate. The assessment covered automated infrastructure discovery across the full server estate, nine application workshops with business area owners, an independent cost comparison across AWS, Azure, and GCP using live pricing data keeping like to like comparison, a cloud readiness assessment across five organisational dimensions, and a weighted hyperscaler selection evaluation. This report presents the findings, the platform recommendation, and the concrete entry point to Phase 2.

## The Five Things That Matter

### 1. Several [Client Name] contracts are converging inside a two-year window.

The Reading and Slough datacentre leases expire in November 2027. The Microsoft Enterprise Agreement expires in May 2027. The Broadcom VMware position has already shifted: [Client Name] holds perpetual licences with expired or expiring Support and Subscription, which means no patches, no new host additions, and no version upgrades without a VCF subscription. Each of these can be renewed independently but doing so re-locks capital into on premises for another cycle. A coordinated approach lets [Client Name] take the decisions together rather than sequentially and is the reason this assessment exists now rather than in twelve or eighteen months.

### 2. The estate is bigger and more varied than the original scope assumed.

The Statement of Work scoped 2,300 servers across VMware only, based on pre-engagement information. At kick-off, additional infrastructure was disclosed (Proxmox, physical bare metal Oracle and SQL Database Servers, appliances, existing cloud). Scope was expanded during Phase 1 to 3,038 servers across five infrastructure types, fully priced and assessed. Full discovery also identified a wider estate of 4,500+ servers; the ~1,500 beyond the in-scope 3,038 are catalogued but not assessed in Phase 1 and are a Phase 2 scope item. [Client Name] has 39 applications across the estate. Mail Online alone represents 72.6% of in-scope servers and has 91 identified sub-components.

### 3. Cloud is materially cheaper than the on-premises baseline at steady state, and Oracle is the largest single variable.

The on-premises estate costs approximately £3.64 million per year (from the updated IT Costs workbook, with hardware and storage capex now populated). The Complete View for cloud, including Oracle Exadata@Cloud, Oracle support retained under BYOL, Windows and SQL Server BYOL (SA assumed), and indicative internet egress, is approximately £3.17M/yr on GCP, £3.29M/yr on AWS, and £4.19M/yr on Azure. Each cloud's sizing was taken from its own native assessment tool (GCP Migration Center, AWS Transform, Azure Migrate) and then priced against live pricing APIs to normalise the comparison and get as close to apples-to-apples as possible. SKU choices and workload mappings on any of the three clouds may refine with deeper assessment in Phase 2. Steady-state savings potential is approximately £340-460K/yr from AWS or GCP against the on-premises baseline.

Oracle modernisation to PostgreSQL is a deeper strategic Phase 2 decision that could add a further £540-780K/yr saving potential if pursued, by eliminating the £650K/yr Oracle support contract. Each hyperscaler provides transformation support paths for this route; selecting it is a careful business decision, not a Phase 1 action.

Year 1 net position cannot yet be stated with confidence. Year 1 includes migration effort (Phase 2 to scope), dual-run cost during the migration overlap (depends on cohort velocity), and hyperscaler commercial offers (pending). Presenting a speculative Year 1 number without these inputs would be false confidence. Steady-state savings accrue fully from Year 2 onwards as datacentre exit becomes viable.

### 4. The recommended platform is AWS, primary, with validated exceptions.

AWS is the path of least resistance for [Client]'s specific challenges. On the refreshed weighted scoring matrix (1-5 scale) the three clouds are effectively tied: Azure 4.3, AWS 4.3, GCP 4.2 (fit 85.6% / 85.0% / 83.4%). Scoring alone does not decide. Cost places GCP first (£264K/mo), AWS second (+3.7%), and Azure third (+32.1%). Three factors outside the matrix confirm the recommendation: AWS supports multicast natively where GCP and Azure do not (and VMware-on-cloud is not a viable path given the VMware exit strategy); video streaming already runs on AWS Elemental for Mail Online; and the largest partner and skills ecosystem supports the preferred upskill-with-partner model. Two exceptions are validated by evidence: commercial data analytics stays on GCP (existing beachhead, BigQuery is best-in-class for this workload), and video streaming stays on AWS (already there). Mail Online's dual ownership (Chief Product Officer for the product, Chief Technology Officer for the infrastructure) must be reflected in programme governance.

### 5. Organisational readiness is at the level typical for organisations starting this journey.

Overall readiness is approximately 2.1 of 5, measured across Business, Governance, Operations, People, and Security using the standard cloud-adoption questionnaire. Governance is the strongest area (3.0). People is the weakest (1.2). This reflects cloud-specific skills and training rather than overall team capability. The infrastructure organisation has deep enterprise expertise in VMware, Oracle, and networking that this dimension does not capture. This is addressable. It is the first phase of any cloud transformation. Phase 2 and the early programme activities (landing zone, training, FinOps, security baselines) close the gap.

## What [Client] Needs To Do Now

### Data to provide

Microsoft Software Assurance formal confirmation from Bluesource (unblocks BYOL modelling as certainty)

Broadcom VCF subscription quote (completes the 'cost of doing nothing' picture)

MOL Oracle B-cluster DMA data collection (the highest-value Phase 2 discovery gap)

### Decisions to make

Primary platform (this report recommends AWS with exceptions)

Atex vendor engagement on unicast support (direct cost impact)

Oracle path commitment: Exadata@Cloud primary, PostgreSQL as a Phase 2 strategic decision

Operating model for Day 2 (partner-assisted with upskilling is the indicated path)

CPO and CTO joint sponsorship for MOL migration

Over the coming weeks you will hear from AWS, Microsoft, and Google directly. Each will present their own view and their own figures. This report is the independent frame of reference against which those presentations can be weighed.

## Where To Find The Detail

Section 3: the case for acting now, the Broadcom position, and the business drivers

Section 4: [Client]'s estate, the 39 applications, the database landscape

Section 5: cost comparison, methodology, Oracle paths, Complete View

Section 6: application fit, cohorts, technical constraints

Section 7: the scoring matrix and the platform recommendation rationale

Section 8: readiness across five dimensions, current state versus target

Sections 9 and 10: specific challenges and opportunities with quantification

Section 11: Moving forward, Phase 2 entry point, indicative timeline

Appendices A through E: TCO methodology, scoring methodology, attached workbooks, open items, glossary

Phase 2 is a separately proposed engagement. It turns this report into a concrete migration plan and executes on the foundational actions.

# Section 2: About This Assessment

## Who You Are and Why We Are Here

[Client Name] operates some of the UK's largest news and publishing brands, with Mail Online as the commercial centrepiece. You commissioned this engagement in February 2026 because three things are converging: the hardware in your datacentres is ageing out, your Broadcom/VMware support position has changed materially, and you have a clear business ambition to reach one million Mail Online subscribers. You needed an independent view of whether public cloud is the right foundation for the next decade and, if so, which platform.

## What You Asked Rackspace To Do

The scope of Phase 1 was to produce:

- An independent infrastructure discovery of [Client]'s UK estate, plus the Sydney satellite datacentre

- An apples-to-apples cost comparison across AWS, Azure, and GCP

- An application profiling pass across [Client]'s major business applications

- A readiness assessment of the organisation against cloud adoption

- A platform recommendation and the entry point for Phase 2

Phase 1 did not include: landing zone design, migration execution, per-application 7R classification across the full estate, or licensing procurement. Those are Phase 2 activities and are defined in Section 11.

## How We Did It

The work ran over eleven weeks between February and April 2026. The team was one lead consultant, three cloud architects (one per hyperscaler) and a senior engagement manager. The work fell into six phases:

- Mobilisation and kick off: stakeholder mapping, access provisioning, workshop scheduling

- Strategy assessment: foundational workshops, business driver capture, hyperscaler selection criteria

- Automated infrastructure discovery: deployment of Google Cloud Migration Center across the estate, Oracle database assessment via Oracle's DMA tool, SQL Server assessment via a separate tooling pass, network dependency capture, application-to-infrastructure mapping

- TCO analysis: independent pricing of every in-scope server against live cloud pricing APIs, to normalise the comparison across providers and produce as close to an apples-to-apples view as possible; optimisation scenarios; Oracle path modelling

- Cloud service provider selection: [Client Name] set the weightings. Rackspace scored the providers in two passes: an unbiased first pass against market baselines, then a refinement against [Client]'s specific estate to confirm each cloud's benefits are usable in practice, not just on paper.

- Strategy report and this playback

Data was collected between 19 February and 27 March 2026. Nine application workshops were completed with business area owners. The data freeze was 27 March. Anything that changed after that date is flagged inline.

## What The Outcome Is

This report presents:

- An apples-to-apples cost comparison for 3,038 servers across three clouds, with an optimised view that factors in licensing and Oracle migration options

- A readiness score across five dimensions, showing current state and the gap to target

- A primary platform recommendation with validated exceptions

- A concrete Phase 2 entry point

## Scope Versus Actual Discovery

Three numbers matter in this section.

- 2,300 servers: the Statement of Work scope, based on pre-engagement information (VMware only).

- 3,038 servers: the actual in-scope count for Phase 1 assessment, after scope was expanded to cover infrastructure disclosed at kickoff (Proxmox, physical bare metal, appliances, existing cloud). Every one of these 3,038 servers was discovered, profiled where possible, and independently priced.

- 4,500+ servers: the full discovered estate. The additional ~1,500 beyond the 3,038 in-scope subsets were catalogued but not assessed in Phase 1 and are a Phase 2 scope item.

Rackspace absorbed the Phase 1 scope expansion from 2,300 to 3,038 at no additional cost to [Client Name]. This represents a material amount of additional discovery and analysis effort delivered without a revised commercial. The extra ~1,500 servers beyond 3,038 remain out of scope for Phase 1 deliverables and require Phase 2 to assess.

This report covers the 3,038 in-scope servers. Where the full estate is referenced (for context or Phase 2 framing), that is called out explicitly.

## What This Report Covers

The sections that follow cover why cloud makes sense now (Section 3), the estate discovery (Section 4), cost comparison (Section 5), business and application fit (Section 6), the platform recommendation (Section 7), organisational readiness (Section 8), specific challenges and opportunities (Sections 9 and 10), and moving forward into Phase 2 (Section 11). Appendices provide methodology and detail for the technical panel.

# Section 3: Why Cloud, Why Now

## Your Business Drivers

Your decision to explore cloud was framed at kickoff around three business drivers. Everything in this report ties back to these.

### 1. Standardisation and Simplification

You operate across multiple brands with approximately 170 technology staff distributed across seven areas. Each area operates with its own tooling, processes, and standards. You told us at kickoff that only one in twenty projects follows a consistent delivery process. The cost of this fragmentation is slower delivery, higher operational risk, and harder co-ordination on changes that span brands.

Your goal is to converge on a limited set of approved platforms and patterns, eliminate shadow IT, and establish a standardised technology foundation that supports growth without adding proportional complexity.

### 2. Productivity and Cost Optimisation

You have set a target of a ten percent cost reduction in Year 1 without reducing headcount. This requires shifting from fixed, capacity-based cost models to demand-aligned consumption, removing custom systems that provide low value, and replacing bespoke workflows with pre-approved blueprints.

The commercial test is whether cloud adoption translates to financial performance. It only does if cost discipline is embedded from day one, through FinOps practice and clear visibility of spend by platform, product, and environment.

### 3. Automation and Workflow Optimisation

Manual processes limit growth and degrade customer experience. You have identified automation of repeatable, high-volume operational workflows as essential for enterprise-scale operations. The outcome is reduced operational and key-person risk, the ability to scale revenue without linear cost growth, and business teams focused on value creation rather than administration.

Enhanced security and data or AI analytical insights are an expected outcome of this transformation, not a standalone driver. Your early-stage AI work (Genie, AI Insights Agents) will benefit from a cloud platform but is not driving the migration timeline.

## The Case For Acting Now

What would happen if you did nothing? Three contract windows tell that story.

### Converging contracts

| Contract | End date | What happens at expiry |
| --- | --- | --- |
| Reading datacentre (Centre Square) | 30 Nov 2027 | Renegotiation or exit. £386K/yr. |
| Slough datacentre (Digital Realty) | 30 Nov 2027 | Renegotiation or exit. £338K/yr. |
| Sydney datacentre (Equinix) | 30 Jun 2028 | Renegotiation or exit. Flexible contract. £40K/yr. |
| Oracle 24x7 support | Ongoing, perpetual | Near one-way: reinstatement after drop costs 150% plus back-support for lapsed period. |
| Microsoft Enterprise Agreement | 31 May 2027 | Renewal or move to MCA. £137K/yr Windows, £119K/yr SQL. |
| Microsoft Bluesource support | 10 Oct 2027 | Renewal or replacement. £80K/yr. |
| Broadcom VMware support and subscription | Expired / expiring | See Broadcom position below. |

Every contract in this table renews or expires within a two-year window. Extending any of them independently re-locks capital for another period. Co-ordinating exit reduces compounding sunk cost commitments and preserves the option value of a cloud migration.

### Broadcom VMware perpetual licence position (KB Article 429208)

Since Broadcom acquired VMware, the licensing model has changed. You hold perpetual VMware licences with Support and Subscription (SnS) that has expired or is expiring.

This creates a specific risk profile:

#### What continues to work

- ESXi hosts and vCenter continue to operate normally

- No automated shutdown, all virtual machines remain powered on

- All management tasks functional

- All features entitled by the current licence edition remain unlocked

#### What stops working

- No access to the Broadcom Support Portal for patches, security updates, or version releases

- No ability to open support requests

- Security posture degrades over time because patches cannot be retrieved. Multiple actively-exploited zero-day vulnerabilities in VMware ESXi and Workstation have been disclosed in 2025 (CVE-2025-22224, CVE-2025-22225, CVE-2025-22226). [Client]'s ability to patch against newly-disclosed VMware CVEs depends on an active SnS contract, which is not currently in place.

- No new ESXi hosts can be added to the environment

- No major version upgrades without active SnS

- Broadcom has ended perpetual licensing for new purchases. If you ever need to expand or upgrade, the only path is VCF subscription licensing. This is not a scare tactic; it is a factual description of where the VMware estate sits today.

- [PENDING: indicative VCF subscription pricing for [Client]'s estate size, for use in the Complete View in Section 5.]

### Operational fragmentation

170 technology staff across seven operating areas, running different tooling, processes, and standards, is not just an organisational problem. It actively limits what can be done operationally. During discovery, we saw several distinct access patterns (different credential stores, approval chains, and documentation maturity) across business areas and server types. Without a consistent control plane, the cost of any change is amplified across brands.

Public cloud gives you a single control plane by default. That is the platform condition for the standardisation, automation, and cost discipline [Client]'s business drivers require.

## The Financial Case

The on-premises estate runs on capital expenditure. Hardware is bought, depreciated, and refreshed on a cycle.

Cloud runs on operational expenditure: payment follows consumption, month-by-month.

For a business with demand based traffic patterns (elections, breaking stories, sports events), OpEx is a better match. For a business targeting a Year 1 cost reduction, the timing advantage of OpEx matters: it is fully deductible in the period incurred, rather than recovered over asset life. And every pound not committed to the next hardware refresh is capital free to invest in content and subscriber growth.

## The 1M Subscriber Ambition

Your north star is one million Mail Online subscribers. Infrastructure that cannot scale elastically, and operational overhead that scales with headcount, both work against this ambition. A cloud platform removes the infrastructure constraint. The operating model changes described in Section 8 remove the operational one.

# Section 4: Your Estate

## What We Found

This section plays back the discovery so you can recognise your own estate in this report. Where we see surprises or gaps, we flag them here rather than burying them.

## Headline Numbers

| Dimension | Value | Note |
| --- | --- | --- |
| Servers discovered (full estate) | 4,500+ | Across five infrastructure types |
| Servers in scope for Phase 1 | 3,038 | Priced and assessed |
| Applications | 39 | Plus 91 MOL sub-components as migration-planning units within Mail Online |
| Infrastructure types | 5 | VMware, Proxmox, physical, appliance, cloud |
| UK datacentres | 2 | Reading (Centre Square), Slough (Digital Realty) |
| Overseas datacentre | 1 | Sydney (Equinix), flexible contract |
| Discovery coverage | 100% of in-scope | 3,038 of 3,038 via Migration Center plus manual collection |
| TCO data captured | 97.0% | Strong. Sufficient for pricing. |
| Network dependency mapping | 27.7% coverage | 2M+ total connections captured across servers where guest-level collection was possible |
| Software inventory | 51.5% coverage | Identifies key software on half the estate |
| Collection period | 5 weeks | 19 February - 27 March 2026 |

The coverage figures are a deliberate trade-off. Phase 1 achieved breadth (every in-scope server discovered) with moderate depth on software and network dependencies. The depth required for migration execution is a Phase 2 activity. We explain why in the discovery narrative below.

## Database Landscape

The database estate drives a disproportionate share of complexity and cost. You have:

- Oracle: 6 physical RAC servers across 4 clusters (MOL A, MOL B, Atex, CHP), 24 processor licences (perpetual), annual support £650K. Combined raw Oracle storage is approximately 540 TB. Actual data per cluster inventory is approximately 176 TB (around 96 TB production, 80 TB standby replica). The remainder is ASM mirroring, redo and archive logs, and temp tablespaces.

- SQL Server: 49 instances across 29 hosts, 252 cores, 185 databases. 48 Enterprise Edition cores (Reading datacentre, Datacenter edition), 66 Standard Edition cores (Slough). Covered by Microsoft Enterprise Agreement with Software Assurance.

- Other databases: MongoDB, MySQL, PostgreSQL, Redis appear across the MOL estate, each in specific sub-services rather than as estate-wide platforms.

- One critical gap: the MOL B-cluster is the production primary Oracle database and has no DMA assessment data collected. This is the single biggest data gap in the assessment. The Oracle cost estimates that follow are based on provisioned hardware specs, not actual workload. Collecting DMA data on the B-cluster is the highest-priority action for Phase 2.

## Applications

[Client Name] has 39 applications documented across the estate. The top ten by server count account for more than 88 percent of in-scope servers. The remaining 29 applications are mostly single-server editorial tooling, shared services, and supporting infrastructure.

### Top ten applications by server count

| Application | Servers | % of in-scope | What it does |
| --- | --- | --- | --- |
| MOL | 2,206 | 72.6% | Mail Online: the digital platform. 91 identified sub-components including search, commenting, video processing, content creation, advertising, real-time analytics, and the Oracle data layer. |
| CHP | 146 | 4.8% | Circulation Hub Platform. Oracle-backed, publishing operations. Runs across Reading, Slough, and Sydney. |
| WPS | 136 | 4.5% | Web Publishing System. MOL's publishing pipeline. Tightly coupled to MOL Oracle B-cluster. |
| Atex | 109 | 3.6% | Editorial content management for print and digital. Multicast-dependent for cluster discovery. |
| RTA | 41 | 1.3% | Real-Time Analytics for MOL. Many instances significantly overprovisioned. |
| OneVision Suite | 36 | 1.2% | Advertising traffic management. Coupled to ECO3 via SMB. |
| Teamcity | 33 | 1.1% | Build and CI tooling. |
| Zabbix | 33 | 1.1% | Monitoring. |
| ECO3 | 27 | 0.9% | Editorial content orchestration. Active-active architecture, feeds OneVision. |
| Circnet | 18 | 0.6% | Circulation network management. Oracle-backed. |

The remaining 29 applications span:

- Publishing and editorial tooling: Publishing Flight Check, Editorial Applications Team Automation Service, Mediaplanner, Fingerpost (general and Advertising), Wombat, InstantPress, MailPlus Puzzles, Tolkien.

- Shared and supporting services: SolarWinds, Landscape, Cockpit, Oracle Enterprise Manager (slo-aocc), plus a small number of internal reporting and integration tools.

- Retirement candidates flagged during workshops: IBM Lotus Notes DB (legacy collaboration), Atex 5.5 (32-bit, cannot lift to modern cloud), SolarWinds and Zabbix (replaceable by cloud-native monitoring), Landscape (Ubuntu management, candidate for consolidation).

Note on MOL sub-components: the 91 sub-components referenced against MOL (Search, Reader Comments, Video Processing, Content Creator, Single Sign On, Cache Invalidation, Registration, AMP module, Ads, Live Commentary, Legal Tool, Elasticsearch, Redis clusters, and so on) sit within Mail Online as a single application. They are migration-planning units, not separate applications.

Full application profile detail (dependencies, business criticality, workshop findings) for all 39 applications is in the Application Scoping workbook. This report highlights the patterns, not the list.

## What The Workshops Told Us

Nine application workshops were completed across the business areas. The following patterns emerged:

- MOL is a distributed monolith. Many sub-services, many dependencies, but not independently releasable as units. Any MOL migration must be planned as a whole, then executed in tranches defined by data and coupling, not by convenience.

- Oracle is the centre of gravity for multiple applications. MOL, Atex, CHP, and Circnet all land on Oracle. A cloud decision that does not address Oracle is incomplete. See Section 5 for the three paths modelled.

- Atex has a hard technical constraint. Prestige clustering uses multicast. This works inside a datacentre LAN and breaks in most cloud virtual networks. Section 6 explains the three options.

- Retirement candidates surfaced naturally. The workshops did not require a 'what can we kill' question. Application owners volunteered IBM Lotus Notes, Atex 5.5, and Wombat as retirement candidates.

- WPS is tightly coupled to MOL. WPS maintains many sustained Oracle connections to the MOL B-cluster. They must migrate together.

- ECO3 and OneVision also coupled. OneVision reads from ECO3's courier database via SMB. Co-migration group.

- Sydney is independent. The CSP application in Sydney runs on approximately four servers with minimal cross-dependency to UK systems. Flexible contract. Natural early-migration candidate.

## Discovery: What We Actually Did

The discovery process itself revealed the scale of the operational challenge. Deploying Migration Center across 3,038 servers required navigating a varied set of obstacles:

- No common credential mechanism. SSH for Linux (where agent-less collection was possible), a Windows Collection VM running against vCenter for the general Windows estate (WMI was blocked so VMware Tools guest operations was the path), and manual PowerShell per-host for SQL Server DB hosts (Guardicore micro-segmentation). What works for MOL's Linux servers does not work for ANL's Windows estate, and neither approach works for bare metal Oracle or Proxmox hosts.

- Multiple teams, sequential engagement. Infrastructure, database, security, and application teams each owned different parts of the access chain. Each team had its own approval process and timeline. This sequential coordination was the primary cause of delays in reaching guest-level coverage.

- Custom automation built specifically for [Client]'s estate. Off-the-shelf discovery tooling could not handle the spread of infrastructure types and access constraints found in Phase 1. The Rackspace team built bespoke collection automation tailored to [Client]'s specific complexity: per-network-zone handling for MOL and ANL, vCenter path filtering with parallel discovery across multiple vCenters, SSH fallback for VMs without VMware Tools, standalone Linux and Proxmox collection, and physical server import workflows. Database collection ran through separate channels (Oracle via DMA, SQL Server via PowerShell scripts run per-host because Guardicore micro-segmentation blocked WMI). The scripts and handover documentation were provided to [Client]'s team so collection can continue beyond Phase 1.

- [Client Name] Technology team stretched thin. [Client]'s technology teams were managing day-to-day operations alongside discovery support. The varied issues (port approvals, credential provisioning, firewall changes, agent deployments) meant the same small group was context-switching across unrelated problems simultaneously.

What this means for [Client Name]: the discovery experience is direct evidence of the fragmentation flagged at kickoff. Different credential stores, different approval chains, and different levels of documentation across business areas are not abstractions; they directly affected how long it took to reach each server. It also means Phase 2 cannot follow a single-threaded model. Multiple parallel workstreams, each with dedicated resources aligned to specific application groups and client teams, are required to maintain velocity and reach the deeper data coverage needed for migration execution planning.

## Data Gaps and Confidence

### What we have

100% coverage of in-scope servers (3,038 of 3,038 discovered via Migration Center plus manual collection)

TCO-grade data for 97% of the estate (sufficient for pricing across all three clouds)

Network dependencies captured for 842 servers, yielding 2M plus connections (deep but narrow)

Software inventory on 51.5% of servers

Full SQL Server assessment (49 instances, 252 cores, 185 databases)

Oracle DMA on 11 database instances across 7 hosts

### What we do not have, and why

- MOL B-cluster DMA assessment. Production primary Oracle. Coordination constraints during Phase 1 prevented collection. Highest-priority Phase 2 action.

- Network dependency mapping at estate scale (coverage is 27.7%). Guest-level collection depth was the main bottleneck. Deeper mapping is a Phase 2 activity.

- Software inventory at estate scale (coverage is 51.5%). Same bottleneck.

- Workload utilisation data on 1,227 servers without VMware Tools. Pricing for these servers uses provisioned specifications rather than observed utilisation. This produces slightly conservative sizing for VMs and is accurate for bare metal.

The data we have is sufficient for the Phase 1 outcomes (cost comparison, readiness assessment, primary platform recommendation). The data we do not yet have is exactly what Phase 2 needs to begin, and is called out in Section 11.

# Section 5: Cost Comparison

## What This Section Does

This section shows what public cloud will cost, how that compares across AWS, Azure, and GCP, and what the main levers are. It is the section your finance stakeholders will read. The numbers are the starting point for the commercial conversation, not the end of it.

## How We Produced These Numbers

Before getting to the figures, it matters how they were built. We used a seven-step process:

- Data normalisation. The same source data (server specifications, memory, storage, operating system) was fed to all three hyperscalers. No cloud got a different version of [Client]'s estate.

- Architectural benchmarking. Each cloud's own sizing tool (GCP Migration Center, AWS Transform, Azure Migrate) produced right-sized target configurations. The native tools did the sizing. Their outputs are the starting point, not the final answer.

- AI logic audit. We audited the SKU mappings each tool produced. Different tools use different optimisation logic. We checked what each tool assumed and why.

- Bias mitigation. To remove tool-specific bias, we re-priced every recommended SKU against the official cloud pricing APIs (AWS Price List API, Azure Retail Prices API, GCP Billing Catalog API). This produced a validated, normalised view. The provider-native outputs are kept for internal validation only.

- Two pricing pillars. We report on-demand (the clean baseline) and 3-year committed (the realistic commitment for an organization of your scale). One-year commitments are deprioritised as a less attractive option.

- Partner and commercial pricing is a separate layer. This sits on top of the normalised baseline. Where commercial offers are not yet received, the layer is flagged [PENDING] rather than inferred.

- Oracle scenarios are modelled separately. Oracle has three fundamentally different migration paths, each with different pricing mechanics. These are separated rather than averaged into compute cost.

This methodology is what gives the figures credibility when each cloud provider presents their own view directly. Your technical panel can verify any number against a specific API response and data normalisation step.

## What Is Included and Excluded

### Included in every figure below

- Compute (vCPU and memory) for each in-scope server

- Block storage (SSD class, IOPS-matched across clouds at 80,000 IOPS per disk where needed)

- Operating system licensing at pay-as-you-go rates unless otherwise stated

- Estimated network cost (5% of compute plus storage, as a cloud estimate, since actual egress requires traffic flow data not collected in Phase 1)

### Excluded from the headline figures

- Network egress across the public internet. Per-GB rates (API-verified, London):

  - AWS $0.09/GB for the first 10TB/mo tapering to $0.05/GB above 150TB/mo;

  - Azure $0.08/GB for the first 10TB tapering to $0.04-0.05/GB at high volumes;

  - GCP Premium Tier $0.12/GB for the first 1TB, $0.11/GB for 1-10TB, $0.08/GB at 10TB+.

  - At low-to-mid monthly volumes GCP is materially more expensive; at high volumes all three converge.

- Backup and disaster recovery, which require RPO and RTO decisions per application (Phase 2).

- Support contracts, which vary by support tier selection.  VMware support costs are not included in the on-premise baseline.

- Migration labour, which is out of scope for Phase 1.

- Licensing optimisation (BYOL), which is modelled separately below because it depends on your Software Assurance status.

- Managed service substitutions (e.g. moving Oracle to PostgreSQL), which require application profiling and are modelled as optimisation scenarios.

- Landing zone infrastructure and interconnect, which depend on landing zone design.

## Apples-to-Apples Baseline (London, 3-Year Committed, Per Month)

The table below shows the same 3,038 servers priced on each cloud at the sizing each cloud's own tool recommended.

| Pricing model | GCP | AWS | Azure |
| --- | --- | --- | --- |
| Pay-as-you-go monthly | 311,264 | 328,223 | 424,831 |
| 3-year committed monthly | 186,974 | 190,285 | 274,881 |

On a 3-year committed basis in London, GCP is the cheapest by approximately 2% over AWS. Azure is approximately 47% more than GCP.

- The cost spread reflects how each cloud's own assessment tool sized the same source workload. GCP Migration Center produced the smallest vCPU allocation at 32% of source, using custom instance shapes down to 1 vCPU.

- AWS Transform sat at 49%.

- Azure Migrate sat at 53%, typically assigning F2s_v2 (2 vCPU minimum) across most of the estate because its sizing algorithm did not generate 1-vCPU SKUs for production workloads, and F-series SKU availability with 3-year Reserved Instance coverage in London shapes the options available.

- Burstable VM families were excluded across all three clouds by team agreement as not suitable for production workloads.

SKU choices and workload mappings on any of the three clouds can be refined with deeper Phase 2 assessment. The numbers above are the right baseline for a Phase 1 independent comparison (same input, each cloud's own tool output, normalised against pricing APIs), not a ceiling or floor for each cloud's commercial position.

## Regional Comparison

Three regions were assessed per cloud to give geographic context.

| Region | GCP | AWS | Azure |
| --- | --- | --- | --- |
| London | 186,974 | 190,285 | 274,881 |
| NL / Ireland | 170,918 | 181,298 | 270,912 |
| Frankfurt | 189,185 | 192,329 | 277,332 |

NL / Ireland is the cheapest across all three clouds. London is approximately 9% more expensive than NL / Ireland for GCP (this is a consistent pattern, not a [Client]-specific premium).

| Purpose | GCP region | AWS region | Azure region |
| --- | --- | --- | --- |
| Primary | europe-west2 (London) | eu-west-2 (London) | uksouth |
| Secondary | europe-west4 (Netherlands) | eu-west-1 (Ireland) | northeurope (Ireland) |
| Tertiary | europe-west3 (Frankfurt) | eu-central-1 (Frankfurt) | germanywestcentral |

GCP does not have an Ireland region so Netherlands is used as the closest equivalent. London remains the primary choice given regulatory and latency considerations for your user base.

## Component Breakdown (London, PAYG, Per Month)

This table explains where the cost differences come from.

| Component | GCP | AWS | Azure |
| --- | --- | --- | --- |
| Compute | 196,025 | 228,907 | 228,410 |
| Storage | 91,005 | 63,587 | 159,446 |
| OS licence | 9,883 | 21,105 | 17,582 |
| Network (5%) | 14,351 | 14,625 | 19,393 |
| Total PAYG | 311,264 | 328,223 | 424,831 |

What to notice:

- GCP compute is cheapest because custom instances allow independent CPU and memory sizing. GCP allocated 32% of source vCPU versus AWS 49% and Azure 53%.

- Storage cost differences reflect each cloud's storage product pricing model rather than sizing choices.

  - AWS gp3 has a relatively low per-GB rate with separately priced IOPS and throughput.

  - GCP Balanced Persistent Disk and Hyperdisk Balanced are per-GB at a higher unit rate.

  - Azure assigns Premium SSD with tiered disk sizes (each tier has a minimum GB), which rounds small disks up to the next tier.

- OS licence costs differ because GCP allocates fewer vCPUs (less Windows per-vCPU licensing) and Azure has a mid-range allocation. The number scales with vCPU count, not server count.

## Beyond The Baseline: Optimisation and Options

The baseline covers compute, storage, OS licence, and internal network. Several items sit on top. Some are mandatory additions for a full view of cloud cost (Oracle, SQL); others are optional levers that reduce cost if [Client Name] meets the conditions (BYOL, storage tiering).

### Mandatory additions (in Complete View)

| Item | GCP | AWS | Azure | Condition |
| --- | --- | --- | --- | --- |
| Oracle (Exadata@Cloud, Option A) | +42,909/mo | +42,909/mo | +42,909/mo | All three clouds offer Exadata@Cloud in London, identical OCI pricing. |
| Oracle support (retained under BYOL) | +54,167/mo | +54,167/mo | +54,167/mo | £650K/yr Oracle support contract retained under BYOL on all Option A/B paths. |
| SQL Server surcharge | +15,284/mo | +14,286/mo | +14,286/mo | Nets to zero if SA confirmed (BYOL). Currently included pending SA confirmation. |

### Optional levers

| Lever | GCP impact | AWS impact | Azure impact | Condition |
| --- | --- | --- | --- | --- |
| Windows BYOL | -7,220/mo | -8,605/mo | -17,529/mo | Requires active Software Assurance. Different mechanics per cloud. In Complete View. |
| Storage tiering (non-prod to HDD) | -18,603/mo | -10,261/mo | -9,964/mo | Apply to 336 TiB non-prod. GCP has widest SSD-HDD gap. In Complete View. |
| RHEL BYOL | -4,935/mo | -5,400/mo | -4,935/mo | 153 servers via Red Hat Cloud Access. Not in Complete View (requires client confirmation). |
| Azure Dev/Test | n/a | n/a | -2,475/mo | 49 non-prod Windows. Requires EA and Visual Studio subscriptions. Not in Complete View. |

Windows BYOL mechanics differ materially per cloud:

- Azure uses Azure Hybrid Benefit (AHB). This is a pricing toggle. No dedicated infrastructure required. It gives the largest saving because it has no infrastructure overhead.

- GCP requires Sole Tenant Nodes. The Sole Tenant premium is 10% on compute pricing. Windows BYOL also requires the N-series machine family, which is more expensive than the E2 baseline used elsewhere in the TCO. The -7,220/mo is the net saving after the Sole Tenant premium and N-series uplift are deducted.

- AWS requires Dedicated Hosts. The -8,605/mo is the net saving after the Dedicated Host cost premium is deducted from the gross BYOL saving.

Important constraint on Windows BYOL on AWS and GCP: Microsoft's Listed Provider rules (October 2019) require that BYOL Windows licences be acquired before 1 October 2019, or true-upped under an Enterprise Agreement that was in force before that date. Only Windows Server 2019 and earlier is eligible. Windows Server 2022 is not eligible for BYOL on AWS or GCP regardless of Software Assurance status.

Of [Client]'s 225 in-scope Windows servers:

  - 160 run Server 2019 (BYOL eligible, subject to EA chain verification)

  - 65 run Server 2022.

Those 65 Server 2022 VMs cannot use [Client]'s existing Windows licences on AWS or GCP. Azure AHB has no such restriction and accepts Server 2022 BYOL normally. This materially affects the BYOL saving realised on AWS and GCP.

## Oracle Paths

Oracle is the single largest cost variable. There are three paths, and they each have very different characteristics. The recommended path for [Client] is Exadata@Cloud (Option A) as the primary way. PostgreSQL modernisation (Option C) is a deeper strategic decision that requires careful later phase planning.

| Path | GCP monthly cost | AWS monthly cost | Azure monthly cost | Key points |
| --- | --- | --- | --- | --- |
| A: Exadata@Cloud (primary path) | £42,909 | £42,909 | £42,909 | All three clouds offer Oracle Database@Cloud in London. Oracle Database@AWS launched March 2026. Same OCI pricing across all three. Data layer stays on Oracle. Lowest migration risk. |
| B: Oracle on IaaS VMs (no RAC, Data Guard HA) | £62,162 | £48,194 | £48,194 | Customer manages Oracle directly. Loses RAC. Uses Data Guard for HA. Cost varies by cloud because underlying VM pricing differs. |
| C: PostgreSQL modernisation | £51,592 (AlloyDB) | £37,687 (Aurora) | £31,899 (Flex Server) | Each cloud's managed PostgreSQL. All with HA. Requires significant application refactoring and PL/SQL conversion. Phase 2 validation essential. |

Important context for Option C (PostgreSQL): this is a Phase 2 strategic decision, not a Phase 1 action. Each hyperscaler has its own transformation support paths (AWS SCT and DMS, Azure Database Migration Service, Google Database Migration Service plus AlloyDB's Oracle compatibility mode). The saving potential is material, but the path requires: full DMA assessment of the MOL B-cluster (currently uncollected), per-cluster PL/SQL conversion scoping, application-by-application impact assessment, and business prioritisation.

Oracle support treatment under each path:

- Option A (Exadata@Cloud, BYOL): you must retain your £650K/yr Oracle support contract while using Exadata@Cloud. BYOL on Oracle requires active support.

- Option B (Oracle on IaaS BYOL): same. £650K/yr retained.

- Option C (PostgreSQL): once Oracle is fully decommissioned, support can be dropped. This is the only path that eliminates the £650K/yr support line. Reinstatement is penalised (150% of last fee plus back-support), so the decision to drop must be final.

## Atex Multicast Cost Impact

The Atex multicast constraint (architectural detail in Section 6) has a cost dimension worth noting here. On AWS, native Transit Gateway multicast adds a small charge (tens to a few hundred pounds per month at [Client]'s traffic profile) from attachment and data-processing fees. On GCP and Azure, the only native workaround is VMware-on-cloud (GCVE, AVS); post-October 2025 these require customer-provided VCF subscription licences on top, making that path materially more expensive than either the AWS native route or a vendor-led Atex unicast refactor.

## The Complete View (London, 3-Year Committed)

This is the full picture: baseline compute and storage, operating system licensing, storage tiering savings, Windows BYOL, SQL Server BYOL (via License Mobility on AWS and GCP, AHB on Azure), Oracle Exadata@Cloud (Option A), Oracle support retained under BYOL, and indicative internet egress. Complete View assumes Microsoft Software Assurance in place for both Windows Server and SQL Server; formal confirmation is pending from Bluesource. All component lines are monthly final row is annual.

| Component | GCP | AWS | Azure |
| --- | --- | --- | --- |
| Baseline 3yr | £186,974 | £190,285 | £274,881 |
| - Windows BYOL (SA assumed) | -£7,220 | -£8,605 | -£17,529 |
| - Storage tiering (non-prod to HDD) | -£18,603 | -£10,261 | -£9,964 |
| + Oracle Option A (Exadata@Cloud) | +£42,909 | +£42,909 | +£42,909 |
| + Oracle support (£650K/yr, retained under BYOL) | +£54,167 | +£54,167 | +£54,167 |
| Complete View subtotal (monthly, pre-egress) | £258,227 | £268,495 | £344,464 |
| + Indicative internet egress at 100TB/month | +£6,274 | +£5,889 | +£4,832 |
| Complete View (monthly) | £264,501 | £274,384 | £349,296 |
| Complete View (annual) | £3,174,012 | £3,292,608 | £4,191,552 |

Note: SQL Server assumed as BYOL in baseline (SA + License Mobility); avoids approximately £15K/mo GCP, £14K/mo each AWS/Azure of cloud-provider license-included surcharge.

Complete View with indicative egress is the reference number for client comparison. The 100TB/month is illustrative; actual [Client Name] egress depends on Akamai CDN cache hit rate and origin traffic patterns, and can be quantified by Phase 2 given traffic flow data.

GCP remains the cheapest by approximately £10K/mo over AWS (around 3.7%). Azure sits approximately £85K/mo higher than GCP, still driven mainly by the sizing methodology gap rather than by pricing. Azure does offset part of this through the strongest Windows BYOL mechanism (AHB).

Notes on what is in and out:

- RHEL BYOL (-4,935 to -5,400/mo) and Azure Dev/Test (-2,475/mo) are not in the Complete View because both require client confirmation. If both are confirmed, Azure Complete View drops to approximately £338,685/mo.

- Enterprise support is excluded from this headline because it is a support tier decision, not a platform cost.

## Status Quo: On-Premises Baseline

For the business case, the cloud figures must be compared to the cost of doing nothing. Your updated IT Costs workbook captures the on-premises annualised cost at £3.64 million per year (approximately £303,000/mo). This is the first time the hardware and storage capital expenditure has been populated:

| Category | Annualised | Notes |
| --- | --- | --- |
| Compute and storage (capex depreciated over 5yr + maintenance) | £547,761 | Server hardware capex £1.26M, storage capex £1.45M |
| Software licensing | £1,440,681 | Includes Oracle support (£650K), SQL (£119K), Windows (£137K), Linux (£91K), security tooling (£444K worst case) |
| Facilities and network | £879,900 | Reading, Slough, Sydney, inter-site, internet |
| Operations | £688,000 | NCS database support (£568K), vendor support, 1 FTE infra management |
| Contracts and commitments | £80,000 | Microsoft Bluesource support |
| Grand total | £3,636,342 | Per year |

This figure is the on-premises anchor. It does not include the Broadcom VCF subscription cost that will apply when new or expanded VMware hosts are needed. It also does not include hardware refresh beyond the existing 5-year depreciation schedule.

The Complete View with indicative egress for GCP (£264,501/mo = £3.17M/yr) is approximately £462K/yr below this baseline. For AWS, approximately £344K/yr below. Azure is approximately £555K/yr above the on-premises baseline. These comparisons exclude migration cost (out of scope for Phase 1 per SoW) and exclude optimisation levers that require client confirmation.

## Commercial Layer (Partner Discounts and Credits)

[PENDING: partner discount and migration credit proposals from AWS, Azure, and GCP. Sales team is co-ordinating with partner leads. Not included in the figures above. Will be added as a distinct layer once received, labelled as commercial rather than retail.]

|  | AWS | GCP | Azure |
| --- | --- | --- | --- |
| Total Cloud Spend (3-yr Reserved yearly) | $ 3,024,396 | $ 2,243,685 | $ 4,368,962 |
| Total Partner Payment(A) (discount against Rackspace Fees) | $ 1,757,600 | $ 1,080,498 | xxxx |
| Total Cloud Credits (B) (discount against [Client Name]’s consumption) | $ 756,099 | $ 745,192 | - |
| Total funding in USD (A+B) | $ 2,513,699 | $ 1,825,690 | - |
| Total funding in GBP | £ 1,897,842 | £ 1,378,396 |  |

The funding calculations presented in the table above, are based on the following assumptions & considerations

- 3-yrs Reserved yearly cloud consumption in USD for London region is taken as a baseline for this calculation, in alignment with the general funding/incentive program provided from the respective Hyperscalers.

- The estimated cloud consumption & the commensurate funding provisions thereof, is likely to change, as per the findings from the upcoming Phase 2 assessment.

- Currency conversion at market prevalent rates 1 USD = 0.755 GBP

# Section 6: Business and Application Fit

## What This Section Does

This section shows how your applications map to cloud. What constraints they carry, how they group for migration, and where the gaps are. It is about the applications themselves, not about which cloud wins. That is Section 7.

## How Applications Were Assessed

Each of the 39 applications was assessed against four criteria:

- Infrastructure fit: the underlying platform (VMware, Proxmox, physical, appliance, cloud) and what each cloud needs to support it

- Database dependency: Oracle RAC, SQL Server edition, MongoDB, MySQL, PostgreSQL, Redis

- Operating system: Linux family and version, Windows version, special cases (Solaris, AIX if any)

- Known technical constraints: multicast, bare metal, specific licensing requirements, vendor certification of cloud platforms

The 39 applications were then grouped into migration cohorts based on readiness, dependencies, and complexity.

## Technical Constraints

Three constraints shape the migration approach. Each is explained below with what it means for cost and the recommended path.

### Multicast (Atex Prestige)

Atex Prestige uses multicast for PrManager cluster node discovery. Multicast is a LAN-era pattern. Cloud virtual networks handle it differently:

AWS supports multicast natively via Transit Gateway (generally available in London).

GCP and Azure do not support multicast natively. VMware-on-cloud (GCVE, AVS) is not a viable workaround for [Client Name], because the VMware exit is itself a driver for this engagement.

This means Atex has two practical paths on GCP or Azure: refactor to unicast (Atex vendor confirmation required) or stay on AWS. AWS is the default path for Atex unless unicast refactor is confirmed. This is a Phase 2 action with direct architectural consequence.

### Oracle RAC

Six physical Oracle RAC servers across four clusters (MOL A, MOL B, Atex, CHP). RAC requires shared storage and specific cluster interconnect features that a general-purpose cloud VM does not provide. All three clouds now offer Oracle Database@Cloud (Exadata) in London: Azure (launched earlier), GCP (launched in 2025), AWS (launched March 2026). Same OCI pricing across all three. Details in Section 5.

### SQL Server Datacenter Edition

Reading DC runs Datacenter edition, Slough runs Standard. Datacenter is materially more expensive per core when priced license-included. BYOL with Software Assurance zeroes out this surcharge. Azure AHB is the simplest mechanism. AWS and GCP require Dedicated Hosts or Sole Tenant Nodes respectively. Windows Server 2022 has additional BYOL restrictions on AWS and GCP (see Section 5).

## The 7Rs, Explained

The 7Rs are the standard classifications for what to do with an application when migrating to cloud:

- Retire: the application or server is no longer needed, decommission it.

- Retain: keep it where it is (on-premises) for now.

- Relocate: move it to a cloud-hosted hypervisor that mirrors the on-premises environment.

- Rehost: lift and shift to cloud VMs. Minimal change.

- Replatform: move to cloud with modest changes (for example, managed database instead of self-managed, or upgrading operating system to the latest version.)

- Repurchase: replace with a SaaS equivalent.

- Rearchitect/Refactor: re-engineer the application to use cloud-native services.

A per-application 7R classification across the full estate is a Phase 2 activity. What we can do now is highlight areas that stood out during the workshops as candidates for each category.

## Areas Of Interest From The Workshops

The following application-level opportunities emerged during the nine application workshops. They are framed as starting points for Phase 2 discussion, not as finalised 7R decisions.

- Retire candidates: IBM Lotus Notes (legacy collaboration, SaaS replacement natural path), Atex 5.5 (32-bit, incompatible with modern cloud VMs, retire when Atex 6 complete), Wombat (narrow use, owners flagged for review), Mediaplanner (aging custom tooling).

- Repurchase candidates: IBM Lotus Notes replacement (Microsoft 365 or Google Workspace). SolarWinds and Zabbix can be replaced by cloud-native monitoring as part of landing zone build.

- Replatform candidates: the 49 SQL Server instances are candidates for managed SQL (Cloud SQL, RDS, Azure SQL). Oracle is a special case covered in Section 5.

- Rehost candidates: MOL sub-components without tight Oracle coupling (many of the 91 identified sub-services). Standard business applications with modern OS. Shared services and tooling.

- Rearchitect candidates: MOL RTA (Real-Time Analytics) significantly overprovisioned. Kubernetes adoption path already started at [Client Name] (PoC in flight).

The list above reflects application owner input captured during workshops and is indicative. Final 7R classification per application is a Phase 2 activity.

## Migration Cohorts

Applications group into five cohorts based on readiness, complexity, and dependencies. These are indicative at Phase 1 level. Phase 2 refines them into a detailed release plan.

| Cohort | Description | Apps | Servers | Characteristics |
| --- | --- | --- | --- | --- |
| Cohort 0 - Foundation | Infrastructure services that must exist before application migration | 5 | 95 | AD, monitoring, security, config management |
| Cohort 1 - Quick Wins | Low-complexity, low-dependency applications | 13 | 63 | Independent apps, well-discovered, clear cloud fit |
| Cohort 2 - Planned Migration | Moderate complexity with manageable dependencies | 17 | 425 | Some database dependencies, cross-app connections, mixed infrastructure |
| Cohort 3 - Complex Migration | High-complexity applications needing detailed planning | 2 | 2,342 | MOL (2,206) + WPS (136). Oracle dependency, 91 sub-services |
| Cohort 4 - Business Decision Required | Applications where a strategic decision is needed first | 2 | 113 | Atex (109) + InstantPress (4). Multicast, Oracle, vendor dependency |

## Co-Migration Groups

Discovery and workshops identified applications that must migrate together. Splitting them breaks data paths or operational coupling.

| Group | Applications | Reason | Cohort |
| --- | --- | --- | --- |
| MOL Core | MOL + WPS | WPS maintains sustained Oracle connections to MOL B-cluster | 3 |
| ECO3 and OneVision | ECO3 + OneVision Suite | OneVision reads from ECO3 courier database (SMB, port 445, network-confirmed) | 2 |
| Atex Publishing | Atex + InstantPress | InstantPress produces PDF output from Atex content | 4 |

## What This Means In Practice

- Mail Online defines the programme timeline. Any Phase 2 plan that does not address MOL is incomplete.

- Cohort 4 (Atex, InstantPress) requires a decision before it can progress: unicast support on Atex, or accept the VMware-on-cloud cost. This is a small cohort but it blocks Atex migration entirely until resolved.

- Quick wins exist. Cohort 1 is 13 applications, 63 servers, deliverable early. These give you measurable cloud cost savings and operational experience before the complex work begins.

- Sydney datacentre is the smallest and most independent workload, with a flexible contract. It is a natural early-migration candidate and provides a DC cost offset proof point.

## Gaps In The Application Assessment

- Per-application 7R classification across the full estate: Phase 2 scope.

- Detailed PL/SQL conversion scoping for Oracle modernisation: Phase 2 scope, highest-value workstream.

- Deep dependency mapping for MOL's 91 sub-components: Phase 2 scope.

- Validation of workshop findings with application owners who were not available during Phase 1: Phase 2 scope.

- Atex vendor engagement on unicast support: Phase 2 action with direct cost impact.

# Section 7: Hyperscaler Recommendation

## What This Section Does

This section reaches the conclusion. It draws on the cost evidence in Section 5 and the application fit evidence in Section 6 to make a clear platform recommendation for [Client Name]. The scoring summary below shows how each cloud performed across the weighted evaluation criteria. The recommendation that follows is the one Rackspace believes best fits [Client]'s situation, and why.

## Weighted Scoring Summary

The weighted hyperscaler scoring was applied across thirteen strategic goals, with weightings [Client Name] signed off at the start of the engagement. Scoring was refined during Phase 1 as commercial data arrived and practical constraints were validated.

| Strategic goal | AWS | Azure | GCP | Winner | Notes |
| --- | --- | --- | --- | --- | --- |
| Uptime | 4.2 | 4.2 | 4.2 | Tied | All three offer 99.99% SLA at multi-zone deployment. |
| Reliability | 4.8 | 4.6 | 4.4 | AWS | Longest operational track record, broadest service catalogue. |
| Scalability | 4.8 | 4.5 | 4.8 | AWS / GCP | Both offer strong elastic demand handling. |
| Security | 4.1 | 4.8 | 4.6 | Azure | Azure Entra ID and Sentinel strongest. |
| Performance | 4.7 | 4.3 | 4.3 | AWS | Best for HPC and specialist compute workloads. |
| Business Analytics | 4.3 | 4.0 | 4.6 | GCP | BigQuery is the clearest native advantage. |
| Transparency | 4.0 | 4.0 | 4.2 | GCP | Marginal advantage, not decisive. |
| Cost | 4.7 | 4.1 | 4.2 | AWS | TCO dial reflects Complete View. |
| Sovereignty | 3.7 | 3.7 | 3.4 | AWS / Azure | Same jurisdictional exposure across all three. |
| Business Fit | 4.5 | 4.5 | 3.7 | AWS | Partner ecosystem, enterprise relationships, skills market. |
| Sustainability | 3.3 | 4.0 | 5.0 | GCP | Genuine differentiator but low-weight. |
| Licensing | 3.5 | 4.3 | 3.0 | Azure | AHB remains Azure's strength on paper, but limited value to [Client]. |
| Velocity | 4.4 | 4.6 | 4.6 | Azure / GCP | DevOps tooling, IaC maturity, managed service abstraction. |
| Weighted score | 4.3 | 4.3 | 4.2 |  |  |

Overall fit against [Client]'s weightings (% of maximum possible): AWS 85.0%, Azure 85.6%, GCP 83.4%. Azure narrowly leads by 0.6 percentage points over AWS; GCP sits 2.2 points behind Azure. No cloud is decisively ahead.

Three observations on the matrix:

- Azure narrowly leads to an overall weighted score. AWS is within 0.6 percentage points. GCP sits 2.2 percentage points behind. No cloud is decisively ahead on scoring alone.

- Scoring refinements applied during Phase 1 include: Uptime parity confirmed across all three, TCO dial updated to reflect actual Complete View numbers, Windows Server 2022 BYOL restrictions on AWS and GCP captured in BYOL Flexibility, AHB practical benefit to [Client]'s use case scored as low in Hybrid Licensing Benefits (Azure Migrate's own recommended SKUs are almost all below the AHB 8-core minimum, with only 9 of 234 Windows servers at 8 vCPU or above).

- Each cloud has genuine strengths: Azure on Security and Licensing mechanism, AWS on Reliability, Performance, Cost, and Business Fit, GCP on Business Analytics, Transparency, and Sustainability.

The matrix tells [Client Name] none of the three clouds is technically unfit. It does not decide the platform on scoring alone. Three factors outside the weighted scoring tip the recommendation.

## The Recommendation

### Primary platform: AWS.

AWS is the path of least resistance for the specific challenges [Client Name] has in its estate. The rationale:

- Atex multicast is a capability gap on GCP and Azure. AWS supports multicast natively via Transit Gateway. GCP and Azure do not. The workaround (VMware-on-cloud overlays: GCVE on GCP, AVS on Azure) contradicts [Client]'s VMware exit strategy. That leaves GCP and Azure with two options for Atex: vendor-dependent unicast refactor, or accept Atex cannot migrate as-is. AWS sidesteps this entirely.

- Video streaming is already on AWS. AWS Elemental is in live production for Mail Online. Moving it creates cost and risk without benefit.

- Cost position is competitive with GCP (see Section 5 Complete View). AWS is +3.7% over GCP, within the range hard constraints can offset. Azure sits at +32.1%.

- Windows Server 2022 BYOL trade-off is manageable. Microsoft's Listed Provider rules block Server 2022 BYOL on AWS and GCP; Azure AHB accepts Server 2022. But Azure Migrate's own recommended SKUs for [Client]'s Windows estate are almost all 2 vCPU. Only 9 of the 234 Windows servers have Azure-recommended SKUs at 8 vCPU or above. Under AHB's eight-core minimum rule, the other 225 servers would consume eight licence cores each to cover a one or two vCPU workload, wasting licence capacity. Azure's AHB advantage at [Client]'s actual Azure sizing is close to nil in practice.

- Largest partner ecosystem and skills market. This matters for Day 2 operations and for the upskilling-with-partner-assistance model that fits [Client]'s cost target (10% reduction, no headcount cuts).

- Scoring is a near-tie. Weighted scores (1-5 scale): Azure 4.3, AWS 4.3, GCP 4.2. Azure narrowly leads by 0.6 percentage points. Second on scoring, second on cost, first on constraints: AWS is the best overall balance.

## Exceptions and Retained Placements

A single-platform recommendation does not mean a single-platform estate. Two specific exceptions are validated by evidence:

- Commercial data analytics stays on GCP. You already run this on GCP. BigQuery's serverless analytics, tight integration with your existing data pipelines, and the operational knowledge your team has built are genuine assets. Moving this to AWS creates cost and disruption for no benefit. Retain.

- Video streaming stays on AWS. Mail Online's video workflows use AWS Elemental today. This is a working service, not a future decision. Retain.

This is 'primary platform with validated exceptions', not multi-cloud strategy. The test for an exception is: does a specific workload have a material technical or operational advantage on another cloud, and is that advantage persistent? For the two above, yes. For everything else, AWS.

## What The Recommendation Means In Practice

- Primary cloud for new workloads: AWS

- Target for migration of the 3,038 in-scope servers: AWS (except retained items)

- Commercial data analytics: continues on GCP

- Video streaming: continues on AWS (already there)

- No wholesale multi-cloud operation. The Cloud Platform Team builds one landing zone (AWS), operates one primary cloud, and manages the GCP analytics environment as a secondary estate.

## Mail Online Needs Joint CPO and CTO Sponsorship

Mail Online is the largest application in scope and the commercial centrepiece. Because its product decisions sit with the CPO and its infrastructure sits with the CTO, the MOL migration path touches both executive domains. Specific decisions that benefit from dual endorsement: the Oracle modernisation path, sub-component sequencing, and any re-architecture choices.

Structuring programme governance with both sponsors visible from the start reduces the risk of mid-programme misalignment.

## A Note On Confidence Level

The scoring spread is very narrow.

On a 1-5 scale:

- Azure 4.3

- AWS 4.3

- GCP 4.2.

Expressed as fit against [Client]'s weightings:

- Azure 85.6%

- AWS 85.0%

- GCP 83.4%

The total spread from highest to lowest is 2.2 percentage points.

Cost positions GCP cheapest, AWS close to GCP, Azure materially higher.

The hard constraints (Atex multicast, video streaming continuity) point to AWS, and the Windows Server 2022 BYOL trade-off on Azure is narrowed in practice by AHB's 8-core minimum against [Client]'s SKU profile.

Rackspace is confident on AWS primary because the constraints and ecosystem fit break the near-tie on scoring.

Even if Atex confirms unicast support for Prestige 6X, moving Atex to unicast is itself a workstream with its own configuration, testing, and cutover cost. On AWS, Atex migrates without that rework because multicast is supported natively. The recommendation is therefore resilient rather than fragile.

# Section 8: How Ready Is [Client Name]

## What This Section Does

Readiness is about whether [Client Name] can execute a cloud migration, not whether cloud is the right choice. This section assesses your current state across five dimensions, describes the target, and lists the gaps that Phase 2 and the early programme need to address.

## The Readiness Scale

Each dimension is scored from 1 to 5:

1: No activity or planning in place

2: Early awareness, some informal activity

3: Documented approach, not consistently applied

4: Consistent practice, actively managed

5: Optimised, measured, continuously improved

The scale measures cloud-adoption readiness specifically. It does not capture overall team capability or enterprise domain expertise. [Client]'s infrastructure organisation has deep experience in VMware, Oracle, physical networking, F5 load balancing, and on-premises Windows/Linux operations. Those strengths are not what this assessment scores.

The scale is a maturity indicator, not a grade. Organisations running on-premises enterprise estates typically sit between 1 and 3 on this scale before a cloud transformation. Getting to 4 across the board is the outcome of the first phase of transformation, not a precondition.

## Current State

| Dimension | Areas assessed | Average score | Current state summary |
| --- | --- | --- | --- |
| Business | 10 | 2.5 | Business objectives clarity is strong and cloud/hypervisor strategy is in flight (this engagement). Weaker on operating model definition and value management. |
| Governance | 3 | 3.0 | CMDB is reasonably maintained; service delivery management is documented; supplier management is mature. Highest-scoring dimension. |
| Operations | 4 | 1.8 | Disaster recovery planning and cross-brand monitoring consistency are the main gaps. |
| People | 4 | 1.2 | Cloud-specific skills and training are at the earliest stage: no formal cloud training plan yet, Cloud Centre of Excellence boundaries still forming. |
| Security | 3 | 2.0 | CISO is engaged in cloud decisions. Shared responsibility model and cloud-native GRC practice are early-stage. |

Overall readiness: approximately 2.1 of 5. Consistent with an organisation at the start of its cloud journey.

## What Each Dimension Means In Practice

### Business (2.5)

Your business objectives are clear: one million MOL subscribers, tech stack standardisation, operational refreshes, consolidation onto virtual platforms, flexibility for projects with partner support, CapEx to OpEx. You have hypervisor and cloud strategy assessment in flight (this engagement).

The gaps: cloud objectives commitment (specific workloads, committed timelines), value management (CFO, COO, CISO buy-in beyond the CTO), IT strategy explicitly linking cloud to business outcomes.

The CTO is making the case across the business. The gap is translating that into a documented IT strategy with signed-off investment and capability-building plan.

### Governance (3.0)

Your strongest area. You have a reasonably maintained CMDB, documented service delivery management, and mature supplier relationships with AWS, Azure, and GCP (though the AWS relationship follows a 'cloud island' model rather than a governed landing zone). Portfolio management and application inventory practices exist. Update cadence could be tighter.

### Operations (1.8)

This is where the fragmentation described in Section 3 shows up operationally:

- Disaster recovery planning: captured in the Cloud Readiness Assessment questionnaire (ranked 1/5), where application owners noted they often cannot clearly distinguish high availability, backup, and business continuity in their DR planning.

- Operating model: multiple third parties operate across the estate (NCS for databases, outsourced SOC for security monitoring, web caching vendor support, COTS vendor dependencies). Each adds coordination overhead.

- Monitoring: not consistent across brands. SolarWinds, Zabbix, application-specific tooling.

- Change management: workshops and stakeholder interviews confirmed that formal change process exists but is applied inconsistently across business areas.

### People (1.2)

Lowest score. No formal cloud training plan. A Cloud Centre of Excellence has not been formed, though the infrastructure team manages cloud accounts today with boundaries and processes that need development. Roles and job descriptions have not been adapted for cloud delivery. The implication: even if infrastructure moves to cloud, the operating model for running it is not yet in place.

This is addressable but requires time and investment. Partner-assisted during transition, progressively upskilling your own teams, is the typical path.

### Security (2.0)

The CISO is engaged in cloud decisions. Shared responsibility in cloud is not yet well understood within the teams who will operate workloads. Governance, risk, and compliance practice is early-stage. Packet inspection exists on internet-facing traffic but not internally. Privileged Access Management (PAM) tooling is not standardised.

A focused security assessment is recommended for Phase 2 rather than inferring security posture from the current five-dimension questionnaire.

## Network and Connectivity (Additional Dimension)

The five dimensions above are the standard readiness framework. For [Client] specifically, network and connectivity warrants explicit attention:

- Multi-site connectivity: two UK datacentres plus Sydney, with inter-site links. Cloud landing zone design has to accommodate these and the eventual interconnect to cloud regions.

- CDN integration: Akamai handles presentation layer caching today. How it integrates with cloud origins is a Phase 2 design question with cost implications.

- DNS migration: same physical servers are registered under both .int and .hsk zones, which means two DNS records per server.

- Load balancer modernisation: F5 (corporate) and Zeus/Ivanti vTM (MOL) are hardware load balancers today. Replacing with cloud-native is a significant modernisation opportunity.

## Target State and The Gap

| Dimension | Current | Target (12-month) |
| --- | --- | --- |
| Business | 2.5 | 4.0 |
| Governance | 3.0 | 4.0 |
| Operations | 1.8 | 3.0 |
| People | 1.2 | 3.0 |
| Security | 2.0 | 4.0 |

Current state average is approximately 2.1. Target average approximately 3.6. The gap is what Phase 2 and the early programme phases address.

## Practical Readiness Issues

- Legacy operating systems: approximately 1,960 servers (roughly two-thirds of the in-scope estate) run OS versions past standard end-of-life.

- Servers without VMware Tools: 1,227 servers without guest-level data collection.

- Dual-zone naming convention: .int and .hsk domains creating DNS planning complexity.

- Standardised access: different credential stores and access patterns per business area.

## Risks Specific To Migration

- Oracle knowledge dependency: MOL Oracle database team owns significant operational knowledge. Any migration path requires their active engagement. Key-person risk applies.

- Third-party dependencies: NCS manages SQL Server and Oracle for CHP, Atex, and Circnet. Migration coordination with NCS is a governance item that affects timeline.

- Application ownership across executives: MOL migration decisions span two executive domains (see Section 7).

- Operating model during transition: the seven-area operating model will continue running alongside the new cloud landing zone during migration.

# Section 9: Challenges

## What This Section Does

Each challenge below is what we found during discovery and workshops. Each item says what it is, why it matters for [Client Name], and what to do about it. Where we can quantify the scale or effort, we do. Where we cannot, we flag the gap honestly.

## Estate Complexity

What we found: the estate is more varied than the SoW scoped. The SoW assumed 2,300 servers across VMware. Actual discovery found 4,500+ servers across five infrastructure types (VMware, Proxmox, physical bare metal, appliance, cloud). Mail Online alone has 40+ interdependent sub-services. Oracle RAC clusters span multiple physical nodes. Atex uses multicast for cluster discovery, a protocol that cloud virtual networks do not natively support. Database management is split between your internal team (MOL Oracle) and a third-party provider (NCS for CHP, Atex, Circnet, SQL Server). Mail Online's dual executive ownership is covered in Section 7.

Why it matters: complexity affects timeline, cost, and risk. Each infrastructure type needs a different discovery, assessment, and migration approach. The dual-ownership flagged for MOL (Section 7) must be reflected in programme governance from day one, not resolved mid-programme.

What to do about it: Phase 2 must be multi-workstream, not a single sequential plan. The dependency map across applications, data, and business ownership is the input to the release plan.

## Legacy Operating Systems

What we found: approximately 1,960 servers (roughly two-thirds of the in-scope estate) run operating system versions past their standard end-of-life dates. The largest groups are Ubuntu 14.04 (~1,120 servers, EOL 2019), Ubuntu 16.04 (~604, EOL 2021), and Ubuntu 18.04 (~75, EOL April 2023). Smaller groups include RHEL 6 (~140, EOL 2020), RHEL 5 (~8), and Solaris 10 (15). The Ubuntu versions may be receiving security patches via Ubuntu Pro / Extended Security Maintenance (the £20K/yr Ubuntu patching line in IT Costs may cover this). Most of the Ubuntu legacy sits inside Mail Online given its Ubuntu base. Solaris is called out separately below.

Why it matters: legacy OS servers cannot be lifted directly to cloud. They must be replatformed to a supported version first. This is a per-server activity, not a batch operation, and adds to the migration timeline and effort. At roughly two-thirds of the in-scope estate, this is a material scope item for Phase 2 sequencing.

What to do about it: Phase 2 quantifies the exact per-application impact and the indicative effort per server. Replatforming happens during migration or as a pre-migration activity, depending on the cohort. Ubuntu Pro / ESM status should be confirmed formally as part of the Phase 2 intake.

## Standardised Access

What we found: different credential stores, different access patterns per business area. During discovery, WMI was blocked on the ANL Windows estate, so collection ran through VMware Tools guest operations via vCenter. The initial run used a domain admin account, which caused VGAuth (VMware Tools' guest authentication) to round-trip to the domain controller every minute per VM, producing CPU spikes on target VMs. Switching to a locally-provisioned admin account on each VM removed the DC round-trip and stabilised collection.

Why it matters: cloud access control depends on federated identity and privileged access management. Multiple credential stores means multiple places to federate from, multiple places where access drift can occur, and higher audit overhead.

What to do about it: PAM tooling (CyberArk or equivalent) evaluation and landing zone IAM design are early programme activities. Consistent administrator access patterns should be a landing zone decision, not a per-application decision.

## VMware Tools Coverage

What we found: 1,227 of 3,038 servers do not have VMware Tools installed or have outdated versions. Guest-level performance and dependency data is unavailable for these servers.

Why it matters: sizing and dependency mapping rely on guest-level data. Where it is missing, pricing uses provisioned specifications (slightly conservative for VMs, accurate for bare metal) and dependency maps cannot see out-bound connections.

What to do about it: update VMware Tools where possible. This is a low-risk, high-value action that improves the data foundation for Phase 2.

## Skills Gap

What we found: the cloud-specific capabilities that Phase 2 and migration execution require are at an early stage across the 170-person technology organisation. Specifically: cloud platform engineering (landing zone, IAM, networking), Infrastructure-as-Code (Terraform or cloud-native equivalent), container orchestration at production scale (a Kubernetes PoC exists; production operation is not yet established), cloud security (cloud-native firewalling, identity federation, secrets management), FinOps, and DevOps automation. These sit alongside deep existing expertise in VMware, Oracle, F5, and editorial engineering that the programme will continue to depend on.

Why it matters: each of these capabilities is needed during migration, not after it. The programme cannot begin landing zone build, cohort migration, or cloud security without them.

What to do about it: the practical path is partner-assisted transition with concurrent upskilling. Migrate and train at the same time. External capability carries the specialist load from the start of Phase 2; [Client]'s internal team works alongside that capability cohort by cohort, absorbing the practice during delivery. The end state is [Client Name]-led operation with internal cloud capability built in-flight.

## Naming Conventions

What we found: servers use both .int and .hsk domain suffixes, with the same physical server registered under both zones.

Why it matters: cloud DNS supports custom private zones with arbitrary suffixes, so the dual-zone pattern itself works in cloud without modification. The complexity is in migration coordination: inventory reconciliation, discovery filtering, external systems that hardcode one suffix, and hybrid-state DNS resolution.

What to do about it: DNS strategy is a landing zone design decision for Phase 2. The choice is whether to preserve the dual-zone pattern in cloud (extra records, lowest change to dependencies) or collapse to a single canonical zone (cleaner long-term, requires updating every downstream dependency).

## Oracle Complexity

What we found: the Oracle estate carries operational complexity beyond its cost profile. The MOL B-cluster (production primary) has no DMA assessment data; its sizing is based on provisioned hardware specification only. Cross-cluster decisions need coordination between the internal MOL DBA team and NCS (which runs CHP, Atex, and Circnet Oracle).

Why it matters: without DMA on the MOL B-cluster, sizing the biggest database remains provisioned-hardware-based. The split between the internal team and NCS means coordination is not purely technical. Programme sequencing must respect the MOL DBA team's BAU load.

What to do about it: DMA assessment of the MOL B-cluster is the highest-priority Phase 2 action. Oracle migration paths and associated costs are in Section 5.

## SQL Server Database Consolidation

What we found: SQL Server instances host databases for multiple applications with cross-database queries between them. Workshop input was explicit: 'Multiple databases for multiple apps on DBServers. Decoupling will be a challenge.' Power BI Report Server licences are tied to the physical SQL Server hardware.

Why it matters: a clean PaaS move to Cloud SQL, RDS, or Azure SQL depends on per-database decoupling. Applications that rely on three-part naming or linked server calls between databases on the same instance will need refactoring. Power BI Report Server is hardware-tied and does not move cleanly to cloud as-is; Power BI Service (cloud) is a separate licensing model.

What to do about it: per-instance assessment and refactoring analysis are scoped in Phase 2 (Section 11).

## Solaris Legacy Stack

What we found: several applications are recorded with Solaris as operating system, including Mail Online sub-components (Mobile, Content), Wikidata, and ESCC.

Why it matters: Solaris is not natively supported as a guest operating system on AWS, Azure, or GCP. Oracle Cloud Infrastructure is the only hyperscaler with native Solaris support. Any Solaris-hosted workload must be either replatformed to Linux before migration, kept on-premises during transition, or retained on Oracle-specific infrastructure.

What to do about it: Phase 2 Solaris inventory to confirm exact version and workload. Solaris should be called out explicitly in the Phase 2 release plan rather than grouped with general legacy OS activity.

## Hardcoded IP Addresses In Legacy Integrations

What we found: ECO3 workshop input confirmed 'ECO3 had used hardcoded IPs to avoid DNS issues'. Other applications also reference load balancer IPs and third-party whitelists by specific address.

Why it matters: hardcoded IP addresses do not translate directly to cloud. Cloud VPCs assign IPs dynamically or via DNS. Any inbound integration that whitelists specific IP addresses must be re-established against cloud IP ranges or DNS.

What to do about it: Phase 2 scope includes per-application IP dependency audit. For each hardcoded IP: replace with service name or DNS, or establish an equivalent cloud static IP and update the downstream integration.

## What The Challenges Do Not Affect

It is worth saying what these challenges do not change:

- The overall cloud recommendation. None of these challenges makes cloud a bad idea. They shape the migration approach, not the destination.

- The business case. The savings potential in Sections 5 and 10 stands. The challenges affect timeline and approach, not outcome.

- [Client]'s ability to succeed. The challenges are addressable with the right programme structure, and are similar in kind to what most enterprise cloud transformations carry at this stage.

# Section 10: Opportunities

## What This Section Does

Each opportunity below is specific to [Client]'s estate. Each item says what it is, what it saves or enables, what is needed to pursue it, and what Phase 2 would validate.

## Database Migration to Managed Services

Moving databases from self-managed infrastructure to managed cloud databases. Eliminates operational overhead for patching, backups, HA failover. For Oracle specifically, a move to PostgreSQL-compatible managed services also removes the licensing entirely. For SQL Server, managed services reduce operational burden and potentially reduce licensing through cloud-native BYOL mechanisms.

Your starting point: you are already testing PostgreSQL as an Oracle replacement. The blocker is business prioritisation, not technical capability. Your 49 SQL Server instances are currently managed in-house and by NCS.

## Overprovisioned Instances (MOL RTA)

MOL's Real-Time Analytics application contains many significantly overprovisioned instances identified during discovery. Right-sizing during migration, rather than lifting as-is, produces an immediate cost saving with minimal risk. The utilisation data proves the current allocation exceeds demand. Phase 2 produces precise sizing recommendations per instance.

## Load Balancing Modernisation

Replacing hardware load balancers (F5 for corporate, Zeus/Ivanti vTM for MOL) with cloud-native load balancers. Benefits include: no hardware lifecycle management, auto-scaling tied to traffic, native integration with cloud monitoring, global load balancing for multi-region deployments, and material cost reduction.

Per-cloud options: GCP Cloud Load Balancing; AWS Application Load Balancer, Network Load Balancer, Global Accelerator; Azure Front Door (global with integrated WAF), Azure Load Balancer, Application Gateway.

## Oracle Modernisation to PostgreSQL

Detailed path analysis is in Section 5 (primary recommendation: Exadata@Cloud for risk reduction, PostgreSQL as a Phase 2 strategic decision).

Saving potential is material: approximately £45-65K/month depending on cloud (combining infrastructure delta with £650K/yr support elimination).

This is the largest single cost item you have.

You are already testing PostgreSQL, which demonstrates organisational appetite.

It is a strategic decision, not a tactical one. Each hyperscaler has transformation support paths. Phase 2 validates the effort, risks, and cost through a per-cluster assessment.

## VMware and Broadcom Contract Exit

Detailed position in Section 3 (Broadcom KB 429208 reference). Migrating to cloud before the Broadcom position forces a VCF subscription decision eliminates that cost pressure entirely. It also removes dependency on a vendor whose pricing strategy has become unpredictable.

## Application Rationalisation

Applications that are candidates for retirement or SaaS replacement rather than cloud migration. Every application retired is servers removed from migration scope.

- Atex 5.5 (Legacy): 32-bit architecture incompatible with modern cloud VMs. Candidate for retirement once Atex 6 migration is complete. Removes approximately 5 TB of Oracle storage.

- IBM Lotus Notes: legacy collaboration platform. SaaS replacement (Microsoft 365 or Google Workspace) eliminates the infrastructure entirely.

- SolarWinds and Zabbix: current monitoring tools. Cloud-native monitoring replaces these as part of landing zone build.

- Other candidates identified by application owners: Wombat, Mediaplanner, Landscape, Fingerpost reporting tools. Each needs owner validation before retirement.

## Sydney Datacentre Quick-Win

Sydney datacentre operates on a flexible contract with no exit penalty. The CSP application (CHP Sydney) runs on approximately four servers with approximately 0.4 TB of Oracle storage. Migrating Sydney early provides an immediate DC cost offset (approximately £40K/yr) and serves as a low-risk proof point for the migration programme.

## SQL Server Licensing Optimisation

SQL Server licensing is 40-60% of the effective cost for SQL workloads. If SA is formally confirmed, SQL Server BYOL eliminates approximately £14-15K/month of surcharge across clouds. Further optimisation possible by moving to managed SQL services.

## Infrastructure as Code and Automation

Adopting Infrastructure-as-Code (Terraform or cloud-native equivalent) as the default for all cloud resource provisioning from day one. Removes manual configuration errors, accelerates environment creation, makes the whole estate reproducible and auditable.

## Observability Consolidation

Replacing SolarWinds and Zabbix with cloud-native observability (Cloud Operations, CloudWatch, Azure Monitor, or a cloud-agnostic tool like Datadog or Grafana Cloud). Delivers consistent monitoring across brands, same metrics and alerting patterns, tight integration with cloud platform services.

## Akamai vs Cloudfront

## Summary of Opportunities

### Quantified savings (modelled in Phase 1)

- Oracle modernisation (£45-65K/month depending on cloud - Phase 2 strategic decision)

- Windows BYOL (£7-18K/month depending on cloud, Software Assurance dependent)

- SQL Server BYOL (£14-15K/month across all three clouds if SA confirmed)

- Storage tiering (£10-19K/month depending on cloud)

- Overprovisioned instance rightsizing (quantified during Phase 2)

### Qualitative opportunities (Phase 2 to quantify)

- Application rationalisation (Lotus Notes, Atex 5.5, monitoring tools)

- Load balancing modernisation

- Sydney DC quick-win

- Infrastructure as Code and automation

- Observability consolidation

# Section 11: Moving Forward and Phase 2

## What This Section Does

This section answers 'so what, now what'. It covers the business case, decision guidance for the hyperscaler presentations [Client Name] is about to receive, the foundational actions needed to prepare for migration, the concrete shape of Phase 2, and the risk of not proceeding.

## The Business Case

- Cost of doing nothing: approximately £3.64 million per year (the on-premises annualised cost) not including Broadcom VCF subscription cost, until the next hardware refresh cycle which will require a large capital outlay.

- Cost of cloud: Complete View with indicative egress, London, 3-year committed, SA assumed): GCP approximately £3.17M/yr, AWS approximately £3.29M/yr, Azure approximately £4.19M/yr.

- Savings opportunity: approximately £340-460K/yr from GCP or AWS Complete View versus on-premises baseline. Oracle modernisation adds £45-65K/mo (£540-780K/yr) on top if the PostgreSQL path is chosen in Phase 2.

- What is missing: migration cost (one-time labour and credits), dual-run cost (on-premises and cloud operating in parallel during transition), and hyperscaler commercial offers (MAP credits, partner discounts, EA concessions).

[PENDING: Year 1 financial picture. Without migration effort estimates, a dual-run schedule, and hyperscaler commercial offers, a credible Year 1 cost forecast cannot be produced.]

## Decision Guidance For Hyperscaler Presentations

### Questions that reveal whether they understand your situation

- 'What is your answer for Oracle?' (not 'how much would it cost to run Oracle on our cloud', but the whole path)

- 'How have you sized our workloads?' (does their methodology match the others?)

- 'What does BYOL look like for our Server 2022 estate?' (only Azure AHB works without the October 2019 Listed Provider restrictions)

- 'What is your commercial offer?' (private pricing, MAP/EA credits, partner pricing)

- 'Who owns Day 2 operations?' (vendor, your team, Rackspace, a combination)

### Warning signs

- All-5 self-rating on evaluation criteria without specific [Client]-grounded justification

- Cost figures that do not include Oracle, SQL Server licensing, or support

- Proposals that ignore your Software Assurance status

- Sizing that uses only their own tool without API cross-validation

- Year 1 savings claims without acknowledging dual-run cost

## What [Client] Needs To Do Now

### Data and inputs still needed

- Microsoft Software Assurance formal confirmation from Bluesource (Complete View assumes SA in place)

- Broadcom VCF subscription quote (completes the 'cost of doing nothing' picture)

- MOL B-cluster DMA collection (largest database; currently sized from provisioned hardware specification only)

### Decisions to make

- Primary platform recommendation (Section 7, architect-led)

- Atex multicast path: engage vendor on unicast support (direct cost impact)

- Oracle path commitment: Exadata@Cloud primary, PostgreSQL strategic decision timing

## Foundational Actions

### Modernise legacy operating systems

Older OS versions cannot be lifted to cloud as-is. Replatforming to supported versions is a per-server activity. Starting early avoids it becoming a critical path blocker.

### Establish cloud governance

Define the cloud operating model before migrating workloads: who provisions, who approves, who pays. Establish tagging and labelling standards for cost attribution. Implement FinOps practice from day one. Define security baselines and compliance requirements.

### Prepare the cloud landing zone

A cloud landing zone is the standardised environment into which workloads are migrated. It includes network topology, IAM, security controls, logging and monitoring foundations, and cost management. Getting the landing zone right before migration begins avoids expensive redesign once workloads are running.

### Adopt automation tooling

Infrastructure-as-Code for all resource provisioning. CI/CD pipelines for infrastructure deployment. Automated compliance checking (policy-as-code). Cloud-native monitoring and alerting to replace SolarWinds and Zabbix.

### Staff training

Cloud platform certification programme for the infrastructure team. Kubernetes training to support the container strategy. FinOps training for finance and technology leadership. Security training for the cloud-native security model.

## Phase 2 Entry Point

Phase 2 is the next engagement. It turns the Phase 1 assessment and recommendation into a concrete migration plan. Phase 2 does not execute migration; migration execution happens in subsequent engagements against the Phase 2 plan.

### Phase 2 scope areas (indicative)

- Server and application profiling: extend assessment to the full 4,500+ estate. Deep performance profiling. MOL sub-component analysis. Utilisation-based right-sizing recommendations.

- Indicative modernisation path: per-application 7R classification. PaaS candidates. Container candidates. Application rationalisation decisions finalised.

- Dependency mapping deep-dive: extend network dependency coverage beyond current 27.7%. Validate co-migration groups. Map external dependencies.

- Data strategy: Oracle modernisation assessment (highest-value workstream). SQL Server per-instance assessment. Data platform architecture.

- Infrastructure and security assessment: landing zone design. Dedicated security posture assessment.

- Network and load balancer modernisation workstream: F5 iRules audit, Zeus/Ivanti vTM migration planning, cloud-native load balancing target design, Akamai CDN retention and cloud origin integration.

- Security policy migration workstream: Guardicore micro-segmentation policies. Akamai retention. Firewall rule migration planning.

- Backup and data protection workstream: Veeam estate inventory, RPO and RTO per application, cloud-native backup options.

- Legacy OS modernisation: specific per-server plan for Solaris, Ubuntu, RHEL 6 / JBoss stacks, and other unsupported versions.

- MOL product impact planning: expected product velocity during Cohort 3 migration window. Editorial SLOs to defend. Sub-component release train mapping.

- High-level release plan: migration cohort sequencing with timeline estimates. Co-migration group scheduling. Double-run cost modelling. Risk register.

- Cloud preparation planning: landing zone design, Cloud Platform Team formation plan, initial staff training roadmap, FinOps tooling selection.

[PENDING: Phase 2 scope, indicative cost, phases, timelines, and funding are to be delivered in a separate Phase 2 proposal from Rackspace's sales team.]

## Indicative Timeline

The migration programme has three phases: planning, execution, and optimisation.

- Phase 2 (planning and design) runs approximately 15 weeks. It produces the landing zone design, per-application migration strategies, cohort sequencing, and a realistic datacentre exit plan. Phase 2 is a separately proposed engagement and requires a commercial agreement to begin.

- Migration execution follows Phase 2 and is expected to run 12 to 18 months depending on the Oracle path decision, Atex unicast confirmation, and the pace at which Customer_App1 sub-components can be sequenced. The UK datacentre leases expire in November 2027. Whether full exit is achievable by that date depends on when Phase 2 starts and how quickly the critical decisions (Oracle path, Atex unicast, CPO/CTO sponsorship for Customer_App1) are made.

- Optimisation follows migration and includes FinOps maturity, PostgreSQL modernisation if the path is chosen, and Oracle support contract decisions.

The key dependency is Phase 2 start date. Every month of delay compresses the execution window against the November 2027 lease expiry.

## Risk Of Not Proceeding

What happens if [Client] defers the decision:

- Contract pressure compounds. The three converging contracts do not pause. Each renewal cycle re-locks capital. Coordinated exit becomes harder every quarter of delay.

- Operational fragmentation continues. The seven-area operating model was flagged at kickoff as limiting growth. It continues to limit until addressed.

- Subscriber growth ambition becomes harder to support. Scaling MOL to one million subscribers on fixed-capacity infrastructure requires capital outlay for the next hardware refresh.

- Broadcom exposure persists. Any expansion or major upgrade requires VCF subscription purchase. Security posture continues to degrade.

- The business case gets worse, not better. Every year of deferral adds another year of on-premises operating cost and potentially another round of Microsoft EA renewal negotiated with less leverage.

The single most compelling reason to proceed now: the window defined by the converging contracts is open for approximately two years. Beyond that, the cost of transformation goes up because the alternatives individually preserve optionality but collectively foreclose it.

## Continuity Into Phase 2

Rackspace is proposing Phase 2 as a separate engagement. The observations from Phase 1 (the seven-area operating model, the multicast constraint, Mail Online's dual ownership, the Oracle B-cluster data gap, Guardicore micro-segmentation, F5 iRule complexity, the ECO3 hardcoded IP pattern, and the Solaris legacy stack) directly inform how Phase 2 should be scoped.

Phase 2 activities can be planned against these known challenges rather than re-discovered.

The Phase 2 commercial proposal is delivered separately from this assessment.

# Appendices

###### Appendix A: TCO Methodology and Detail

### Approach

The TCO analysis priced all 3,038 in-scope servers independently across three clouds using live pricing APIs. Each cloud's own assessment tool recommended instance types from the same source data, and those recommendations were then priced against public API rates to normalise the comparison.

| Cloud | Pricing source | Currency handling |
| --- | --- | --- |
| GCP | Cloud Billing Catalog API | £native, no conversion |
| AWS | AWS Price List API | USD, converted at 0.755 GBP/USD (April 2026 corporate average) |
| Azure | Retail Prices REST API | £native, no conversion |

### Assumptions

- Tool-based sizing: servers priced at instance types recommended by each cloud's own TCO toolkit.

- SSD baseline across all clouds: GCP Balanced PD / Hyperdisk Balanced, AWS gp3, Azure Premium SSD. IOPS matched at 80,000 per disk where needed.

- PAYG operating system in the baseline: Windows and RHEL at pay-as-you-go rates. BYOL modelled separately.

- 3-year committed pricing: GCP 3-year CUD, AWS 3-year Standard Reserved, Azure 3-year Reserved VM Instances.

- Single FX rate: USD to £at 0.755 (April 2026 average). Applied to AWS pricing only.

- No Azure Hybrid Benefit in the baseline: AHB not applied because Software Assurance status is unverified.

- Physical servers at provisioned specification: 38 manually collected servers sized at provisioned CPU, memory, storage.

- Burstable VM families excluded by team agreement as not production-grade.

### Detailed TCO workbooks

[Client]_TCO_Comparison.xlsx: Summary, Rate Card, Repricing per region (London, NL/Ireland, Frankfurt), Methodology sheet.

[Client]_TCO_Optimized.xlsx: Scenario Summary, Oracle Options, Migration Credits, Methodology. Windows BYOL, SQL Server licensing, Oracle migration scenarios, storage tiering, RHEL BYOL, Azure Dev/Test.

###### Appendix B: Scoring Methodology and Detail

### Scoring approach

Hyperscaler scoring was conducted against 57 value dials organised under thirteen strategic goals. [Client Name] set the weightings. Rackspace scored each provider in two passes: an unbiased first pass against market baselines, followed by a refinement against [Client]'s specific estate.

### Overall weighted score

| Cloud | Weighted score | Fit % | Rank |
| --- | --- | --- | --- |
| Azure | 4.3 | 85.6% | 1 |
| AWS | 4.3 | 85.0% | 2 |
| GCP | 4.2 | 83.4% | 3 |

The spread is very narrow. Azure leads AWS by 0.6 percentage points. GCP sits 2.2 percentage points behind Azure.

### Per-application detail

Per-application cloud affinity scores, readiness assessments, cohort assignments, and dependency relationships are available in the Business Summary workbook:

- Wave Planning (Summary) sheet: all in-scope applications with cloud affinity, migration strategy (indicative 7R), criticality, and cohort assignment

- App Dependency Matrix sheet: network-confirmed and interview-confirmed dependencies

- Executive Summary sheet: per-application discovery coverage percentages

###### Appendix C: Attached Workbooks

| Workbook | Contents |
| --- | --- |
| [Client]_InScope_Business_Summary.xlsx | Executive Summary, Application Coverage, Per-Service Breakdown, Gap List, Database Discovery, Database Instance Inventory, App Dependency Matrix, Wave Planning (Summary), Raw Data |
| [Client]_TCO_Comparison.xlsx | Summary, Rate Card, Repricing per region (London, NL/Ireland, Frankfurt), Methodology. All 3,038 servers priced per region from live API rates. |
| [Client]_TCO_Optimized.xlsx | Scenario Summary, Oracle Options, Migration Credits, Methodology. Windows BYOL, SQL Server licensing, Oracle scenarios, storage tiering, RHEL BYOL, Azure Dev/Test. Includes Oracle support line (£650K/yr retained under BYOL). |
| [Client] Weighted Selection Criteria.xlsx | Weighted hyperscaler scoring across mutually agreed parameters. |

###### Appendix D: Open Items

| Item | Status | Impact | Section |
| --- | --- | --- | --- |
| Microsoft SA formal confirmation (Bluesource) | PENDING | Unblocks BYOL modelling as certainty | 5, 6 |
| Weighted hyperscaler scoring matrix | COMPLETE | Feeds Section 7 recommendation | 7 |
| MOL Oracle B-cluster DMA assessment | Not yet collected | Production primary Oracle; biggest Phase 1 data gap | 4, 5, 9 |
| On-premises DC cost data (updated) | RECEIVED | £3.64M/yr baseline incorporated | 5, 11 |
| Broadcom VCF subscription quote | PENDING | Completes cost of doing nothing picture | 3, 5, 11 |
| Pre-sales Phase 2 content | PENDING | Indicative cost, phases, timelines, funding | 11 |
| Year 1 financial forecast | PENDING | Requires migration effort, dual-run schedule, commercial layer | 11 |
| Commercial layer (MAP, credits, partner pricing) | PENDING from sales team | Adjusts Complete View with commercial offers | 5 |
| AVS UK South node pricing | VERIFY | Multicast cost range accuracy | 5, 6 |
| Microsoft E3/E5 productivity licensing status | PENDING client confirmation | Affects productivity suite decision | 3 |
| Names of the seven technology operating areas | PENDING CTO | Specificity of Section 3 narrative | 3 |
| Legacy OS per-application mapping | Phase 2 intake | Sequencing of replatform-before-migrate activity | 8, 9 |
| Atex vendor confirmation on unicast support | PENDING vendor engagement | Direct cost impact on multicast constraint | 5, 6, 10 |
| Sydney cluster independence validation | PENDING | Confirmation that Sydney can exit without UK dependency | 10 |
| UK CMA Strategic Market Status investigation | WATCH ITEM (~Feb 2027) | Potential Windows Server licensing parity across clouds | 5, 7 |

###### Appendix E: Glossary

| Term | Definition |
| --- | --- |
| AHB | Azure Hybrid Benefit. Allows use of existing Microsoft licences on Azure. |
| ALng | Annual Licence (new). Microsoft Enterprise Agreement line item prefix. |
| AVS | Azure VMware Solution. VMware-on-Azure offering that supports multicast. |
| BYOL | Bring Your Own Licence. Using existing software licences on cloud infrastructure. |
| CoE | Cloud Centre of Excellence. |
| CRA | Cloud Readiness Assessment. |
| CUD | Committed Use Discount (GCP). Discounts for 1 or 3-year commitment. |
| DMA | Database Migration Assessment. Google open-source tool for Oracle/SQL assessment. |
| EA | Enterprise Agreement (Microsoft). |
| Exadata@Cloud | Oracle's Exadata engineered system as a cloud service on AWS, Azure, and GCP. |
| FinOps | Financial operations for cloud. Practice combining technology, finance, and business accountability. |
| GCVE | Google Cloud VMware Engine. |
| GKE | Google Kubernetes Engine. |
| HA | High Availability. |
| IaC | Infrastructure as Code. |
| IOPS | Input/Output Operations Per Second. |
| Landing Zone | Pre-configured, standardised cloud environment for workload migration. |
| Listed Provider | Microsoft's designation for certain cloud providers where BYOL restrictions apply. |
| MACC | Microsoft Azure Consumption Commitment. |
| MAP | Migration Acceleration Programme (AWS). |
| MOL | Mail Online. [Client]'s digital platform, 72.6% of in-scope servers. |
| NCS | Third-party provider managing SQL Server and Oracle for certain [Client] applications. |
| OCI | Oracle Cloud Infrastructure. Underpins Exadata@Cloud across all three clouds. |
| PAM | Privileged Access Management. |
| PAYG | Pay As You Go. |
| PL/SQL | Procedural Language extensions to SQL, used by Oracle. |
| RAC | Oracle Real Application Clusters. |
| RI | Reserved Instance (AWS). |
| SA | Software Assurance (Microsoft). |
| Sole Tenant Node | GCP feature where a physical host is dedicated to a single customer. |
| SnS | Support and Subscription (Broadcom). |
| TCO | Total Cost of Ownership. |
| TGW | AWS Transit Gateway. |
| TOM | Target Operating Model. |
| VCF | VMware Cloud Foundation. Broadcom's subscription-based VMware licensing model. |
| 7Rs | Seven migration strategy options: Retire, Retain, Relocate, Rehost, Replatform, Repurchase, Rearchitect. |
| WPS | Web Publishing System. Mail Online's publishing pipeline. |