| DOCUMENT INFORMATION |  |
| --- | --- |
| Document Purpose: | The commercial handoff document that initiates the Part 2 migration engagement. Contains: Part 2 scope, timeline, investment, and next steps. The customer signs this at the Phase 4 playback meeting. |
| CRA Phase: | Phase 4: Planning -- Part 2 Handoff |
| Target Audience: | Customer CTO/CFO (for signature) + Rackspace Pre-Sales (for pricing) |
| When to Complete: | Phase 4 weeks 3-5; present at Phase 4 playback and leave for signature |
| Est. Time: | 6-8 hours (much of content comes from Phase 3 outputs); 8-12 pages |
| Version: | v1.0 |
| WHAT TO CUSTOMISE - Section 3 (Hyperscaler Recommendation): copy from Phase 3 report; do not re-derive - Section 4 (TCO Summary): reference Phase 3 TCO model; use 3-year net figure - Section 5 (Partner Funding): confirm AMM/MAP/PSO registration status with Alliance Manager - Section 10 (Investment): obtain pricing from Pre-Sales; do not estimate without approval |  |
| Template version: v1.0 -- CRA Framework v2.0 -- Rackspace Cloud Solutions Architecture |  |
| IMPORTANT: AMM/MAP/PSO deal registration must be COMPLETE before Rackspace countersigns this document. Check with the Alliance Manager before preparing Section 5. See docs/DMG-MEDIA-UK-LESSONS-LEARNED.md Lesson 5. |  |

CLOUD READINESS ASSESSMENT

Part 2 Entry Point

| Customer: | [CUSTOMER LEGAL ENTITY NAME] |
| --- | --- |
| Prepared By: | [LEAD ARCHITECT NAME], Rackspace Technology |
| Engagement Reference: | [ENGAGEMENT ID / SOW REFERENCE] |
| Date: | [DD Month YYYY] |
| Document Version: | 1.0 |
| Classification: | Client Confidential |

Footer on all pages: [Customer Name] — Cloud Readiness Assessment Part 2 Entry Point — Rackspace Confidential

# How to Use This Template

This document is the authoring blueprint for the Part 2 Entry Point. Work through each section in order. Every section includes: Purpose, Required Content, Format, and a populated DMG Media UK example.

Replace all [PLACEHOLDER] text with engagement-specific content

Tables with 'TEMPLATE ROW' labels: duplicate the row for each item in your engagement

Sections marked with [MANDATORY] must not be omitted — write 'TBD — [reason]' if data is incomplete

Sections marked [OPTIONAL] are strongly recommended for enterprise customers

SECTION 1 — EXECUTIVE SUMMARY [MANDATORY]

## 1. Executive Summary

Purpose: Give the CTO/CFO a one-page standalone summary they can extract for their board. If they read nothing else, they read this.

Required content (in order):

One-sentence engagement statement — what was assessed, by whom, over what period

Estate summary — total VMs/servers, application count, DC locations assessed

Recommended hyperscaler — primary + rationale in two sentences

Three-year TCO summary — on-prem baseline vs. recommended cloud (net saving / net increase + %)

Partner funding identified — AMM / MAP / PSO credits available (£/$ headline figure)

Recommended next step — one sentence describing what Part 2 is and the proposed start date

Format: Boxed 'At a Glance' summary table + 2–3 paragraph narrative. Maximum 1 page.

| At a Glance |  |
| --- | --- |
| Organisation | [CUSTOMER NAME] |
| Assessment Period | [Start Date] – [End Date] ([N] weeks) |
| Estate Assessed | [N] VMs · [N] applications · [N] data centres |
| Recommended Hyperscaler | [PRIMARY CLOUD] — [REGION] |
| 3-Year TCO: On-Premises | £/$ [X] |
| 3-Year TCO: Recommended Cloud (Optimised + Partner Funding) | £/$ [X] ([Y]% saving) |
| Partner Funding Identified | [AMM / MAP / PSO] — estimated £/$ [X]–[Y] |
| Recommended Next Step | [Part 2 description] — proposed start [Quarter Year] |

Narrative (2–3 paragraphs):

Rackspace Technology completed a Cloud Readiness Assessment of [CUSTOMER NAME]'s on-premises estate across [N] data centres from [Start Month] to [End Month] [Year]. The assessment covered [N] virtual machines, [N] Oracle RAC clusters, and approximately [N] in-scope applications.

DMG Media UK example: Rackspace Technology completed a Cloud Readiness Assessment of DMG Media UK's on-premises estate across two London data centres from February to May 2026. The assessment covered 4,212 virtual machines, 18 Oracle RAC clusters, and approximately 280 in-scope applications. Primary recommendation: Microsoft Azure (UK South primary, UK West DR). Three-year TCO: On-premises status quo £18.4M. Azure (3-year RI, AHB applied) £11.2M. Net saving: £7.2M (39%) before AMM funding. Partner funding: Microsoft AMM eligibility identified — estimated £800K–£1.2M.

SECTION 2 — SCOPE OF PART 1 ASSESSMENT [MANDATORY]

## 2. Scope of Part 1 Assessment

### 2.1 Estate Summary Table

| Category | Count | Notes |
| --- | --- | --- |
| Virtual Machines (in scope) | [N] | [TEMPLATE ROW — add rows as needed] |
| Physical Servers | [N] |  |
| Oracle RAC clusters | [N] |  |
| SQL Server instances | [N] |  |
| Applications profiled | [N] |  |
| Data centres / locations | [N] | [Location names] |
| Assessment period | [Start] – [End] | [N] weeks |

DMG Media UK example: 4,212 VMs · 18 Oracle RAC · 340+ SQL Server · 280 applications · 2 DCs (London Docklands + Sovereign House) · 16 weeks.

### 2.2 What Was Out of Scope

List any assets explicitly excluded. This prevents scope creep in Part 2 or disputes about what was and was not assessed.

| Asset / Area | Reason Out of Scope |
| --- | --- |
| [TEMPLATE ROW] | [TEMPLATE ROW] |

DMG Media UK example: Network infrastructure redesign (flagged as Part 2 workstream) · SaaS applications (separate SaaS rationalisation workstream) · DR/BC detailed design (preliminary flags only in Part 1).

### 2.3 Scope Variance Note  [MANDATORY if applicable]

MANDATORY — If scope grew during the engagement, document it here to protect Part 2 commercial baseline.

"The original SOW estimated [N] in-scope VMs. Final assessed estate was [N] VMs — a [X]% variance. This variance was managed through [agreed mechanism: change control / extended timeline / additional resource]. The Part 2 SOW should be scoped against the final assessed figure of [N] VMs."

DMG Media UK example: Original SOW: 2,700 VMs. Final estate: 4,212 VMs. 57% variance. Managed through phased scope expansion with customer approval. Part 2 SOW must be scoped at 4,212 VMs.

SECTION 3 — HYPERSCALER RECOMMENDATION [MANDATORY]

## 3. Hyperscaler Recommendation

Evidence before recommendation — always show the data first. Section 3.1 (scoring table) must come before Section 3.2 (recommendation rationale).

### 3.1 Hyperscaler Scoring Summary

| Evaluation Criterion | Weighting | Azure | AWS | GCP | Notes |
| --- | --- | --- | --- | --- | --- |
| TCO (3-year, primary workloads) | [X]% | [Score/10] | [Score/10] | [Score/10] | [TEMPLATE ROW] |
| Licensing advantage (AHB / BYOL) | [X]% |  |  |  |  |
| Regulatory compliance posture | [X]% |  |  |  |  |
| Partner commercial (AMM / MAP / PSO) | [X]% |  |  |  |  |
| Technical fit (workload types) | [X]% |  |  |  |  |
| Strategic alignment (enterprise agreements) | [X]% |  |  |  |  |
| WEIGHTED TOTAL | 100% | [Score] | [Score] | [Score] |  |
| RECOMMENDATION |  | [PRIMARY] | Secondary | Tertiary |  |

### 3.2 Recommendation Rationale

Write 3–5 bullet points, each citing a specific data point from the assessment. Use the structure below:

Cost: "[Primary cloud] TCO over 3 years is [£/$X] vs. on-prem [£/$Y] — a [Z]% saving, driven by [AHB / RI pricing / licensing overlay]."

Licensing: "[N] SQL Server licences eligible for AHB — saving [£/$X] vs. PAYG. [N] Oracle workloads [recommended migration path]."

Compliance: "[Primary cloud] holds [specific certifications relevant to sector] required for [specific regulatory obligation]."

Partner funding: "[AMM / MAP / PSO] funding eligibility identified — estimated [£/$X] available."

Strategic: "[Primary cloud] aligns to existing [enterprise agreement / support contract / roadmap commitment]."

### 3.3 Multi-Cloud Exceptions

Document any workloads that cannot move to the primary cloud:

| Application / Workload | Reason for Exception | Recommended Cloud | Notes |
| --- | --- | --- | --- |
| [TEMPLATE ROW] | [TEMPLATE ROW] | [TEMPLATE ROW] |  |

SECTION 4 — TCO SUMMARY [MANDATORY]

## 4. TCO Summary

Every figure must trace back to a tab in the TCO Excel model (business-case-tco-roi.xlsx).

### 4.1 Three-Year Cost Comparison

| Scenario | Year 1 | Year 2 | Year 3 | 3-Year Total | vs. On-Prem |
| --- | --- | --- | --- | --- | --- |
| On-premises (status quo) | £/$ [X] | £/$ [X] | £/$ [X] | £/$ [X] | Baseline |
| [Primary cloud] — Like-for-Like | £/$ [X] | £/$ [X] | £/$ [X] | £/$ [X] | [+/-X%] |
| [Primary cloud] — Optimised (RI / AHB / CUD) | £/$ [X] | £/$ [X] | £/$ [X] | £/$ [X] | [+/-X%] |
| [Primary cloud] — Optimised + Partner Credits | £/$ [X] | £/$ [X] | £/$ [X] | £/$ [X] | [+/-X%] |

Note on Year 1: Year 1 includes dual-running costs (on-prem + cloud overlap during migration). See Section 4.2.

### 4.2 Year 1 Dual-Running Forecast

Year 1 is typically the most expensive year because workloads run in both environments during migration. Document this explicitly to avoid budget shock.

| Cost Component | Amount | Notes |
| --- | --- | --- |
| On-premises costs (full year — decommission not yet complete) | £/$ [X] |  |
| Cloud costs (partial year — wave 1 + 2 migrated) | £/$ [X] |  |
| Migration tooling and licences | £/$ [X] |  |
| Professional services (Part 2) | £/$ [X] |  |
| YEAR 1 TOTAL (dual-running) | £/$ [X] |  |
| Year 1 Net (offset by AMM/MAP/PSO credits) | £/$ [X] |  |

### 4.3 Licensing Overlay

| Licence Type | Volume | Current Annual Cost | Cloud Path | Optimised Annual Cost | Saving |
| --- | --- | --- | --- | --- | --- |
| Windows Server (AHB eligible) | [N] | £/$ [X] | AHB + 3yr RI | £/$ [X] | £/$ [X] |
| SQL Server (AHB eligible) | [N] | £/$ [X] | AHB + 3yr RI | £/$ [X] | £/$ [X] |
| Oracle (BYOL) | [N] | £/$ [X] | BYOL on [VM/RDS/Exadata] | £/$ [X] | £/$ [X] |
| [Other — TEMPLATE ROW] |  |  |  |  |  |
| LICENSING TOTAL SAVING |  |  |  |  | £/$ [X] |

SECTION 5 — PARTNER FUNDING [MANDATORY]

## 5. Partner Funding

MANDATORY: Programme deal registration must be completed BEFORE Part 2 SOW signature. Registration after Part 2 start risks funding eligibility. Confirm with Alliance Manager before completing this section.

### 5.1 Partner Funding Summary Table

| Programme | Provider | Eligibility | Estimated Value | CRA Deliverables Required | Status |
| --- | --- | --- | --- | --- | --- |
| Azure Migration and Modernisation (AMM) | Microsoft | [Yes/No/TBC] | £/$ [X]–[Y] | MRA, inventory, business case, wave plan | [Not yet registered / Registered / Approved] |
| AWS Migration Acceleration Programme (MAP) | AWS | [Yes/No/TBC] | £/$ [X]–[Y] | MRA, inventory, business case, wave plan | [Not yet registered / Registered / Approved] |
| Google Cloud RAMP / PSO | Google | [Yes/No/TBC] | £/$ [X]–[Y] | GCAF assessment, discovery export, opportunity registration | [Not yet registered / Registered / Approved] |

### 5.2 AMM Pre-Qualification Checklist  [if Azure primary]

| Requirement | Status | Evidence |
| --- | --- | --- |
| Migration Readiness Assessment (MRA) complete | [ ] / [x] | CRA Phase 2 output |
| Validated infrastructure inventory | [ ] / [x] | Templates/01-discovery/ |
| Business case with 3-year TCO | [ ] / [x] | Templates/03-evaluation/business-case-tco-roi.xlsx |
| Migration wave plan (high level) | [ ] / [x] | Templates/04-planning/migration-wave-planner.xlsx |
| Azure as primary or co-primary cloud | [ ] / [x] | Hyperscaler recommendation |
| Rackspace registered in MSPP as Delivery Partner | [ ] / [x] | Rackspace Alliance Manager to confirm |

SECTION 6 — MIGRATION APPROACH (HIGH LEVEL) [MANDATORY]

## 6. Migration Approach — High Level

### 6.1 Recommended Migration Approach

| Phase | Workloads | Approach | Target Completion |
| --- | --- | --- | --- |
| Wave 0 — Proof of Concept | [N] VMs — [lowest risk workloads] | Rehost — IaaS lift-and-shift | [Month Year] |
| Wave 1 — Core Infrastructure | [N] VMs — [dev/test, non-critical] | Rehost — IaaS | [Month Year] |
| Wave 2 — Business Applications | [N] VMs — [business apps, mid-tier] | Rehost / Replatform | [Month Year] |
| Wave 3 — Tier-1 / Production | [N] VMs — [prod, customer-facing] | Rehost with optimisation | [Month Year] |
| Wave 4 — Oracle / Complex | [N] nodes — [Oracle RAC, legacy] | Replatform / Rearchitect | [Month Year] |
| Wave 5 — Decommission On-Prem | All | DC exit | [Month Year] |

Wave plan above is indicative. Part 2 will produce a detailed wave plan with application-level sequencing, dependency management, and cutover windows.

### 6.2 7Rs Estate View — High Level

| Migration Pattern | Est. VM / App Count | Notes |
| --- | --- | --- |
| Rehost (lift-and-shift) | [N] ([X]%) | Majority of estate — low complexity |
| Replatform | [N] ([X]%) | PaaS-eligible (SQL to managed service, etc.) |
| Rearchitect / Refactor | [N] ([X]%) | Greenfield rebuild or containerisation candidates |
| Repurchase (SaaS) | [N] | Replace with SaaS equivalent |
| Retire | [N] | Confirmed decommission — do not migrate |
| Retain | [N] | Cannot migrate — regulatory / latency / dependency |
| Relocate | [N] | Move to different DC without cloud migration |

SECTION 7 — RISK REGISTER (SUMMARY) [MANDATORY]

## 7. Risk Register — Summary

Document the top risks identified in Part 1 so Part 2 has a risk baseline. Do not defer to Part 2 — risks identified now reduce surprises later.

| # | Risk | Category | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- | --- | --- |
| 1 | Oracle licensing cost overrun — BYOL complexity | Licensing | [H/M/L] | [H/M/L] | [Action] |
| 2 | Network redesign delays wave 1 | Technical |  |  |  |
| 3 | Scope variance from additional discovery | Commercial |  |  |  |
| 4 | CAB approval lead time for firewall changes | Operational |  |  |  |
| 5 | [TEMPLATE ROW] |  |  |  |  |

DMG Media UK top risks: (1) Oracle RAC decommission — 18 clusters — BYOL path modelled, Oracle account team engaged. (2) Scope variance risk — estate grew 57% in Part 1 — scope gate added at Part 2 SOW. (3) Redis OSS licence change — 140+ instances — Redis Enterprise Ltd commercial negotiation parallel-tracked. (4) EoL OS (Windows 2012, RHEL 6) — 340+ servers — ESU cost modelled, upgrade wave prioritised. (5) CAB approval lead time 5–10 business days per firewall change — CAB pre-engagement initiated in week 1 of Part 2.

SECTION 8 — ORACLE MODERNISATION [OPTIONAL — include if Oracle in estate]

## 8. Oracle Modernisation

Oracle is frequently the highest-risk and highest-cost element of any migration. A named section prevents it from being buried in the wave plan.

### 8.1 Oracle Estate Summary

| Workload | Version | Licence Model | VM / Node Count | Recommended Path | Est. Annual Saving |
| --- | --- | --- | --- | --- | --- |
| Oracle RAC | [version] | BYOL (Processor) | [N nodes] | Oracle DB on dedicated VM hosts (BYOL) — evaluate OCI in 24 months | £/$ [X] |
| Oracle SE / EE standalone | [version] | BYOL | [N] | Rehost BYOL on [Azure / AWS / GCP] | £/$ [X] |
| Oracle Forms / E-Business Suite | [version] | BYOL | [N] | Rehost IaaS — no PaaS alternative at scale | N/A |
| [TEMPLATE ROW] |  |  |  |  |  |

### 8.2 Oracle Licensing Flags

[ ] Is Oracle licensing currently processor-based or NUP? (affects cloud core count)

[ ] Does the customer have an Oracle Unlimited Licence Agreement (ULA)?

[ ] Are any workloads eligible for Oracle database service inclusion in OCI? (changes hyperscaler recommendation)

[ ] Has the customer engaged Oracle account management on cloud migration intent?

Rackspace Oracle practice note: Engage the Rackspace Oracle DBA practice before committing Oracle licensing recommendations to the Part 2 SOW. Oracle licensing in the cloud has non-obvious traps (VMware soft-partitioning, cloud vCPU multipliers) that require specialist review.

SECTION 9 — PART 2 ENGAGEMENT MODEL [MANDATORY]

## 9. Part 2 Engagement Model

### 9.1 What Part 2 Delivers

| Deliverable | Description | Format |
| --- | --- | --- |
| Detailed migration wave plan | Application-level sequencing with dependencies, cutover windows, rollback plans | Excel + PPTX |
| Architecture blueprints | Landing zone design, network topology, IAM model for [primary cloud] | Visio / draw.io + DOCX |
| Migration runbooks | Wave-level runbooks for Rehost migrations; application-specific for complex workloads | DOCX |
| Oracle migration plan | Detailed Oracle estate migration path with licensing confirmation | DOCX |
| Governance framework | Operating model for cloud-first operations post-migration | DOCX |
| Programme governance | Programme board, weekly reporting, RAID log, change control | Ongoing |
| [Additional — TEMPLATE ROW] |  |  |

### 9.2 Indicative Timeline

| Phase | Duration | Activities |
| --- | --- | --- |
| Foundation | Weeks 1–4 | Landing zone build, tooling deployment, Wave 0 PoC |
| Wave 1 | Weeks 5–12 | Dev/test + non-critical workloads |
| Wave 2 | Weeks 13–20 | Business applications |
| Wave 3 | Weeks 21–32 | Tier-1 / production |
| Wave 4 | Weeks 33–44 | Oracle / complex workloads |
| DC Exit | Weeks 45–52 | Decommission on-prem, final validation |

Timeline is indicative and based on [N] VMs and [N] waves. Actual timeline confirmed at Part 2 kick-off after detailed wave planning.

### 9.3 Investment Summary

| Component | Indicative Range | Basis |
| --- | --- | --- |
| Professional services (Rackspace Part 2 delivery) | £/$ [X]–[Y] | Per SOW |
| Cloud consumption (Year 1 — post-migration) | £/$ [X]–[Y] | Per TCO model |
| Migration tooling (licences) | £/$ [X]–[Y] |  |
| AMM / MAP / PSO funding offset | (£/$ [X]–[Y]) | Subject to programme approval |
| NET YEAR 1 INVESTMENT | £/$ [X]–[Y] | After partner funding |

SECTION 10 — NEXT STEPS [MANDATORY]

## 10. Next Steps

The customer must leave this document knowing exactly what happens next and who does what.

| # | Action | Owner | Target Date |
| --- | --- | --- | --- |
| 1 | Customer sign-off on Part 2 Entry Point | [Customer sponsor name] | [DD Month YYYY] |
| 2 | Rackspace issues Part 2 SOW for review | Rackspace Delivery Manager | [DD Month YYYY] |
| 3 | AMM / MAP / PSO deal registration | Rackspace Alliance Manager | Before SOW signature |
| 4 | Part 2 kick-off meeting (SAs + customer architects) | [Lead Architect] | [DD Month YYYY] |
| 5 | Landing zone decision confirmed (greenfield vs. existing) | [Customer CTO / Lead Architect] | [DD Month YYYY] |
| 6 | Oracle account management engagement | [Customer Oracle owner] | [DD Month YYYY] |
| [TEMPLATE ROW] |  |  |  |

DOCUMENT CONTROL

| Version | Date | Author | Changes |
| --- | --- | --- | --- |
| 0.1 | [DD Month YYYY] | [Lead Architect] | Initial draft |
| 0.2 | [DD Month YYYY] | [Lead Architect] | Customer review feedback incorporated |
| 1.0 | [DD Month YYYY] | [Delivery Director] | Approved for customer presentation |

# Appendix A — Glossary

| Term | Definition |
| --- | --- |
| AMM | Azure Migration and Modernisation — Microsoft funded migration programme |
| AHB | Azure Hybrid Benefit — licence portability for Windows Server and SQL Server on Azure |
| CRA | Cloud Readiness Assessment — Rackspace four-phase assessment framework |
| CUD | Committed Use Discount — GCP equivalent of Reserved Instances |
| L4L | Like-for-Like — cloud sizing based on current on-prem specs without rightsizing |
| MAP | Migration Acceleration Programme — AWS funded migration programme |
| MRA | Migration Readiness Assessment — structured questionnaire required for AMM and MAP |
| Part 2 | CRA Phase 2 — migration execution; follows this Entry Point document |
| PSO | Professional Services Organisation — Google Cloud delivery partner programme |
| RAMP | Rapid Assessment & Migration Program — Google structured migration programme |
| RI | Reserved Instance — pre-committed compute pricing on AWS and Azure (1yr or 3yr) |
| 7Rs | Seven migration patterns: Rehost, Replatform, Rearchitect, Repurchase, Retire, Retain, Relocate |

Content Specification: Rackspace Cloud Solutions Architecture — CRA Framework v2.0

© 2026 Rackspace Technology. All rights reserved.