## Instructions
Instructions — dependency-mapping.xlsx
Read this before opening any other tab
PURPOSE
Map application-to-application and application-to-infrastructure dependencies. This is used to identify dependency clusters in Phase 2 and sequence migration waves in Phase 4. Applications with tightly-coupled dependencies cannot be separated across different migration waves.
WHO FILLS THIS IN
Lead Architect (facilitation) + Application Owners (workshop participants). The dependency data comes from two sources: (1) automated discovery tooling (Azure Migrate network dependencies, AWS ADS, GCP Migration Center), and (2) workshops with application owners.
WHEN TO USE
Phase 1 Weeks 2–6. Workshops with application owners should be scheduled in Phase 1 Week 2 while discovery tooling is still collecting data in the background. Do not wait for Phase 1 to complete.
WHAT 'GOOD DATA' LOOKS LIKE
• Every Tier-1 application has its dependencies validated by its application owner
• Dependency Cluster IDs assigned to all tightly-coupled groups
• External dependencies (SaaS, APIs, third-party services) are documented
• Bi-directional dependencies captured (upstream AND downstream)
• Latency-sensitive dependencies flagged (cannot tolerate WAN latency post-migration)
COMMON MISTAKES TO AVOID
• Relying on automated tools only — they miss application-level logical dependencies
• Not capturing database-level dependencies (shared SQL instances across apps)
• Ignoring SaaS dependencies — a migrated app that calls an on-prem SaaS proxy breaks
• Not clustering tightly-coupled apps — splitting them across waves causes migration failures
CRA Framework v2.0 ¦ Rackspace Cloud Solutions Architecture ¦ dependency-mapping.xlsx

## Dashboard
CLOUD READINESS ASSESSMENT
DEPENDENCY MAPPING TEMPLATE
PROJECT INFORMATION
Field | Value |  |  | Field | Value
Project Name | [Enter Project Name] |  |  | Project Manager | [Enter PM Name]
Organization | [Enter Organization] |  |  | Technical Lead | [Enter Tech Lead]
Assessment Start Date | [Enter Date] |  |  | Target Completion | [Enter Date]
Cloud Target(s) | [AWS/Azure/GCP] |  |  | Assessment Phase | [Discovery/Analysis]
DISCOVERY METRICS (Auto-Calculated)
Metric | Count | Source
Total Servers Discovered |  | Server_Inventory
Total Network Connections |  | Network_Dependencies
Total Application Dependencies |  | App_Dependencies
Total Processes Mapped |  | Process_Mapping
DISCOVERY SOURCE BREAKDOWN
Source | Servers | Network | Apps | Processes
AWS ADS
Azure Migrate
GCP Migration Center
Manual Entry
DEPENDENCY CRITICALITY ANALYSIS
Criticality Level | Count | Percentage
Critical
High
Medium
Low
READINESS ASSESSMENT STATUS
Assessment Area | Status | Completion % | Owner | Notes
Server Discovery | Not Started | 0%
Network Dependency Mapping | Not Started | 0%
Application Dependency Analysis | Not Started | 0%
Process Inventory | Not Started | 0%
Data Validation | Not Started | 0%
Stakeholder Review | Not Started | 0%
TEMPLATE INSTRUCTIONS
Step 1: Fill in Project Information above
Step 2: Deploy cloud discovery tools (AWS ADS, Azure Migrate, GCP Migration Center)
Step 3: Export data and populate inventory sheets
Step 4: Dashboard metrics auto-calculate as data is added
Step 5: Update status and complete stakeholder review
PREREQUISITES & REMEDIATION SUMMARY
Cloud Provider | Total Prerequisites | Complete | In Progress | Blocked
AWS ADS | 16
Azure Migrate | 18
GCP Migration Center | 16
Category | Total Items | Validated/Resolved | Pending
Assumptions | 15
Active Gaps/Remediation Items | 20

## Overview
CLOUD READINESS ASSESSMENT - DEPENDENCY MAPPING TEMPLATE
Reusable Template for Cloud Migration Dependency Discovery
PURPOSE
This template provides a standardized, cloud-agnostic approach to capture dependency mapping data
as part of cloud readiness assessment projects. It is designed to be populated with data from:
• AWS Application Discovery Service (ADS)
• Azure Migrate Dependency Analysis
• Google Cloud Migration Center
• Manual discovery and documentation
CLOUD PROVIDER TOOLS REFERENCE
Cloud Provider | Migration Tool | Dependency Feature | Discovery Method | Export Format
AWS | Application Discovery Service | Agent & Agentless Discovery | TCP Connections, Processes | CSV via Migration Hub
Azure | Azure Migrate | Dependency Analysis | Service Map, TCP Data | CSV, Log Analytics
Google Cloud | Migration Center | Application Dependency Mapping | Topology Scanning | BigQuery, CSV
TEMPLATE SHEETS OVERVIEW
Sheet Name | Purpose | Data Source | Key Fields
Dashboard | Project overview & auto-calculated metrics | Auto-populated from other sheets | Metrics, Status, Progress
Server_Inventory | Master list of discovered servers | Cloud tool exports | Server ID, IP, OS, Resources
Network_Dependencies | TCP connections between servers | Agent-based discovery | Source, Destination, Ports
App_Dependencies | Application-to-application dependencies | Discovery + Manual input | Apps, Criticality, Protocols
Process_Mapping | Running processes on servers | Agent-based discovery | Processes, Ports, Resources
Tool_Reference | Cloud tool guidance | Reference documentation | Commands, Features, Tips
Process_Data_Guide | Detailed instructions for extracting process data | Reference guide - AWS, Azure, GCP extraction methods | Commands, Queries, Field Mappings
Prerequisites_Remediation | Prerequisites, assumptions & remediation guide | Template reference + project tracking | Prerequisites, Assumptions, Gaps, Remediation
HOW TO USE THIS TEMPLATE
Step | Action | Details
1 | Initialize Project | Fill in project information on Dashboard sheet
2 | Deploy Discovery Tools | Install AWS ADS Agent, Azure Migrate Appliance, or GCP collectors
3 | Run Discovery | Allow tools to collect data (typically 1-4 weeks for complete mapping)
4 | Export Data | Use native export features to download CSV/BigQuery data
5 | Populate Sheets | Map exported fields to template columns using Tool_Reference guide
6 | Validate Data | Cross-check dependencies, identify gaps
7 | Review & Sign-off | Stakeholder review of dependency mapping completeness
DEPENDENCY MAPPING SCOPE
In Scope | Out of Scope
Server discovery and inventory | Migration wave planning
Network dependency mapping (TCP connections) | Target architecture design
Application-to-application dependencies | Migration execution
Process and service mapping | Cost estimation/TCO
Dependency criticality assessment | Workload right-sizing
Data validation and review | Application modernization decisions
VERSION CONTROL
Version | Date | Author | Changes
1 | [Date] | [Author] | Initial template creation

## Server_Inventory
SERVER INVENTORY
Cloud Readiness Assessment - Dependency Mapping Template
Instructions: Populate with data exported from AWS ADS, Azure Migrate, or GCP Migration Center
Server ID | Hostname | FQDN | Primary IP | Secondary IPs | Operating System | OS Version | CPU Cores | RAM (GB) | Storage (GB) | Environment | Data Center/Location | Application Name | Server Role | Hypervisor/Platform | Discovery Source | Discovery Date | AWS ADS ID | Azure Migrate ID | GCP MC ID
[Auto/Manual] | [hostname] | [fqdn.domain.com] | [x.x.x.x] | [comma separated] | [Windows/Linux] | [version] | [#] | [#] | [#] | [Prod/Dev/Test] | [DC Name] | [App Name] | [Web/DB/App] | [VMware/HyperV/KVM/Physical] | [AWS ADS/Azure Migrate/GCP Migration Center/Manual] | [YYYY-MM-DD] | [d-server-xxx] | [srv-xxx] | [mc-xxx]

## Network_Dependencies
NETWORK DEPENDENCIES
Cloud Readiness Assessment - TCP Connection Mapping
Instructions: Capture TCP connections from AWS ADS exports, Azure Migrate, or GCP Migration Center
Connection ID | Source Server ID | Source Hostname | Source IP | Source Process | Source Port | Dest Server ID | Dest Hostname | Dest IP | Dest Port | Dest Process | Protocol | Bytes Transferred | Connection Count | First Observed | Last Observed | Dependency Type | Discovery Source | Notes
[Auto/CON-xxx] | [SRV-xxx] | [hostname] | [x.x.x.x] | [process name] | [port#] | [SRV-xxx] | [hostname] | [x.x.x.x] | [port#] | [process name] | [TCP/UDP] | [bytes] | [count] | [YYYY-MM-DD] | [YYYY-MM-DD] | [Database/API/Web/Cache/etc] | [AWS ADS/Azure Migrate/GCP Migration Center/Manual] | [notes]

## App_Dependencies
APPLICATION DEPENDENCIES
Cloud Readiness Assessment - Application-to-Application Dependency Mapping
Instructions: Document dependencies between applications for readiness assessment
Dependency ID | Source Application | Source Owner | Source Environment | Target Application | Target Owner | Target Environment | Dependency Direction | Criticality | Protocol | Port(s) | Data Flow Description | SLA Requirement | Can Operate Independently? | Readiness Impact | Discovery Source | Validation Status | Notes
[APP-DEP-xxx] | [App Name] | [Team/Owner] | [Prod/Dev/Test] | [App Name] | [Team/Owner] | [Prod/Dev/Test] | [Inbound/Outbound/Bidirectional] | [Critical/High/Medium/Low] | [HTTPS/TCP/REST/SOAP] | [port#] | [description] | [99.99%/99.9%/etc] | [Yes/No/Degraded] | [Critical/High/Medium/Low] | [AWS ADS/Azure Migrate/GCP Migration Center/Manual] | [Validated/Pending/Failed] | [notes]

## Process_Mapping
PROCESS MAPPING
Cloud Readiness Assessment - Server Process Discovery
Instructions: Populate with process data from agent-based discovery (AWS ADS Agent, Azure Dependency Agent)
Process ID | Server ID | Hostname | Process Name | Process Path | Process User | PID | Parent Process | Application Name | Listening Ports | Active Connections | CPU Usage (%) | Memory Usage (MB) | Start Time | Status | Service Type | Dependencies | Discovery Source | Notes
[PROC-xxx] | [SRV-xxx] | [hostname] | [process] | [/path/to/process] | [user] | [#] | [parent] | [App Name] | [port,port] | [#] | [%] | [MB] | [datetime] | [Running/Stopped] | [Web/DB/App/Cache/Queue] | [comma separated] | [AWS ADS/Azure Migrate/GCP Migration Center/Manual] | [notes]

## Tool_Reference
CLOUD DEPENDENCY MAPPING - TOOL REFERENCE GUIDE
Quick Reference for AWS, Azure, and Google Cloud Native Discovery Tools
AWS APPLICATION DISCOVERY SERVICE (ADS)
Feature | Description | Data Captured | Export Method | Best Use Case
Agentless Discovery | VMware vCenter Connector OVA | VM inventory, basic metrics | CSV via Migration Hub | Quick inventory scan
Agent-Based Discovery | Discovery Agent on each server | Processes, TCP connections, performance | CSV Export, API | Deep dependency mapping
Network Connections | TCP connection capture between servers | Source/Dest IP, Port, Bytes | Network CSV Export | Server communication mapping
Migration Hub | Centralized discovery dashboard | Aggregated server data | Console, API | Unified view
AWS ADS Export Commands:
Command | Purpose
aws discovery start-export-task | Export data to S3 bucket
aws discovery describe-configurations | Query server configurations
aws discovery list-configurations | List all discovered items
AZURE MIGRATE - DEPENDENCY ANALYSIS
Feature | Description | Data Captured | Export Method | Best Use Case
Agentless Analysis | Azure Migrate Appliance polls TCP | Source/Dest server, process, port | CSV (30 days retention) | VMware, Hyper-V, Physical
Agent-Based Analysis | Log Analytics + Dependency Agent | Connections, latency, data transfer | Log Analytics Query | Deep analysis with Service Map
Dependency Visualization | Interactive map of connections | Visual graph, connection details | Screenshot, CSV | Understanding architecture
Service Map | Azure Monitor solution | Process-level dependencies | Kusto Query | Complex environments
Azure Migrate Capabilities:
Capability | Details
Polling Frequency | Every 5 minutes for TCP data
Data Retention | 30 days (agentless), configurable (agent)
Supported Platforms | VMware, Hyper-V, Physical, AWS, GCP VMs
GOOGLE CLOUD MIGRATION CENTER
Feature | Description | Data Captured | Export Method | Best Use Case
Migration Center Discovery | Automated asset discovery | Server inventory, dependencies | BigQuery, CSV | Multi-cloud environments
Application Mapping | Cross-workload dependencies | Server interactions, topology | BigQuery, Console | Complex architectures
BigQuery Exporter | Advanced analytics export | Full infrastructure data | BigQuery tables | Custom reporting
GCP Partner Tools:
Tool | Provider | Key Feature
CAST Software | CAST | Static code analysis
Matilda Cloud | Matilda | Agentless topology discovery
Txture | Txture | IT infrastructure mapping
DATA FIELD MAPPING GUIDE
Map exported data from each cloud tool to this template's columns
SERVER_INVENTORY FIELD MAPPING
Template Column
Server ID | configurationId | Machine ID | Asset ID
Hostname | server.hostName | Machine name | Name
Primary IP | networkInterfaceInfo.ipAddress | IP addresses | IP Address
Operating System | server.osName | Operating system | OS Type
OS Version | server.osVersion | OS version | OS Version
CPU Cores | server.cpuCount | Number of cores | CPU Count
RAM (GB) | server.totalRamInMB / 1024 | Memory (MB) / 1024 | Memory GB
NETWORK_DEPENDENCIES FIELD MAPPING
Template Column
Source IP | sourceServer.ipAddress | Source IP | Source Address
Source Process | sourceProcess.name | Source process name | Source Process
Dest IP | destinationServer.ipAddress | Destination IP | Destination Address
Dest Port | destinationPort | Destination port | Destination Port
Bytes Transferred | bytesTransferred | Data sent/received | Traffic Volume
BEST PRACTICES FOR DEPENDENCY DISCOVERY
Recommendation
Discovery Duration | Run discovery for 2-4 weeks to capture periodic connections
Multiple Sources | Use both agentless AND agent-based for comprehensive coverage
Validate Results | Cross-check discovered dependencies with application owners
Document Manual Entries | Some dependencies may not be captured automatically
Update Regularly | Re-run discovery before major migration phases
TEMPLATE VERSION INFORMATION
Item
Template Version | 1
Last Updated | 2026-04-01
Scope | Cloud Readiness Assessment - Dependency Mapping

## Process_Data_Guide
PROCESS MAPPING DATA COLLECTION GUIDE
How to Extract Process Data from AWS, Azure, and GCP Migration Tools
AWS APPLICATION DISCOVERY SERVICE - PROCESS DATA EXTRACTION
⚠️ PREREQUISITE: Agent-Based Discovery Required - Agentless does NOT capture process data
Method 1: AWS Console Export
Step | Action | Details | Output
1 | Navigate to Migration Hub | AWS Console → Migration Hub → Discover → Servers | Server list
2 | Select Server | Click on server hostname | Server detail page
3 | View Processes Tab | Click 'Running processes' tab | Process list
4 | Export Data | Click 'Export' → Select 'Running processes' | CSV download
5 | Repeat for All | Export for each server | Multiple CSVs
Method 2: AWS CLI Bulk Export
Command | Purpose
aws discovery start-export-task --export-data-format CSV | Initiates bulk export to S3
aws discovery describe-export-tasks | Check export status
processes.csv in S3 bucket | Contains all process data
AWS ADS → Process_Mapping Field Mapping
Template Column | AWS ADS Field | Notes
Process Name | process.name | Executable name
Process Path | process.cmdLine | Full command line
Process User | process.user | Running user
Listening Ports | process.transportProtocol + portNumber | Combine fields
CPU Usage (%) | process.cpuUsagePct | Average CPU
Memory Usage (MB) | process.memoryUsageMB | Memory consumption
AZURE MIGRATE - PROCESS DATA EXTRACTION
⚠️ PREREQUISITE: Agentless = limited data ¦ Agent-Based (Service Map) = full process details
Method 1: Agentless Dependency Analysis (Limited Process Data)
Step | Action | Details | Output
1 | Enable Dependency Analysis | Azure Portal → Azure Migrate → Enable | Polling starts
2 | Wait 30 days | Appliance polls every 5 minutes | Data accumulates
3 | View Dependencies | Click server → Dependencies | Process names & ports
4 | Export CSV | Click 'Export' button | CSV file
Method 2: Agent-Based (Service Map) - RECOMMENDED for Full Process Data
Step | Action | Details | Output
1 | Create Log Analytics Workspace | Azure Portal → Log Analytics → Create | Workspace ready
2 | Enable Service Map | Workspace → Solutions → Add Service Map | Solution enabled
3 | Install Log Analytics Agent | Download & install on servers | Agent reporting
4 | Install Dependency Agent | Install after LA Agent | Full capture starts
5 | Query VMProcess table | Log Analytics → Logs → KQL query | Process data
6 | Export Results | Export query to CSV | All fields available
KQL Query for Process Data:
VMProcess ¦ where TimeGenerated > ago(7d)
¦ project Computer, Process, ExecutablePath, UserName, Pid, WorkingSet
¦ summarize by Computer, Process, ExecutablePath, UserName
Azure → Process_Mapping Field Mapping
Template Column | Service Map Field | Agentless Field | Notes
Process Name | Process | Process name | Both methods
Process Path | ExecutablePath | N/A | Agent only
Process User | UserName | N/A | Agent only
PID | Pid | N/A | Agent only
Memory (MB) | WorkingSet / 1048576 | N/A | Convert bytes
Listening Ports | Query VMConnection | DestinationPort | Join tables
GOOGLE CLOUD MIGRATION CENTER - PROCESS DATA EXTRACTION
⚠️ PREREQUISITE: Discovery Client (mcdc) or Partner Tools (StratoZone) required for process data
Method 1: Migration Center Discovery Client (mcdc)
Step | Action | Details | Output
1 | Download mcdc | gcloud migration-center discovery-client download | mcdc binary
2 | Run Discovery | mcdc discover --project=PROJECT_ID | Collects process data
3 | Upload Data | mcdc upload --project=PROJECT_ID | Data in console
4 | Export to BigQuery | Migration Center → Export → BigQuery | BQ tables
5 | Query & Export | SELECT * FROM dataset.processes | CSV export
Method 2: StratoZone (Partner Tool - More Detailed)
Step | Action | Details | Output
1 | Request Access | Contact Google Cloud or partner | Portal access
2 | Deploy Collector | Install StratoProbe in environment | Discovery starts
3 | Install Agent | Deploy on servers for process data | Process capture
4 | Generate Reports | StratoZone → Reports | Process report
5 | Export Data | Reports → Export CSV | All fields
GCP → Process_Mapping Field Mapping
Template Column | Migration Center Field | StratoZone Field | Notes
Process Name | process_name | process_name | Both methods
Process Path | process_path (partial) | executable_path | StratoZone better
Process User | process_user (partial) | run_as_user | StratoZone better
Listening Ports | listening_ports | open_ports | Both methods
CPU Usage (%) | cpu_utilization | avg_cpu_percent | Both methods
Memory (MB) | memory_usage_mb | memory_mb | Both methods
PROCESS DATA CAPABILITY COMPARISON
Process_Mapping Field | AWS ADS (Agent) | Azure (Service Map) | GCP (mcdc/StratoZone)
Process Name | ✅ Full | ✅ Full | ✅ Full
Process Path | ✅ Full | ✅ Full | ⚠️ Partial / ✅ StratoZone
Process User | ✅ Full | ✅ Full | ⚠️ Partial / ✅ StratoZone
PID | ⚠️ Limited | ✅ Full | ❌ N/A
Parent Process | ❌ N/A | ✅ Full | ❌ N/A
Listening Ports | ✅ Full | ✅ Full | ✅ Full
CPU Usage | ✅ Full | ⚠️ Requires query | ✅ Full
Memory Usage | ✅ Full | ✅ Full | ✅ Full
Active Connections | ✅ Full | ✅ Full | ✅ Full
Legend: | ✅ = Full ¦ ⚠️ = Partial ¦ ❌ = N/A
REMEDIATION: WHEN PROCESS DATA IS NOT AVAILABLE
Scenario | Root Cause | Remediation | Fallback
No process data | Agentless only | Deploy agents | Manual: ps aux / Get-Process
Missing process path | Agent limitation | Use agent-based | Manual: wmic process
No listening ports | Firewall blocking | Update firewall rules | Manual: netstat -tlnp
Partial coverage | Incomplete deployment | Complete agent rollout | Prioritize critical servers
Stale data | Short discovery period | Run 2-4 weeks minimum | Re-run discovery
Unsupported OS | Legacy OS | Document as gap | Manual collection
Permission denied | Insufficient privileges | Request admin access | Work with server owners
MANUAL PROCESS COLLECTION COMMANDS (FALLBACK)
OS | Command | Purpose
Linux | ps aux --sort=-%mem ¦ head -50 | Top 50 processes by memory
Linux | ss -tlnp | Listening TCP ports with processes
Linux | lsof -i -P -n | Open network connections
Linux | systemctl list-units --type=service | Running services
Windows | Get-Process ¦ Select Name, Id, CPU, WorkingSet | Process list with resources
Windows | Get-NetTCPConnection -State Listen | Listening ports
Windows | Get-Service ¦ Where Status -eq Running | Running services
Windows | wmic process get name,processid,executablepath | Process details

## Prerequisites_Remediation
PREREQUISITES, ASSUMPTIONS & REMEDIATION GUIDE
Cloud Readiness Assessment - Dependency Mapping Template
Document prerequisites, validate assumptions, and define remediation actions when dependency data cannot be captured
AWS APPLICATION DISCOVERY SERVICE (ADS) - PREREQUISITES
Prerequisite Category | Prerequisite Item | Description/Requirement | Status | Responsible Party | Notes/Remediation
Account & Permissions | AWS Account | Active AWS account with billing enabled | ☐ Not Started | [Assign Owner] | Create AWS account if not available
Account & Permissions | IAM Permissions | AWSApplicationDiscoveryServiceFullAccess policy | ☐ Not Started | [Assign Owner] | Create IAM role with required permissions
Account & Permissions | Migration Hub Access | Access to AWS Migration Hub in target region | ☐ Not Started | [Assign Owner] | Enable Migration Hub in supported region
Network Requirements | Outbound Internet | HTTPS (443) to discovery.us-west-2.amazonaws.com | ☐ Not Started | [Assign Owner] | Configure firewall/proxy rules
Network Requirements | Internal Network | Agent must reach all servers to discover | ☐ Not Started | [Assign Owner] | Review network segmentation
Agent-Based Discovery | Discovery Agent | Download and install AWS Discovery Agent on servers | ☐ Not Started | [Assign Owner] | Plan agent deployment strategy
Agent-Based Discovery | Supported OS | Windows 2008R2+, Amazon Linux, Ubuntu, RHEL, CentOS | ☐ Not Started | [Assign Owner] | Identify unsupported OS - use agentless
Agent-Based Discovery | Root/Admin Access | Administrator (Win) or root (Linux) for installation | ☐ Not Started | [Assign Owner] | Obtain elevated credentials
Agentless Discovery | VMware vCenter | vCenter Server 5.5+ with read-only credentials | ☐ Not Started | [Assign Owner] | Request vCenter access from VMware team
Agentless Discovery | OVA Appliance | Deploy Discovery Connector OVA in VMware env | ☐ Not Started | [Assign Owner] | Download OVA from AWS console
Agentless Discovery | vCenter Permissions | Read-only access to VMs, folders, datacenters | ☐ Not Started | [Assign Owner] | Create service account in vCenter
Data Export | S3 Bucket | S3 bucket for data export (optional) | ☐ Not Started | [Assign Owner] | Create S3 bucket with appropriate policies
Data Export | Export Permissions | IAM permissions for s3:PutObject | ☐ Not Started | [Assign Owner] | Add S3 permissions to IAM role
Timeline | Discovery Duration | Minimum 2-4 weeks for complete mapping | ☐ Not Started | [Assign Owner] | Plan discovery window in project timeline
Stakeholder | Application Owners | Contact list for dependency validation | ☐ Not Started | [Assign Owner] | Gather stakeholder contact information
Documentation | Server Inventory | Initial server list for agent deployment planning | ☐ Not Started | [Assign Owner] | Export from CMDB or manual collection
AZURE MIGRATE - DEPENDENCY ANALYSIS PREREQUISITES
Prerequisite Category | Prerequisite Item | Description/Requirement | Status | Responsible Party | Notes/Remediation
Subscription & Permissions | Azure Subscription | Active Azure subscription with Contributor access | ☐ Not Started | [Assign Owner] | Create subscription or request access
Subscription & Permissions | Resource Group | Resource group for Azure Migrate project | ☐ Not Started | [Assign Owner] | Create RG in target region
Subscription & Permissions | RBAC Permissions | Contributor role on subscription or resource group | ☐ Not Started | [Assign Owner] | Request RBAC assignment from Azure admin
Subscription & Permissions | Azure Migrate Project | Create Azure Migrate project in portal | ☐ Not Started | [Assign Owner] | Navigate to Azure Migrate > Create project
Agentless Discovery | Azure Migrate Appliance | Deploy appliance VM (OVA for VMware, VHD for Hyper-V) | ☐ Not Started | [Assign Owner] | Download from Azure portal
Agentless Discovery | Appliance Requirements | 16 GB RAM, 8 vCPUs, 80 GB disk minimum | ☐ Not Started | [Assign Owner] | Provision VM meeting requirements
Agentless Discovery | vCenter Credentials | Read-only account for VMware vCenter (VMware only) | ☐ Not Started | [Assign Owner] | Create service account
Agentless Discovery | Hyper-V Credentials | Domain or local admin for Hyper-V hosts | ☐ Not Started | [Assign Owner] | Obtain credentials from Hyper-V team
Network Requirements | Outbound Connectivity | HTTPS 443 to *.azure.com, *.microsoftonline.com | ☐ Not Started | [Assign Owner] | Configure proxy/firewall exceptions
Network Requirements | Port Requirements | TCP 443, 5985 (WinRM), 22 (SSH) for discovery | ☐ Not Started | [Assign Owner] | Open required ports
Agent-Based Analysis | Log Analytics Workspace | Create workspace for dependency data storage | ☐ Not Started | [Assign Owner] | Create in same region as Migrate project
Agent-Based Analysis | Microsoft Monitoring Agent | Install MMA on Windows servers | ☐ Not Started | [Assign Owner] | Deploy via SCCM, GPO, or manual
Agent-Based Analysis | Dependency Agent | Install Dependency Agent on all servers | ☐ Not Started | [Assign Owner] | Deploy alongside MMA
Agent-Based Analysis | Supported OS | Windows Server 2008R2+, RHEL 6+, Ubuntu 14.04+ | ☐ Not Started | [Assign Owner] | Identify unsupported OS - use agentless
Service Map | Service Map Solution | Enable Service Map in Log Analytics workspace | ☐ Not Started | [Assign Owner] | Add solution from Azure Marketplace
Data Retention | Retention Period | Configure 30+ days retention for dependency data | ☐ Not Started | [Assign Owner] | Set retention in workspace settings
Stakeholder | Application Owners | Contact list for dependency validation | ☐ Not Started | [Assign Owner] | Gather stakeholder information
Timeline | Discovery Duration | Minimum 2-4 weeks for comprehensive mapping | ☐ Not Started | [Assign Owner] | Plan in project schedule
GOOGLE CLOUD MIGRATION CENTER - PREREQUISITES
Prerequisite Category | Prerequisite Item | Description/Requirement | Status | Responsible Party | Notes/Remediation
Project & Permissions | GCP Project | Active GCP project with billing enabled | ☐ Not Started | [Assign Owner] | Create project in GCP Console
Project & Permissions | IAM Roles | Migration Center Admin or Editor role | ☐ Not Started | [Assign Owner] | Assign roles/migrationcenter.admin
Project & Permissions | API Enablement | Enable Migration Center API | ☐ Not Started | [Assign Owner] | gcloud services enable migrationcenter.googleapis.com
Project & Permissions | Service Account | Service account for discovery collectors | ☐ Not Started | [Assign Owner] | Create SA with required permissions
Discovery Methods | Discovery Client CLI | Install mcdc (Migration Center Discovery Client) | ☐ Not Started | [Assign Owner] | Download from GCP documentation
Discovery Methods | VMware Discovery | vSphere credentials for VMware environments | ☐ Not Started | [Assign Owner] | Create read-only vCenter account
Discovery Methods | AWS Import | AWS credentials for cross-cloud discovery | ☐ Not Started | [Assign Owner] | Create IAM user with read permissions
Discovery Methods | Azure Import | Azure credentials for cross-cloud discovery | ☐ Not Started | [Assign Owner] | Create service principal
Network Requirements | Outbound HTTPS | HTTPS 443 to *.googleapis.com | ☐ Not Started | [Assign Owner] | Configure firewall rules
Network Requirements | Collector Network | Collector must reach all target servers | ☐ Not Started | [Assign Owner] | Review network topology
Data Export | BigQuery Dataset | Create BigQuery dataset for export | ☐ Not Started | [Assign Owner] | Create dataset in same region
Data Export | BigQuery Permissions | BigQuery Data Editor role for export | ☐ Not Started | [Assign Owner] | Grant permissions to service account
Partner Tools | CAST Software | License for CAST (if using for code analysis) | ☐ Not Started | [Assign Owner] | Contact CAST for licensing
Partner Tools | Matilda Cloud | Matilda subscription (if using) | ☐ Not Started | [Assign Owner] | Contact Matilda for trial/license
Stakeholder | Application Owners | Contact list for validation | ☐ Not Started | [Assign Owner] | Compile stakeholder list
Timeline | Discovery Duration | 2-4 weeks minimum for comprehensive data | ☐ Not Started | [Assign Owner] | Allocate time in project plan
KEY ASSUMPTIONS FOR DEPENDENCY MAPPING
Assumption ID | Assumption Category | Assumption Statement | Validation Required? | Impact if Invalid | Validated By
ASM-001 | Network Access | All servers are reachable from discovery tools/agents | Yes | Incomplete dependency discovery | [Validator]
ASM-002 | Credentials | Required credentials will be provided within project timeline | Yes | Discovery delays | [Validator]
ASM-003 | Discovery Duration | 4-week discovery period captures all periodic connections | Yes | Missing monthly/quarterly batch jobs | [Validator]
ASM-004 | Agent Deployment | Agents can be deployed on all in-scope servers | Yes | Gaps in process-level data | [Validator]
ASM-005 | VMware Environment | VMware vCenter is available for agentless discovery | Yes | Must use agent-based only | [Validator]
ASM-006 | Firewall Rules | Firewall changes can be implemented for discovery traffic | Yes | Limited connectivity data | [Validator]
ASM-007 | Application Knowledge | Application owners can validate discovered dependencies | Yes | Unvalidated dependency data | [Validator]
ASM-008 | Data Accuracy | Discovery tools capture >90% of active connections | Yes | Manual gap analysis required | [Validator]
ASM-009 | Server Inventory | Initial server inventory is accurate and complete | Yes | Missing servers in discovery | [Validator]
ASM-010 | Change Freeze | No major infrastructure changes during discovery period | Yes | Inconsistent baseline data | [Validator]
ASM-011 | Cloud Account Access | Cloud accounts (AWS/Azure/GCP) provisioned before kickoff | Yes | Project start delays | [Validator]
ASM-012 | Stakeholder Availability | Key stakeholders available for reviews and validation | Yes | Sign-off delays | [Validator]
ASM-013 | Tool Licensing | Required tool licenses available (if third-party tools) | Yes | Alternate tool selection needed | [Validator]
ASM-014 | Data Retention | Discovery data retained for full assessment duration | Yes | Re-discovery may be needed | [Validator]
ASM-015 | Security Approvals | Security team approves agent deployment and data collection | Yes | Blocked discovery activities | [Validator]
REMEDIATION ACTIONS - WHEN DEPENDENCY DATA CANNOT BE CAPTURED
Gap ID | Data Gap Scenario | Root Cause | Remediation Action | Fallback Approach | Risk if Unresolved
GAP-001 | Agent cannot be installed on legacy servers | Unsupported OS (Windows 2003, old Linux) | Use agentless discovery + manual interviews | Manual dependency documentation from SMEs | Incomplete process-level dependencies
GAP-002 | Network connections not visible | Firewall blocking discovery traffic | Request firewall rule changes for discovery ports | Network team provides firewall logs for analysis | Missing inter-zone dependencies
GAP-003 | vCenter access not available | VMware team security restrictions | Escalate to management, provide security docs | Deploy agents on individual VMs instead | No agentless discovery capability
GAP-004 | Encrypted traffic not decoded | TLS/SSL connections hide application data | Use agent-based discovery for process names | Application owner interviews to identify endpoints | Unknown application-level dependencies
GAP-005 | Cloud account not provisioned | Approval delays for cloud access | Parallel track: prepare while awaiting access | Use third-party tools (CAST, Matilda) if licensed | Delayed project start
GAP-006 | Batch jobs not captured | Jobs run monthly/quarterly, outside discovery window | Extend discovery period or schedule job runs | Review job scheduler configs, interview operators | Missing periodic dependencies
GAP-007 | DR/Secondary site not discovered | Agents not deployed in DR environment | Include DR environment in discovery scope | Manual documentation of DR dependencies | Incomplete DR dependency map
GAP-008 | Third-party SaaS dependencies | External services not in discovery scope | Manual documentation of SaaS integrations | Application config review, DNS analysis | Unknown external dependencies
GAP-009 | Database dependencies unclear | Connection pooling hides actual sources | Query database connection logs directly | DBA interviews, application config review | Inaccurate DB dependency mapping
GAP-010 | Containerized workloads | Traditional agents don't work in containers | Use container-native discovery (if available) | Review Kubernetes/Docker configs, service mesh | Missing container dependencies
GAP-011 | Load balancer hiding backends | VIP masks actual server connections | Discover LB configs, document backend pools | Network team provides LB configuration export | Incomplete server-to-server mapping
GAP-012 | Air-gapped networks | No internet connectivity for cloud tools | Deploy on-premises data collector | Manual discovery with network scanning tools | Limited automation capability
GAP-013 | Credentials not provided in time | Security/compliance approval delays | Escalate, provide security questionnaire responses | Start with subset of servers with access | Delayed discovery completion
GAP-014 | High server count overwhelms tools | Discovery tool performance limits | Phased discovery by application group | Prioritize critical applications first | Extended discovery timeline
GAP-015 | Dynamic IP addressing | DHCP causes IP changes during discovery | Use hostname-based correlation | Document IP ranges, use DNS resolution | Inconsistent connection mapping
GAP-016 | Multi-cloud environment gaps | Different tools needed per cloud | Use cloud-agnostic tools or multiple native tools | Consolidate data manually into this template | Fragmented dependency view
GAP-017 | Application owner unavailable | SME not available for validation | Schedule dedicated validation sessions early | Use technical documentation, code review | Unvalidated dependency data
GAP-018 | Mainframe/Legacy systems | No modern discovery agent support | Use network flow analysis, SNMP data | Manual documentation from operations team | No automated legacy discovery
GAP-019 | Ephemeral/Auto-scaled instances | Instances created/destroyed frequently | Capture launch configs, not instance-level | Review auto-scaling group configurations | Point-in-time snapshot only
GAP-020 | Discovery data export fails | Tool export functionality issues | Troubleshoot with cloud support | Manual data extraction via console/API | Delayed data population
PROJECT-SPECIFIC PREREQUISITE TRACKING
Tracking ID | Prerequisite/Assumption/Gap | Current Status | Target Date | Owner | Resolution Notes
TRK-001 | [Enter prerequisite, assumption, or gap reference] | ☐ Not Started | [YYYY-MM-DD] | [Assign Owner] | [Enter resolution notes]
TRK-002 | [Enter prerequisite, assumption, or gap reference] | ☐ Not Started | [YYYY-MM-DD] | [Assign Owner] | [Enter resolution notes]
TRK-003 | [Enter prerequisite, assumption, or gap reference] | ☐ Not Started | [YYYY-MM-DD] | [Assign Owner] | [Enter resolution notes]
TRK-004 | [Enter prerequisite, assumption, or gap reference] | ☐ Not Started | [YYYY-MM-DD] | [Assign Owner] | [Enter resolution notes]
TRK-005 | [Enter prerequisite, assumption, or gap reference] | ☐ Not Started | [YYYY-MM-DD] | [Assign Owner] | [Enter resolution notes]
TRK-006 | [Enter prerequisite, assumption, or gap reference] | ☐ Not Started | [YYYY-MM-DD] | [Assign Owner] | [Enter resolution notes]
TRK-007 | [Enter prerequisite, assumption, or gap reference] | ☐ Not Started | [YYYY-MM-DD] | [Assign Owner] | [Enter resolution notes]
TRK-008 | [Enter prerequisite, assumption, or gap reference] | ☐ Not Started | [YYYY-MM-DD] | [Assign Owner] | [Enter resolution notes]
TRK-009 | [Enter prerequisite, assumption, or gap reference] | ☐ Not Started | [YYYY-MM-DD] | [Assign Owner] | [Enter resolution notes]
TRK-010 | [Enter prerequisite, assumption, or gap reference] | ☐ Not Started | [YYYY-MM-DD] | [Assign Owner] | [Enter resolution notes]
QUICK REFERENCE - STATUS VALUES & USAGE GUIDE
Status Values: |  |  | How to Use This Sheet:
☐ Not Started - Prerequisite has not been addressed |  |  | 1. Review all prerequisites for your target cloud(s)
⏳ In Progress - Work is underway to meet prerequisite |  |  | 2. Assign owners and update status as work progresses
✓ Complete - Prerequisite has been met and validated |  |  | 3. Document any assumptions that apply to your project
⚠ Blocked - Prerequisite blocked, remediation needed |  |  | 4. If gaps occur, reference Remediation section for solutions
✗ Not Applicable - Prerequisite not relevant for this project |  |  | 5. Track project-specific items in the tracking table
SECTION NAVIGATION
Section | Row Range | Description | Color Code
AWS ADS Prerequisites | Rows 5-22 | AWS Application Discovery Service requirements | Orange (#FF9900)
Azure Migrate Prerequisites | Rows 24-43 | Azure Migrate Dependency Analysis requirements | Blue (#0078D4)
GCP Migration Center Prerequisites | Rows 45-62 | Google Cloud Migration Center requirements | Google Blue (#4285F4)
Key Assumptions | Rows 64-80 | Assumptions for dependency mapping project | Green (#2E7D32)
Remediation Actions | Rows 82-103 | Actions when data cannot be captured | Red (#C62828)
Project Tracking | Rows 105-116 | Track project-specific items | Purple (#6A1B9A)

## Dependency Heat Map
Dependency Heat Map — Applications by Cluster and Coupling Level
Cluster ID | Application Name | App Tier | Coupling Level | Notes
C001 | [App Name - from inventory] | Tier 1 | Tightly Coupled | Cannot migrate independently - shares DB with C001-B
C001 | [App Name - from inventory] | Tier 2 | Tightly Coupled | C001 cluster must move together in same wave
C002 | [App Name - from inventory] | Tier 3 | Loosely Coupled | Soft dependency - can migrate in adjacent wave
NONE | [App Name - from inventory] | Tier 3 | Independent | No dependencies - Wave 0 PoC candidate
Legend: | Tightly Coupled = must migrate in same wave | Loosely Coupled = adjacent wave | Independent = any wave