## Instructions
Instructions — risk-assessment.xlsx
Read this before opening any other tab
PURPOSE
Document and score all identified risks for the CRA engagement. This register is maintained throughout the engagement and is a key deliverable in the Phase 3 Assessment Report and Part 2 Entry Point. All 11 risk categories must be reviewed for every engagement.
WHO FILLS THIS IN
Lead Architect (maintains). Delivery Manager (reviews weekly). Customer IT Director (reviews at Phase 3 playback). Alliance Manager reviews Commercial category risks.
WHEN TO USE
Phase 2 onwards. Pre-populate all 11 default risk categories at Phase 1 kickoff. Update likelihood and impact scores as more information becomes available. Review and refresh before each phase gate review.
WHAT 'GOOD DATA' LOOKS LIKE
• All 11 risk categories have at least one row (even if Low likelihood)
• Every risk has a named mitigation owner
• Oracle licensing and scope variance risks are scored accurately
• Risk scores (Likelihood x Impact) are current — not from initial assessment
• All Critical and High risks have a documented mitigation plan
COMMON MISTAKES TO AVOID
• Leaving risk register empty until Phase 3 — risks identified early can be mitigated early
• Under-scoring scope variance risk — it is High Likelihood on most engagements
• Not including Commercial category risks (missed partner registration = loss of AMM/MAP funding)
• Marking risks as 'Closed' without verifying the mitigation was actually implemented
CRA Framework v2.0 ¦ Rackspace Cloud Solutions Architecture ¦ risk-assessment.xlsx

## Risk Assessment
Risk & Compliance Assessment
Version 1.0 ¦ Phase: Evaluation ¦ Tasks 6.1, 6.2, 6.3 ¦ Requirements 6.1-6.9
Section 1 — Risk Assessment Matrix (5 × 5)
Likelihood Scale
Level | Rating | Description
5 | Almost Certain | >90% probability, expected to occur
4 | Likely | 60-90% probability, will probably occur
3 | Possible | 30-60% probability, might occur
2 | Unlikely | 10-30% probability, could occur
1 | Rare | <10% probability, exceptional circumstances
Impact Scale
Level | Rating | Description
5 | Critical | Business-critical failure, regulatory breach, >£1M loss
4 | Major | Significant disruption, major financial impact, £500K-£1M
3 | Moderate | Noticeable impact, manageable disruption, £100K-£500K
2 | Minor | Limited impact, minor inconvenience, £10K-£100K
1 | Negligible | Minimal impact, easily absorbed, <£10K
Risk Heat-map (Score = Likelihood × Impact)
| Impact 1 (Negligible) | Impact 2 (Minor) | Impact 3 (Moderate) | Impact 4 (Major) | Impact 5 (Critical)
Likelihood 5 (Almost Certain) | 5 | 10 | 15 | 20 | 25
Likelihood 4 (Likely) | 4 | 8 | 12 | 16 | 20
Likelihood 3 (Possible) | 3 | 6 | 9 | 12 | 15
Likelihood 2 (Unlikely) | 2 | 4 | 6 | 8 | 10
Likelihood 1 (Rare) | 1 | 2 | 3 | 4 | 5
Section 2 — Security Risk Register
ID | Risk Description | Category | Likelihood (1-5) | Impact (1-5) | Score | Mitigation Strategy | Residual Risk | Owner
SR-001 | Data exposure during migration | Data Security
SR-002 | Unauthorized access to cloud resources | Access Control
SR-003 | Encryption gaps in transit/at rest | Encryption
SR-004 | Identity management misconfiguration | IAM
SR-005 | Vulnerability in cloud configuration | Configuration
SR-006 | Insider threat during migration | Personnel
SR-007 | DDoS attack on cloud endpoints | Network
SR-008 | Key management failure | Cryptography
SR-009
SR-010
SR-011
Section 3 — Operational Risk Register
ID | Risk Description | Category | Likelihood (1-5) | Impact (1-5) | Score | Mitigation Strategy | Residual Risk | Owner
OR-001 | Service availability degradation | Availability
OR-002 | Performance degradation post-migration | Performance
OR-003 | Increased operational complexity | Operations
OR-004 | Skills gap in cloud operations | Personnel
OR-005 | Vendor lock-in risk | Strategic
OR-006 | Cost overrun during migration | Financial
OR-007 | Extended downtime during cutover | Migration
OR-008 | Rollback failure | Migration
OR-009
OR-010
OR-011
Section 4 — Compliance Risk Register
ID | Risk Description | Framework | Likelihood (1-5) | Impact (1-5) | Score | Mitigation Strategy | Residual Risk | Owner
CR-001 | GDPR data residency violation | GDPR
CR-002 | PCI-DSS scope expansion | PCI-DSS
CR-003 | Audit trail gaps in cloud | SOC2
CR-004 | Data sovereignty breach | Local Regs
CR-005 | Compliance certification gap | ISO 27001
CR-006 | Third-party data processing risk | GDPR
CR-007
CR-008
CR-009
Section 5 — Compliance Requirements Matrix
Requirement | Applicable | Current Status | Cloud Gap | AWS Coverage | Azure Coverage | GCP Coverage | Remediation | Owner
GDPR
PCI-DSS
HIPAA
SOC 2
ISO 27001
UK DPA 2018
Section 6 — Data Residency & Sovereignty
Data Category | Classification | Current Location | Required Location | Cloud Region | Compliant | Cross-Border | Notes | Owner
Cross-Border Transfer Requirements
Data Processing Agreements Required
Standard Contractual Clauses Required
Section 7 — Security Controls Assessment
Control Area | Current State | Cloud Target | Gap | Priority | Owner | Notes
Identity & Access Management
Encryption (at rest)
Encryption (in transit)
Network Security
Vulnerability Management
Logging & Monitoring
Incident Response
Backup & Recovery
Section 8 — Risk Summary
Category | Total Risks | Critical | High | Medium | Low
Security
Operational
Compliance
Total
Overall Risk Rating
Recommendation
Template Version 1.0 — Cloud Readiness Accelerator Framework

## Risk Summary
Risk Summary Dashboard — CRA Engagement Risk Status
Risk Category | Red Risks (>=9) | Amber Risks (6-8) | Green Risks (<=5)
Scope | 0 | 0 | 0
Data Quality | 0 | 0 | 0
Dependency | 0 | 0 | 0
Licensing | 0 | 0 | 0
End-of-Life OS | 0 | 0 | 0
Regulatory | 0 | 0 | 0
Schedule | 0 | 0 | 0
Resource | 0 | 0 | 0
Commercial | 0 | 0 | 0
Stakeholder | 0 | 0 | 0
Third-Party | 0 | 0 | 0
Note: Update counts manually from the Risk Assessment tab, or add COUNTIFS formulas once row structure is confirmed.