## Cover
Cloud Readiness Assessment — Project Plan
Document Title | Cloud Readiness Assessment — Project Plan & Timeline
Version | 1.0
Status | Draft for Review
Prepared By | Cloud Solutions Architecture Team
Prepared For | [Customer Name]
Date Prepared | April 25, 2026
Engagement Type | Cloud Readiness Assessment (Default Profile)
Target Hyperscaler | Microsoft Azure (primary), AWS / GCP (comparative)
Estate Size (assumed) | Large enterprise — 3,800 servers
Primary Discovery Tool | Azure Migrate (Server Assessment) + RVTools / native exports
Total Elapsed Duration | 16 weeks (~4 months) with parallelized workstreams
Right-Sizing Data Window | Minimum 2 weeks; target 4 weeks for weekly seasonality
Workbook Contents
Cover | Document control, engagement profile, and key parameters.
Assumptions | Engagement assumptions, estate profile, and constraints driving the plan.
Phase Summary | Phase-level durations, dates, and effort with audit notes from the Sr Director review.
WBS & Gantt | Detailed Work Breakdown Structure with task-level Gantt visualization across 18 weeks.
RACI | Roles and responsibilities matrix across all major activities.
Resource Plan | Roles, allocation %, and effort across the engagement.
Risk Register | Top risks with likelihood, impact, mitigation, and owner.
Deliverables | Phase-mapped deliverables with acceptance criteria.

## Assumptions
Engagement Assumptions & Estate Profile
Estate & Scope
# | Assumption | Detail
1 | Estate size | 3,800 servers (large enterprise). Plan scales for this band; smaller = compress, larger = extend Phase 1–2.
2 | Datacenters / sites | 2 – 3 primary datacenters; up to 2 small remote / colocation sites.
3 | Workload mix | ~70% virtualized (VMware vSphere primarily, some Hyper-V); ~20% physical; ~10% PaaS/SaaS already.
4 | OS mix | ~60% Windows Server (2012 R2 → 2022); ~40% Linux (RHEL, Ubuntu, SUSE).
5 | Application count | 150 – 400 distinct business applications, mix of COTS and custom.
6 | In-scope domains | Compute, storage, networking, identity, data, application portfolio, security & compliance posture, FinOps baseline.
7 | Out of scope (default) | Detailed migration execution, code refactoring, application modernization PoCs, end-user computing, IoT/OT estate.
Hyperscaler & Tooling
# | Assumption | Detail
1 | Primary target | Microsoft Azure (Landing Zone aligned to Azure Cloud Adoption Framework).
2 | Comparative target | AWS and GCP TCO comparison at portfolio level (not workload level) unless customer requests deep dive.
3 | Discovery tooling — primary | Azure Migrate appliance (Server Assessment + Dependency Analysis) for VMware/Hyper-V/Physical.
4 | Discovery tooling — supplemental | RVTools (vSphere export), native cloud-side scanners for AWS/GCP if hybrid, SQL Server Assessment, App Service Migration Assistant.
5 | Application discovery | Azure Migrate Dependency Analysis (agentless preferred; agent-based for deeper insight on critical apps only).
6 | Pricing & FinOps | Azure Pricing Calculator, Azure TCO Calculator, ACM/Cost Mgmt for current state where Azure already used; AWS Pricing Calculator and GCP Pricing Calculator for comparative view.
Discovery Data Quality (Sr Director audit)
# | Assumption | Detail
1 | Right-sizing data window — floor | MINIMUM 2 weeks of continuous utilization data before issuing right-sizing recommendations with confidence.
2 | Right-sizing data window — target | 4 weeks recommended to capture weekly seasonality (e.g., month-end batch jobs, weekend reporting cycles).
3 | Discovery setup buffer | 3 weeks budgeted for tooling stand-up — accounts for CAB lead time on firewall changes (typically 5–10 business days), service account provisioning, and appliance certification.
4 | Discovery troubleshooting buffer | 1 week embedded in Phase 1 for known data-capture issues: on-prem firewall egress blocks, WMI/SSH/SNMP failures, OS-level GPO/PowerShell execution policy restrictions, sudoers misconfiguration.
5 | Re-discovery contingency | Assume 10–15% of in-scope servers will require re-discovery cycles due to credential, network, or agent issues. Built into Phase 2 duration.
6 | Inventory completeness target | >= 95% of in-scope servers with utilization data; >= 90% with dependency data. Below this, Phase 4 right-sizing is flagged as low-confidence.
Customer & Governance
# | Assumption | Detail
1 | Change management | Customer follows a formal CAB process. Firewall/network change requests require 5–10 business day lead time; built into Phase 1.
2 | Stakeholder availability | Application owners assumed available 2–3 hours/week per app for interviews. Limited availability is the #1 critical-path risk.
3 | Decision cadence | Weekly Steering Committee, bi-weekly executive readout, daily stand-up within delivery team.
4 | Travel / on-site | Discovery setup and final readouts on-site; majority of work delivered remotely.
5 | Languages / regions | Single primary geography assumed. Multi-region adds 2–3 weeks (data residency, latency studies).
Commercial & Delivery
# | Assumption | Detail
1 | Engagement model | Time & Materials with not-to-exceed cap, milestone-based invoicing.
2 | Team mix | 1 PM (50%, 16 weeks), 1 Lead Cloud Solutions Architect (75%, 16 weeks), 1 Cloud Engineer (100%, 12 weeks), 1 Technical Consultant (75%, 12 weeks), 1 Network Firewall SME (25%, 5 weeks).
3 | Working calendar | 5-day work week, US holidays observed. Plan does NOT compress for hero schedules.
4 | Quality gate | Each phase has a formal exit gate with stakeholder sign-off before next phase commences.

## Phase Summary
Phase Summary — Durations & Audit Notes
# | Phase | Duration (wks) | Start | End | Effort (PD) | Remarks
0 | Initiate & Mobilize | 2 | 2026-04-27 | 2026-05-10 | 18 | Tight but realistic. Assumes contracts already signed and team identified. If MSA negotiation is open, add 2 weeks.
1 | Discovery — Tooling Setup | 3 | 2026-05-11 | 2026-05-31 | 42 | Includes 5–10 business day CAB buffer for firewall changes plus 1-week troubleshooting reserve for OS-level access issues. Compressing this is the #1 cause of unreliable data downstream.
2 | Discovery — Data Collection | 4 | 2026-06-01 | 2026-06-28 | 40 | Hard floor: 2 weeks utilization data for confident right-sizing; targeting 4 weeks to capture weekly seasonality (month-end, payroll, reporting cycles). Includes 1-week buffer for re-discovery on ~10–15% of estate.
3 | Analysis — Application & Infra Profiling | 4 | 2026-06-15 | 2026-07-12 | 38 | Runs in parallel with the back half of Phase 2. Critical-path risk is application-owner availability (2–3 hrs/wk per app). Do NOT shorten.
4 | Evaluation — Right-Sizing & TCO | 3 | 2026-06-29 | 2026-07-19 | 32 | Cannot start until Phase 2 has 2+ weeks of clean utilization data. Pricing modeling, RI/Savings Plan strategy, license optimization (Azure Hybrid Benefit), and 6Rs disposition.
5 | Planning — Migration Waves & Roadmap | 2 | 2026-07-20 | 2026-08-02 | 22 | Wave grouping driven by dependency analysis output. Tighter window acceptable because heavy lifting was done in Phase 3–4.
6 | Readiness Report & Recommendations | 1 | 2026-08-03 | 2026-08-09 | 12 | Compressed to 1 week — requires tight coordination on QA and deliverable finalization. No room for rework.
7 | Stakeholder Review & Sign-off | 1 | 2026-08-10 | 2026-08-16 | 7 | Compressed to 1 week — single combined technical + executive session. Customer must pre-commit to decision-ready attendees.
| TOTAL ELAPSED (parallelized) | 16 | 2026-04-27 | 2026-08-16 | 211 | Sequential total would be 22 weeks; parallelization of Phase 2/3 saves ~6 weeks without compromising data quality.
Formulas:
End = [Start]+([Duration (wks)]*7)-1
End = [End, row above]
Start = [End, row above]+1
Start = [Start, row above]+14

## WBS & Gantt
Work Breakdown Structure & Gantt — 16 Weeks
WBS | Task | Phase | Owner | Start Wk | Dur (wks) | Effort (PD) | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16
0.1 | Project kickoff, charter, and communication plan | 0. Initiate | PM | 1 | 1 | 4 | bar: W1
0.2 | Stakeholder identification and RACI sign-off | 0. Initiate | PM / Lead Cloud Solutions Architect | 1 | 2 | 5 | bar: W1 to W2
0.3 | Tooling licensing and environment access requests | 0. Initiate | Lead Cloud Solutions Architect | 1 | 2 | 4 | bar: W1 to W2
0.4 | Steering committee and governance cadence established | 0. Initiate | PM | 2 | 1 | 3 | bar: W2
0.5 | Detailed plan baseline and risk register v1 | 0. Initiate | PM | 2 | 1 | 4 | bar: W2
0.6 | Phase 0 exit gate review | 0. Initiate | PM / Steering | 2 | 1 | 2 | bar: W2
1.1 | Discovery architecture and tooling design | 1. Discovery Setup | Cloud Engineer | 3 | 1 | 6 | bar: W3
1.2 | CAB submission for firewall/network changes | 1. Discovery Setup | Network Firewall SME | 3 | 2 | 4 | bar: W3 to W4
1.3 | Service accounts, credentials, vault setup | 1. Discovery Setup | Cloud Engineer | 3 | 2 | 5 | bar: W3 to W4
1.4 | Azure Migrate appliance deployment (per site) | 1. Discovery Setup | Cloud Engineer | 4 | 2 | 12 | bar: W4 to W5
1.5 | Initial discovery test — connectivity & data flow | 1. Discovery Setup | Cloud Engineer | 4 | 2 | 8 | bar: W4 to W5
1.6 | Troubleshoot data-capture gaps (firewall/OS/credentials) | 1. Discovery Setup | Cloud Engineer + Network Firewall SME | 5 | 1 | 10 | bar: W5
1.7 | Phase 1 exit gate — discovery operational | 1. Discovery Setup | Lead Cloud Solutions Architect | 5 | 1 | 2 | bar: W5
2.1 | Continuous infrastructure inventory collection | 2. Discovery Data | Cloud Engineer | 6 | 4 | 16 | bar: W6 to W9
2.2 | Utilization data collection (min 2 wks, target 4 wks) | 2. Discovery Data | Cloud Engineer | 6 | 4 | 12 | bar: W6 to W9
2.3 | Daily appliance health checks and re-sync | 2. Discovery Data | Cloud Engineer | 6 | 4 | 8 | bar: W6 to W9
2.4 | Re-discovery cycles for ~10–15% of estate | 2. Discovery Data | Cloud Engineer | 7 | 2 | 8 | bar: W7 to W8
2.5 | Application dependency mapping (agentless) | 2. Discovery Data | Cloud Engineer | 7 | 3 | 12 | bar: W7 to W9
2.6 | Inventory completeness validation (>=95%) | 2. Discovery Data | Lead Cloud Solutions Architect | 9 | 1 | 4 | bar: W9
2.7 | Phase 2 exit gate — data sufficient for analysis | 2. Discovery Data | Lead Cloud Solutions Architect | 9 | 1 | 2 | bar: W9
3.1 | Application owner interviews and questionnaires | 3. Analysis | Technical Consultant | 8 | 4 | 24 | bar: W8 to W11
3.2 | Business criticality and tier classification | 3. Analysis | Technical Consultant | 8 | 3 | 8 | bar: W8 to W10
3.3 | Compliance, regulatory, and data residency review | 3. Analysis | Lead Cloud Solutions Architect | 9 | 2 | 6 | bar: W9 to W10
3.4 | Infrastructure profiling and pattern analysis | 3. Analysis | Lead Cloud Solutions Architect | 8 | 3 | 10 | bar: W8 to W10
3.5 | Integration and external dependency mapping | 3. Analysis | Technical Consultant | 9 | 3 | 10 | bar: W9 to W11
3.6 | 6Rs disposition draft (Rehost / Replatform / etc.) | 3. Analysis | Lead Cloud Solutions Architect | 10 | 2 | 10 | bar: W10 to W11
3.7 | Phase 3 exit gate — analysis package validated | 3. Analysis | Lead Cloud Solutions Architect | 11 | 1 | 2 | bar: W11
4.1 | Right-sizing recommendations (req 2+ wks data) | 4. Evaluation | Technical Consultant + Lead Cloud Solutions Architect | 10 | 2 | 14 | bar: W10 to W11
4.2 | Azure landing zone target architecture (CAF aligned) | 4. Evaluation | Lead Cloud Solutions Architect | 10 | 3 | 14 | bar: W10 to W12
4.3 | TCO model — Azure (5-yr, with RI/SP, AHB) | 4. Evaluation | Technical Consultant | 11 | 2 | 10 | bar: W11 to W12
4.4 | Comparative TCO — AWS and GCP (portfolio level) | 4. Evaluation | Technical Consultant | 11 | 2 | 8 | bar: W11 to W12
4.5 | License optimization analysis (AHB, BYOL, RHEL) | 4. Evaluation | Technical Consultant | 11 | 2 | 6 | bar: W11 to W12
4.6 | Security & compliance gap analysis | 4. Evaluation | Lead Cloud Solutions Architect | 11 | 2 | 6 | bar: W11 to W12
4.7 | Phase 4 exit gate — evaluation reviewed | 4. Evaluation | Lead Cloud Solutions Architect | 12 | 1 | 2 | bar: W12
5.1 | Migration wave grouping (dependency-driven) | 5. Planning | Lead Cloud Solutions Architect | 13 | 2 | 10 | bar: W13 to W14
5.2 | Wave-level migration approach and effort estimates | 5. Planning | Lead Cloud Solutions Architect | 13 | 2 | 10 | bar: W13 to W14
5.3 | Risk assessment and rollback strategy | 5. Planning | PM / Lead Cloud Solutions Architect | 13 | 2 | 6 | bar: W13 to W14
5.4 | High-level migration roadmap and Gantt | 5. Planning | PM | 14 | 1 | 6 | bar: W14
5.5 | Phase 5 exit gate — wave plan approved | 5. Planning | Lead Cloud Solutions Architect | 14 | 1 | 2 | bar: W14
6.1 | Executive summary and business case authoring | 6. Report | PM / Lead Cloud Solutions Architect | 15 | 2 | 8 | bar: W15 to W16
6.2 | Technical findings and recommendations doc | 6. Report | Lead Cloud Solutions Architect | 15 | 2 | 10 | bar: W15 to W16
6.3 | Internal QA and peer review | 6. Report | Lead Cloud Solutions Architect | 15 | 1 | 4 | bar: W16
6.4 | Customer-ready deliverable package | 6. Report | PM | 15 | 1 | 4 | bar: W16
7.1 | Technical workshop walkthrough with customer | 7. Sign-off | Lead Cloud Solutions Architect | 15 | 1 | 3
7.2 | Revisions based on technical feedback | 7. Sign-off | Lead Cloud Solutions Architect | 15 | 1 | 4
7.3 | Executive readout and Q&A | 7. Sign-off | PM / Lead Cloud Solutions Architect | 16 | 1 | 3
7.4 | Final sign-off and engagement closeout | 7. Sign-off | PM | 16 | 1 | 3
| TOTAL EFFORT (person-days) |  |  |  |  | 334

## RACI
RACI — Roles & Responsibilities
Activity | Exec Sponsor | Steering Committee | PM | Lead Cloud Solutions Architect | Network Firewall SME | Cloud Engineer | Technical Consultant | Customer App Owners
Engagement governance & escalation | A | C | R | C | I | I | I | I
Stakeholder management | I | C | R | C | I | I | I | C
Discovery tooling design | I | I | I | A | C | R | C | I
Firewall / network change requests | bar: I to I
Appliance deployment | I | I | I | A | I | R | I | I
Discovery troubleshooting | I | I | I | A | C | R | C | C
Utilization data collection | I | I | I | A | I | R | C | I
Application dependency mapping | I | I | I | A | I | R | C | C
Application owner interviews | I | I | C | A | I | I | R | C
Business criticality & tiering | I | C | I | A | I | I | R | C
Compliance & data residency review | I | C | I | R | I | I | C | C
Right-sizing recommendations | I | I | I | A | I | C | R | I
Landing zone target architecture | I | C | I | R | I | C | C | I
TCO modeling — Azure / AWS / GCP | I | C | I | A | I | I | R | I
License optimization (AHB, BYOL) | I | I | I | A | I | I | R | I
Security & compliance gap analysis | I | C | I | R | I | I | C | I
Migration wave planning | I | C | C | R | I | C | C | C
Risk register maintenance | I | C | R | C | I | C | C | I
Readiness report authoring | I | C | R | R | I | C | C | I
Executive readout | A | C | R | R | I | I | I | C
Final acceptance & sign-off | A | R | C | C | I | I | I | I
Legend
R | A A: Responsible — does the work
A | A A: Accountable — single point of approval
C | A A: Consulted — provides input
I | A A: Informed — kept up to date

## Resource Plan
Resource Plan — Allocation & Effort
Role | Allocation % | Weeks Active | Total PD | Notes
Engagement / Project Manager | 50% | 16 | 40 | Drives plan, governance, status, risk register. Active across all phases.
Lead Cloud Solutions Architect | 75% | 16 | 60 | Solution authority, target architecture, exit gate sign-off, customer-facing lead. Also covers security/compliance review, gap analysis, network discovery validation, and hybrid connectivity review.
Cloud Engineer | 100% | 12 | 60 | Owns Phase 1–2 (discovery tooling setup, data collection, troubleshooting, dependency mapping).
Technical Consultant | 75% | 12 | 45 | Phase 3–4 lead — application interviews, criticality, 6Rs, right-sizing, TCO, RI/SP, license optimization.
Network Firewall SME | 25% | 5 | 6 | Firewall rule changes, CAB submissions, network change requests, and firewall troubleshooting support for discovery.
TOTAL |  |  | 211
Note: Rates shown are illustrative blended day rates. Replace with negotiated rates per the customer MSA / SOW.

## Risk Register
Risk Register
ID | Risk | Category | Likelihood (1-5) | Impact (1-5) | Score | Mitigation | Owner
R01 | Firewall / network change requests delayed beyond 10-day CAB lead time, blocking discovery appliance. | Discovery | 4 | 4 | 16 | Submit CAB requests on Day 1 of Phase 0 (not Phase 1). Pre-stage all required ports/IPs in writing. Escalation path defined with customer Network Director. | Network Firewall SME
R02 | OS-level restrictions (PowerShell ExecutionPolicy, sudoers, GPO lockdown) prevent agent or WMI/SSH discovery on subset of hosts. | Discovery | 5 | 3 | 15 | Embed 1-week troubleshooting buffer in Phase 1. Pre-validate access on a 10-host pilot before full rollout. Have agent-based fallback ready for problem hosts. | Cloud Engineer
R03 | Less than 2 weeks of clean utilization data captured before Phase 4 right-sizing kickoff, undermining recommendation confidence. | Data Quality | 3 | 5 | 15 | HARD GATE: Phase 4 cannot start until 2-week data threshold met. PM tracks daily on the dashboard. Escalate to Steering if slipping. | Lead Cloud Solutions Architect
R04 | Application owners unavailable for interview windows, slowing Phase 3 dependency and criticality work. | Stakeholder | 4 | 4 | 16 | Customer-side scheduling commitment built into Phase 0. Steering committee escalation if owner participation drops below 80% in any week. | PM
R05 | CMDB data is stale or incomplete, requiring extensive manual reconciliation. | Data Quality | 4 | 3 | 12 | Pre-engagement CMDB sample review during Phase 0. Discovery output treated as authoritative; CMDB used for reconciliation only. | Lead Cloud Solutions Architect
R06 | Scope expansion mid-engagement (new sites, new apps, new compliance requirements). | Scope | 3 | 4 | 12 | Formal change control via SOW change order. Steering must approve any scope additions; impact on timeline and cost is transparently modeled. | PM
R07 | Customer security team withholds credentials needed for deeper application discovery. | Discovery | 3 | 4 | 12 | Service account requirements documented and approved in Phase 0. Privileged Access Workstation (PAW) approach offered. Vault-based credentials used. | Lead Cloud Solutions Architect
R08 | Right-sizing recommendations conflict with application owner sizing assumptions, eroding trust. | Stakeholder | 3 | 3 | 9 | Always present P95 utilization plus headroom; show methodology transparently. Frame as starting point, with right-of-refusal per workload owner. | Technical Consultant
R09 | Comparative AWS/GCP TCO becomes the focus and dilutes the Azure-primary recommendation. | Commercial | 2 | 3 | 6 | Frame comparative TCO at portfolio level only. Detailed workload-level multi-cloud requires separate engagement scope. | Lead Cloud Solutions Architect
R10 | Holiday / freeze periods reduce effective working weeks during Phase 2 data collection. | Schedule | 3 | 3 | 9 | Calendar reviewed in Phase 0. If freeze overlaps Phase 2, either extend window or start data collection earlier (with appliance live first). | PM
R11 | Network or storage subsystem in Phase 4 right-sizing is materially undersized due to lack of peak-event capture (e.g., no month-end captured). | Data Quality | 3 | 4 | 12 | Target 4-week data window (covers month-end). Where 2-week window only, recommendations explicitly flagged 'medium confidence' with sensitivity range. | Technical Consultant
R12 | Customer change in executive sponsorship mid-engagement. | Governance | 2 | 5 | 10 | Steering committee includes deputy sponsor. Knowledge transfer plan triggered on any leadership change. | PM
R13 | Compressed Phase 6-7 timeline (2 weeks reduced to 1 week each) leaves no buffer for deliverable rework or stakeholder rescheduling. | Schedule | 4 | 4 | 16 | Pre-schedule all review sessions in Phase 0. Deliverable templates pre-approved. Customer commits to decision-ready attendees. Parallel QA track during Phase 5. | PM

## Deliverables
Deliverables — Phase Mapped
Phase | Deliverable | Format | Acceptance Criteria | Owner
0. Initiate | Project Charter | DOCX | Sponsor signature on charter; objectives and success criteria agreed. | PM
0. Initiate | Detailed Project Plan & RACI | XLSX | Steering approval of timeline, resources, and gates. | PM
0. Initiate | Communication Plan | DOCX | Cadence and audiences agreed by stakeholders. | PM
1. Discovery Setup | Discovery Architecture Design | DOCX | Lead Architect approval; tooling, ports, accounts documented. | Lead Cloud Solutions Architect
1. Discovery Setup | Tooling Operational Confirmation | Memo | Successful test discovery on >= 95% of pilot scope. | Cloud Engineer
2. Discovery | Inventory Dataset | XLSX / CSV | Coverage >= 95% of in-scope servers; reconciled with CMDB. | Cloud Engineer
2. Discovery | Utilization Dataset | XLSX / CSV | Min 2 weeks (target 4 weeks) of CPU/Mem/Disk/Net per server. | Cloud Engineer
2. Discovery | Dependency Map | Visio / XLSX | Coverage >= 90% of in-scope servers; dependency direction validated. | Cloud Engineer
3. Analysis | Application Portfolio Profile | XLSX | All in-scope apps tiered, criticality assigned, owners confirmed. | Technical Consultant
3. Analysis | Compliance & Data Residency Findings | DOCX | Customer Security Officer review and concurrence. | Lead Cloud Solutions Architect
3. Analysis | 6Rs Disposition Draft | XLSX | Disposition rationale documented per app; reviewed by Lead Arch. | Lead Cloud Solutions Architect
4. Evaluation | Right-Sizing Recommendations | XLSX | Per-server target SKU with confidence level (high/med/low). | Technical Consultant
4. Evaluation | Azure Landing Zone Target Architecture | DOCX + Visio | CAF-aligned, customer Cloud Architect concurrence. | Lead Cloud Solutions Architect
4. Evaluation | TCO Model — Azure | XLSX | 5-yr TCO with RI/SP scenarios, Azure Hybrid Benefit applied. | Technical Consultant
4. Evaluation | Comparative TCO — AWS / GCP | XLSX | Portfolio-level comparison with explicit assumptions documented. | Technical Consultant
5. Planning | Migration Wave Plan | XLSX | Waves grouped by dependency; effort estimates per wave. | Lead Cloud Solutions Architect
5. Planning | Risk & Rollback Strategy | DOCX | Mitigations and rollback approach per wave. | PM
6. Report | Executive Summary | DOCX / PPTX | Sponsor-ready; business case included. | PM / Lead Cloud Solutions Architect
6. Report | Technical Findings & Recommendations | DOCX | Lead Architect peer review complete. | Lead Cloud Solutions Architect
6. Report | Migration Roadmap | PPTX / XLSX | Aligned with wave plan; phased timeline visible. | PM
7. Sign-off | Final Deliverable Package | All formats | Customer formal acceptance signature. | PM