Cloud Readiness Assessment

Statement of Work

Prepared by: Cloud Solutions Architecture Team

Prepared for: [Customer Name]

| Document | Cloud Readiness Assessment — Statement of Work |
| --- | --- |
| Version | 1.0 (Draft) |
| Date | [Date] |
| Prepared by | Cloud Solutions Architecture Team |
| Engagement Type | Cloud Readiness Assessment (Default Profile) |
| Target Hyperscaler | To be confirmed (Azure / AWS / Google Cloud) |
| Estate Profile | Large enterprise — 3,800 servers |
| Duration | 16 weeks elapsed (~4 months) |

# Document Control & Distribution

| Owner | Cloud Solutions Architecture Team |
| --- | --- |
| Status | Draft |
| Intended Audience | Customer Executive Sponsor, Steering Committee, and Senior Technical Leadership |
| Confidentiality | Confidential — for intended recipients only |
| Distribution | Shared by the Customer Sponsor (or delegate) to approved stakeholders |

Contents

1. Executive Summary
2. Engagement Assumptions
3. Scope of Services
4. Deliverables
5. Timeline
6. Team & Responsibilities
7. Customer Obligations
8. Exclusions
9. Key Risks & Mitigations
10. Change Control
11. Acceptance Criteria
12. Commercial Terms
13. Signatures

Statement of Work for Professional & Consulting Services. This Statement of Work (“SOW”) is between [Rackspace Legal Entity] (“Rackspace”) and [Customer Legal Entity] (“Customer”). This SOW is subject to and governed by the applicable master services agreement and professional services terms between the parties (the “Agreement”). The Agreement constitutes the complete agreement between the parties regarding the Services described in this SOW and supersedes any prior communications regarding the same subject matter.

# 1. Executive Summary

## 1.1 Executive Overview

## Objective: Deliver a data-driven Cloud Readiness Assessment for the in-scope estate and provide a defensible recommendation for target cloud landing-zone requirements, migration approach options, and a comparative view across Azure, AWS, and Google Cloud (as required).

- Duration: 16 weeks elapsed (fixed), with defined parallelization to protect data-quality requirements.

- Estate Profile: Large enterprise — approximately 3,800 servers and less than 50 applications (assumed).

- Critical Data Gates: Minimum 2 weeks of utilization data before right-sizing; target 4 weeks to capture weekly seasonality.

- Governance: Weekly Steering Committee, bi-weekly executive readout, and phase exit gates with sign-off.

- Commercial Model: Fixed Fee with milestone-based invoicing tied to phase exit gates.

## 1.2 Key Decisions Required

- Executive Sponsor and Steering Committee confirmation (names/roles) and approval of the governance cadence.

- Confirmation of the target cloud decision path (Azure / AWS / Google Cloud) and the desired depth of comparative analysis (portfolio-level baseline included).

- Approval for discovery approach and tooling (agentless preferred) and timely processing of CAB/network changes and service-account provisioning.

- Commitment of Application Owner participation windows for interviews/workshops during the Analysis phase.

This Statement of Work (SOW) covers the scope, approach, deliverables, timeline, and commercial terms for a Cloud Readiness Assessment for [Customer Name]. The assessment will provide a clear recommendation for the in-scope estate. It will include landing zone requirements, migration approach options, and a comparative view across Microsoft Azure, Amazon Web Services (AWS), and Google Cloud Platform (GCP), as needed.

The work is delivered in eight phases. It starts with Initiation, then moves through Discovery, Analysis, Evaluation, and Planning. It ends with Reporting and Sign-off. The schedule includes time to set up discovery tooling and fix common access issues (firewall and OS permissions). We also treat two weeks of utilization data as a hard requirement before we produce right-sizing recommendations.

The engagement duration is fixed at 16 weeks (elapsed). All activities and deliverables in this SOW are planned within this window. Some workstreams run in parallel. We do not reduce the minimum discovery, data-quality, or stakeholder review time needed for a reliable assessment.

# SOW Term & Business Hours

Business Hours. Business hours for performance of this SOW are 8:30am to 5:30pm Monday through Friday (excluding public holidays) in the time zone in which the Services are being performed, unless otherwise agreed in writing.

SOW Term. The Services under this SOW are for a fixed term of 16 weeks elapsed from the mutually agreed start date, unless otherwise amended through change control.

# 2. Engagement Assumptions

The pricing, duration, and resourcing in this SOW are predicated on the following assumptions. Material deviations will be handled via formal change control.

## 2.1 Estate & Scope

- Estate size of approximately 3,800 servers (large enterprise). The plan and resourcing in this SOW are sized for this band; materially smaller estates may compress, and larger estates may extend Phase 1–2 via change control.

- Workload mix is approximately 70% virtualized (predominantly VMware vSphere, some Hyper-V), 20% physical, and 10% already on PaaS or SaaS.

- Operating system mix is approximately 60% Windows Server (2012 R2 through 2022) and 40% Linux (RHEL, Ubuntu, SUSE).

- Application portfolio of less than 50 business applications (assumed).

- In-scope domains include compute, storage, networking, identity, data, application portfolio, security and compliance posture, and a FinOps baseline.

## 2.2 Hyperscaler & Tooling

- Target cloud (Azure / AWS / GCP) will be confirmed during Phase 0 based on customer strategy, constraints, and stakeholder alignment. The assessment remains cloud-neutral until this decision is confirmed.

- A comparative cost and capability view across Azure, AWS, and GCP is included at the portfolio level. If workload-level multi-cloud deep dives are required, they will be added via change order.

- Discovery tooling will be selected and confirmed in Phase 0 based on the target cloud and customer security constraints. Tooling may include native discovery services (e.g., Azure Migrate, AWS Application Discovery Service, Google Cloud discovery/assessment tooling) and/or supplemental exports (e.g., VMware RVTools, CMDB/monitoring exports).

- Supplemental data sources may include VMware exports (e.g., RVTools), OS and database assessment utilities, current cloud account data (if applicable), and existing monitoring/ITSM data to improve inventory and utilization completeness.

- Pricing and TCO modeling uses the hyperscaler calculators and pricing references aligned to the target and comparative clouds (e.g., Azure Pricing/TCO, AWS Pricing Calculator, and Google Cloud Pricing Calculator), with assumptions documented in the cost model.

## 2.3 Discovery Data Quality

The following data-quality requirements are built into the plan and drive the timeline:

- A minimum of two weeks of continuous utilization data is required before right-sizing recommendations are issued with confidence. Four weeks is the target window to capture weekly seasonality (month-end batch jobs, weekend reporting cycles).

- A three-week setup window is budgeted for discovery tooling stand-up. This includes the typical 5- to 10-business-day Change Advisory Board (CAB) lead time for firewall and network change requests, service-account provisioning, and appliance certification.

- A one-week troubleshooting reserve is embedded in the discovery setup phase to address known data-capture issues: on-prem firewall egress blocks, WMI/SSH/SNMP failures, OS-level GPO and PowerShell ExecutionPolicy restrictions, and sudoers misconfiguration.

- Approximately 10–15% of in-scope servers are expected to require re-discovery cycles due to credential, network, or agent issues. This contingency is built into the data-collection phase duration.

- Inventory completeness target is at least 95% of in-scope servers with utilization data and at least 90% with dependency data. Below these thresholds, the right-sizing recommendation in the Evaluation phase will be flagged as low-confidence and a remediation plan will be proposed.

## 2.4 Customer & Governance

- The customer follows a formal Change Advisory Board (CAB) process. Firewall and network change requests require a 5- to 10-business-day lead time; this has been built into the schedule.

- Application owners are assumed to be available for two to three hours per week per application during the Analysis phase. Limited availability of application owners is the engagement’s top stakeholder risk and is tracked weekly.

- A weekly Steering Committee, a bi-weekly executive readout, and a daily delivery-team stand-up are established as the governance cadence.

- A single primary geography is assumed. Multi-region operation adds two to three weeks for data-residency and latency considerations.

## 2.5 Commercial & Delivery

- The engagement is delivered on a Fixed Fee basis, with milestone-based invoicing tied to phase exit gates.

- The baseline delivery team (planned to execute the 16-week schedule) aligns to the Project Plan workbook Resource Plan: Project Manager (50% for 16 weeks), Lead Cloud Solutions Architect (75% for 16 weeks), Cloud Engineer (100% for 12 weeks), Technical Consultant (75% for 12 weeks), and Network Firewall SME (25% for 5 weeks). Specialist advisory roles (e.g., hyperscaler/AI/pre-sales/alliances) participate as needed for key reviews and do not change the baseline effort unless explicitly added via change control.

- A standard five-day work week is assumed, with US holidays observed. The plan does not compress for hero schedules; aggressive compression is the leading cause of unreliable assessment outputs.

- Each phase is gated by a formal exit review. The next phase does not commence until the prior gate is signed (or, where phases are explicitly parallelized in the project plan, until the defined dependency gate is met).

# 3. Scope of Services

The Cloud Readiness Assessment is structured in eight phases (one initiation, four assessment, one planning, one reporting, one sign-off). The four assessment phases align to the existing Cloud Readiness Accelerator methodology: Discovery, Analysis, Evaluation, and Planning.

## 3.1 Phase 0 — Initiate & Mobilize (Weeks 1–2)

We set up the team and agree how we will run the engagement. We confirm governance, communication, and change control. We complete kickoff and charter sign-off, confirm stakeholders, and sign off the RACI. We also raise access and tooling requests and set up the steering committee cadence.

Deliverables:

- Project Charter

- Detailed Project Plan & RACI

## 3.2 Phase 1 — Discovery: Tooling Setup (Weeks 3–5)

We design and set up the discovery tooling. This includes CAB requests for firewall and network changes, service account setup, and deployment per site or environment. We run a connectivity test and confirm data flow. We keep a one-week buffer to fix common issues, such as firewall blocks, OS permissions, or credential gaps. On-premises server and network remediation required to restore connectivity or access is performed by the customer, with Rackspace providing requirements and validation results. The phase exits when discovery works for at least 95% of the pilot scope.

Deliverables:

- Tooling Operational Confirmation

## 3.3 Phase 2 — Discovery: Data Collection (Weeks 6–9)

Continuous infrastructure inventory, utilization, and dependency data are collected. The phase runs for four weeks to satisfy the two-week minimum utilization window and to target the four-week ideal that captures weekly seasonality. Daily appliance health checks are performed, re-discovery is run for the expected 10–15% of hosts requiring it, and inventory completeness is validated against the 95% / 90% thresholds before the phase exits.

Deliverables:

- Inventory & Utilization Datasets

- Application Dependency Map

## 3.4 Phase 3 — Analysis: Application & Infrastructure Profiling (Weeks 8–11, parallel)

We interview application owners and capture business criticality and tiering. We review compliance and data residency needs. We also analyze infrastructure patterns and map integrations and dependencies. We produce a draft 6Rs disposition (Rehost, Replatform, Refactor, Repurchase, Retire, Retain). This phase overlaps with the end of Phase 2 to save time while keeping data quality intact.

Deliverables:

- Application Portfolio Profile

## 3.5 Phase 4 — Evaluation: Right-Sizing & TCO (Weeks 10–12)

We create right-sizing recommendations once we have at least two weeks of utilization data. We document the target landing zone and governance architecture for the selected target cloud. We also build a five-year TCO model for the target option, including common discount and licensing assumptions where they apply. If required, we provide a portfolio-level comparison across Azure, AWS, and GCP. We also complete a security and compliance gap review.

Deliverables:

- Right-Sizing Recommendations

- TCO Model (Target Cloud) + Comparative View (Azure / AWS / GCP)

## 3.6 Phase 5 — Planning: Migration Cohorts & Roadmap (Weeks 13–14)

Migration waves are grouped using dependency-mapping output. Each wave is assigned a migration approach (lift-and-shift, replatform, refactor, retire, retain) and an effort estimate. A risk and rollback strategy is defined per wave, and a high-level migration roadmap and Gantt chart are produced.

Deliverables:

- Migration High Level Cohorts

## 3.7 Phase 6 — Readiness Report & Recommendations (Week 15)

The executive summary, business case, technical findings, and migration roadmap are finalized and subjected to internal QA and peer review. A customer-ready deliverable package is produced. Per the project plan baseline, this report finalization cycle is scheduled in Week 15, with stakeholder review and final acceptance occurring in Week 16.

Deliverables:

- Executive Summary & Business Case

- Technical Findings & Recommendations

## 3.8 Phase 7 — Stakeholder Review & Sign-off (Week 16)

A technical workshop walkthrough is conducted with the customer’s technical stakeholders and revisions are incorporated. An executive readout is delivered, followed by formal acceptance and engagement closeout. This sign-off activity is scheduled within Week 16 as part of the 16-week engagement timeline.

Deliverables:

- Final Deliverable Package

# 4. Deliverables

The following deliverables are produced and accepted via the formal phase exit gates. Acceptance criteria are documented in the accompanying Project Plan workbook.

| Phase | Deliverable | Format | Acceptance Criteria |
| --- | --- | --- | --- |
| 0. Initiate | Project Charter | DOCX | Sponsor signature; objectives and success criteria agreed. |
| 0. Initiate | Detailed Project Plan & RACI | XLSX | Steering approval of timeline, resources, and gates. |
| 1. Discovery Setup | Discovery Architecture Design | DOCX | Lead Architect approval; tooling, ports, accounts documented. |
| 1. Discovery Setup | Tooling Operational Confirmation | Memo | Successful test discovery on >= 95% of pilot scope. |
| 2. Discovery Data | Inventory & Utilization Datasets | XLSX / CSV | >= 95% inventory coverage; >= 2 weeks utilization data. |
| 2. Discovery Data | Application Dependency Map | Visio / XLSX | >= 90% of in-scope servers with validated dependencies. |
| 3. Analysis | Application Portfolio Profile | XLSX | All in-scope apps tiered, criticality assigned. |
| 3. Analysis | 6Rs Disposition Draft | XLSX | Disposition rationale documented per app. |
| 4. Evaluation | Right-Sizing Recommendations | XLSX | Per-server target SKU with confidence level. |
| 4. Evaluation | Target Landing Zone Architecture | DOCX + Visio | Aligned to the confirmed target cloud reference architecture; customer Cloud Architect concurrence. |
| 4. Evaluation | TCO Model (Target Cloud) + Comparative View (Azure / AWS / GCP) | XLSX | 5-year TCO with commitment/discount scenarios and license optimization assumptions applied as applicable; explicit assumptions documented. |
| 5. Planning | Migration Wave Plan | XLSX | Waves grouped by dependency; effort estimates per wave. |
| 6. Report | Executive Summary & Business Case | DOCX / PPTX | Sponsor-ready; business case included. |
| 6. Report | Technical Findings & Recommendations | DOCX | Lead Architect peer review complete. |
| 7. Sign-off | Final Deliverable Package | All formats | Customer formal acceptance signature. |

# 5. Timeline

The engagement runs for 16 weeks total (elapsed), beginning [Start Date] (or the mutually agreed start date). All activities and phase exit gates outlined in this SOW are planned within this 16-week timeline.

| Phase | Name | Weeks | Effort (PD) | Critical Constraint |
| --- | --- | --- | --- | --- |
| 0 | Initiate & Mobilize | Weeks 1 to 2 | 18 | Tooling licensing and access lead time |
| 1 | Discovery — Tooling Setup | Weeks 3–5 | 42 | CAB lead time; OS/firewall troubleshooting |
| 2 | Discovery — Data Collection | Weeks 6 to 9 | 40 | 2-week minimum utilization data window |
| 3 | Analysis — Profiling | Weeks 8–11 (concurrent) | 38 | Application owner availability |
| 4 | Evaluation — Right-Sizing & TCO | Weeks 10–12 | 32 | Hard gate on 2 weeks of clean data |
| 5 | Planning — Migration Waves | Weeks 13–14 | 22 | Dependency map quality |
| 6 | Readiness Report | Week 15 | 12 | Internal QA cycle |
| 7 | Stakeholder Sign-off | Week 16 | 7 | Executive availability |
|  | Total Elapsed (parallelized) | 16 weeks | 211 | Sequential equivalent: ~22 weeks |

Phase 3 (Analysis) is parallelized with the back half of Phase 2 (Data Collection). The detailed week-by-week Gantt is maintained in the accompanying Project Plan workbook.

# 6. Team & Responsibilities

The engagement is delivered by the joint customer-and-provider delivery team described below. Roles and responsibilities are aligned to the Project Plan workbook (Resource Plan and RACI) and are used to govern accountability for each activity and phase exit gate.

## 6.2 Baseline Delivery Team (per Project Plan workbook)

- Executive Sponsor (Customer) — accountable for business outcomes, removes roadblocks, and provides executive decisions at key gates.

- Steering Committee (Customer) — provides governance oversight, confirms priorities, and supports escalation and decision cadence.

- Project Manager (Provider) — owns the integrated project plan, governance cadence, RAID log, change control, stakeholder coordination, and phase exit gate orchestration.

- Lead Cloud Solutions Architect / Cloud Architects (Provider) — solution authority for the assessment and accountable for architecture decisions and recommendation quality. The provider will staff either (a) one multi-cloud architect with proven expertise across AWS, Azure, and Google Cloud, or (b) three platform architects (one each for AWS, Azure, and Google Cloud) if a single multi-cloud architect is not available. The lead runs technical workshops, validates data-quality gates, and signs off technical exit gates. Platform architects support service mapping and validate recommendations for their respective hyperscaler.

- Cloud Engineer (Provider) — implements discovery tooling setup, data collection, daily health checks, and troubleshooting for connectivity/credential/OS-level issues; supports dependency mapping.

- Technical Consultant (Provider) — leads application interviews and profiling, criticality/tiering, 6Rs disposition, right-sizing inputs, and TCO analysis in coordination with the Lead Cloud Solutions Architect.

- Network / Firewall SME (Provider) — supports CAB submissions, firewall/network change requests, and troubleshooting required to enable discovery tooling connectivity.

- Customer Application Owners (Customer) — provide application context, participate in interviews/workshops, validate dependencies and criticality, and review recommendations for their applications.

A RACI matrix is maintained as part of the engagement project plan to confirm accountability for each activity and phase gate and is reviewed during mobilization.

# 7. Customer Obligations

To stay on schedule, the customer must meet the commitments below. These align with the RACI in the Project Plan workbook. If any commitment slips, we will escalate through the Steering Committee and may need to re-baseline the plan.

- Provide a named Executive Sponsor and ensure they (or a designated delegate) is available for executive decisions and final acceptance/sign-off.

- Establish a Steering Committee and maintain the agreed governance cadence (weekly Steering Committee; bi-weekly executive readout) to resolve risks, confirm priorities, and support escalations.

- Ensure Customer Application Owners participate in interviews/workshops (assumed 2–3 hours per week per in-scope application during the Analysis phase) and validate application criticality, dependencies, and recommendation assumptions.

- Process firewall and network change requests through the CAB within the standard 5–10 business day lead time. Provide approvals on time so discovery can run.

- Customer is responsible for all on-premises server and network troubleshooting required to enable discovery tooling (for example: firewall rule remediation, routing/DNS issues, proxy configuration, host-based firewall changes, WMI/SSH access enablement, and credential/permission remediation). Rackspace will provide required ports, connectivity requirements, and validation results to support resolution.

- Provide the required service accounts, credentials, and access listed in the Discovery Architecture Design. Complete security reviews on time so approved discovery methods can be used.

- Provide read access (or export extracts) for relevant systems (e.g., CMDB, monitoring, ITSM) to support inventory reconciliation, dependency validation, and assumptions confirmation.

- Provide on-site access where required for discovery setup and for the final technical and executive readouts.

# 8. Exclusions

The following are explicitly out of scope for this SOW and require a separate change order to add:

- Migration execution, including target environment build-out, data migration, and cutover.

- Application code refactoring, modernization proofs of concept, and containerization work.

- End-user computing, virtual desktop infrastructure, and mobile device management.

- Industrial control systems, SCADA, IoT, and OT estate.

- Workload-level multi-cloud architecture deep dives (portfolio-level comparative analysis is included).

- Detailed FinOps operating model design and tooling rollout.

- Production support, managed services, and post-assessment break-fix activities.

# 9. Key Risks & Mitigations

The top risks and their mitigations are summarized below; the full risk register is maintained in the Project Plan workbook.

| ID | Risk | Score | Mitigation |
| --- | --- | --- | --- |
| R01 | Firewall / network CAB delays block discovery appliance. | 16 | Submit CAB on Day 1 of Phase 0; pre-stage all ports/IPs; defined escalation to Network Director. |
| R02 | OS-level restrictions block WMI/SSH discovery on subset of hosts. | 15 | 1-week troubleshooting buffer in Phase 1; 10-host pilot validation before full rollout; agent-based fallback prepared. |
| R03 | Less than 2 weeks of clean utilization data before Phase 4 kickoff. | 15 | Hard gate — Phase 4 cannot start without the 2-week threshold; PM tracks daily; Steering escalation if slipping. |
| R04 | Application owner availability below threshold during Phase 3. | 16 | Customer scheduling commitment in Phase 0; Steering escalation if owner participation drops below 80% per week. |
| R05 | CMDB stale or incomplete, requiring manual reconciliation. | 12 | Pre-engagement CMDB sample review in Phase 0; discovery output treated as authoritative. |
| R11 | Right-sizing miscalibrated due to no peak-event capture (e.g., no month-end). | 12 | Target 4-week data window; if 2-week only, recommendations are flagged as medium confidence with a sensitivity range. |

# 10. Change Control

Any change to scope, deliverables, timeline, team, or commercial terms must be agreed in writing through a Change Order signed by both parties. The Change Order will describe the change and confirm the impact on schedule and cost. Work continues against the current baseline until both parties sign the Change Order.

# 11. Acceptance Criteria

We review each deliverable against the acceptance criteria in the Project Plan workbook. The customer will review each deliverable within five business days of submission. If the customer does not reject a deliverable in writing within that window, it is treated as accepted. Final acceptance happens at the end of Phase 7 when the customer signs the Final Deliverable Package.

# 12. Commercial Terms

This engagement is delivered on a Fixed Fee basis. Invoicing is milestone-based, tied to phase exit gates.

| Milestone | Trigger | % of Total |
| --- | --- | --- |
| M1 — Mobilization Complete | Phase 0 exit gate signed | 10% |
| M2 — Discovery Operational | Phase 1 exit gate signed | 15% |
| M3 — Data Collection Complete | Phase 2 exit gate signed | 20% |
| M4 — Analysis & Evaluation Complete | Phase 4 exit gate signed | 25% |
| M5 — Wave Plan Approved | Phase 5 exit gate signed | 10% |
| M6 — Final Acceptance | Phase 7 final sign-off | 20% |

The fixed fee amount and payment schedule are documented in the Commercial Annex. Travel and out-of-pocket expenses (if applicable) are reimbursed at cost upon receipt, unless otherwise specified in the Commercial Annex.

# 13. Signatures

By signing below, both parties acknowledge they have read, understood, and agree to the terms of this Statement of Work.

| [Customer Name] | Cloud Solutions Architecture Team |
| --- | --- |
| Signature:________________________ Date:_____________________________ Name:____________________________ Title:_____________________________ Company: [Customer Legal Entity] | Signature:________________________ Date:_____________________________ Name:____________________________ Title:_____________________________ Company: [Rackspace Legal Entity] |