## Wave Planning
Migration Wave Planning
Version 1.0 ¦ Phase: Evaluation/Planning ¦ Tasks 7.1, 7.2 ¦ Requirements 7.1-7.8
Section 1 — Migration Wave Grouping
Wave Assignment Criteria
Factor | Weight | Description
Dependency constraints | 30% | Applications that must migrate together
Readiness score | 25% | Higher readiness = earlier wave
Business criticality | 20% | Lower criticality = earlier wave (lower risk)
Complexity | 15% | Lower complexity = earlier wave
Business value | 10% | Higher value = prioritize
Total | 100%
Wave Assignments
Wave | Application | Readiness Score | Criticality | Dependencies | Migration Approach | Estimated Duration (weeks)
Wave 0 (Pilot) |  |  | Low/Medium | None/minimal | Rehost/Replatform
Wave 1
Wave 1
Wave 1
Wave 2
Wave 2
Wave 2
Wave 3
Wave 3
Wave 3
Deferred |  |  |  |  | Retain/Retire/Repurchase
Section 2 — Wave Sequencing
Wave | Start Date | End Date | Duration (weeks) | Parallel With | Gate / Checkpoint | Owner
Wave 0 |  |  | 0 | — | Pilot review & approval
Wave 1 |  |  | 0 | — | Wave 1 review
Wave 2 |  |  | 0 | Wave 1 (partial) | Wave 2 review
Wave 3 |  |  | 0 | Wave 2 (partial) | Final review
Section 3 — Tight Coupling Groups
Group ID | Applications | Coupling Type | Shared Resources | Migration Constraint | Wave Assignment | Notes
TCG-001 |  |  |  | Must migrate together in same wave
TCG-002 |  |  |  | Must migrate together in same wave
TCG-003 |  |  |  | Must migrate together in same wave
TCG-004 |  |  |  | Must migrate together in same wave
TCG-005 |  |  |  | Must migrate together in same wave
TCG-006 |  |  |  | Must migrate together in same wave
Section 4 — Cutover Plan per Wave
Step | Activity | Duration (hours) | Owner | Rollback Trigger | Rollback Action | Notes
1 | Pre-cutover validation
2 | DNS / traffic switch |  |  | Errors > threshold | Revert DNS
3 | Data sync verification |  |  | Data mismatch | Resync from source
4 | Application validation |  |  | Functional failures | Rollback to on-prem
5 | Performance validation |  |  | Performance degradation | Rollback to on-prem
6 | Stakeholder sign-off |  |  | Stakeholder rejection | Rollback to on-prem
7 | Decommission source (after soak, days) |  |  | N/A | N/A
Rollback Window (hours) |  | Soak Period Before Decommission (days) |  | Go/No-Go Decision Maker
Section 5 — Resource Requirements per Wave
Wave | Cloud Architect | Migration Engineer | DBA | Network Engineer | App Owner / QA | Total FTE-Weeks
Wave 0 | [5 empty] | 0
Wave 1 | [5 empty] | 0
Wave 2 | [5 empty] | 0
Wave 3 | [5 empty] | 0
Total | 0 | 0 | 0 | 0 | 0 | 0
Section 6 — Migration Roadmap Summary
Milestone | Target Date | Status | Dependencies | Owner | Notes
Assessment complete
Landing zone ready
Pilot complete |  |  | Landing zone
Wave 1 complete |  |  | Pilot review
Wave 2 complete |  |  | Wave 1 review
Wave 3 complete |  |  | Wave 2 review
Full migration complete |  |  | All waves
Decommission complete |  |  | Soak period
Template Version 1.0 — Cloud Readiness Accelerator Framework