## Slide 1: Cloud Readiness Accelerator — Technical Framework Overview
Methodology, templates, tooling, and delivery guide for CRA practitioners
Rackspace Cloud Solutions Architecture | CRA Framework v2.0

## Slide 2: Framework architecture — four phases, two gates, one parallelisation point
PHASE 1: DISCOVERY (Wks 1–7): Azure Migrate / GCP Migration Center / AWS ADS · VM + app + network data · App inventory
PHASE 2: ANALYSIS (Wks 6–10): Cloud readiness scoring (5 dims) · Governance maturity · OSS licence flags
PHASE 3: EVALUATION (Wks 11–14): 7-layer TCO per hyperscaler · Hyperscaler decision matrix · Recommendation
PHASE 4: PLANNING (Wks 11–20): Migration wave plan · Risk register · Governance model · Part 2 Entry Point
PARALLELISATION: Phase 2 starts at Phase 1 Week 6 — do NOT wait for Phase 1 to complete
GATE 1 (hard): >=14 days clean utilisation data for >=90% of VMs before Phase 3
GATE 2 (pre-commercial): Alliance partner deal registration COMPLETE before Part 2 SOW countersignature

## Slide 3: Phase 1 — three workstreams running simultaneously
Core objective: Complete, accurate, validated inventory with >=14 days clean CPU/RAM/storage/network utilisation data from >=90% of VMs.
1. Infrastructure discovery tooling: VM specs, OS, hypervisor, utilisation data, storage I/O
2. Application inventory: tech stack, DB, VM count, readiness flag, dependencies
3. Dependency mapping (with app owners): dependency heat map, tightly-coupled clusters
CRITICAL: Serialising these workstreams costs 4–6 weeks. Application workshops CAN start at Week 2 while tooling is collecting data.
Run RVTools export on Day 1 regardless of target hyperscaler — provides instant VMware inventory for cross-validation.
Submit firewall CAB request on Day 1 — can take 5–15 business days to approve in enterprise organisations.

## Slide 4: Phase 1 — discovery tooling selection
Tool | Hyperscaler | Deployment | Key Output
Azure Migrate | Azure primary | Agent or agentless (vCenter connector) | infrastructure-profiling.xlsx source data
AWS ADS | AWS primary | Agent-based or Agentless Connector | aws-evaluation.xlsx input
GCP Migration Center | GCP primary | VM Manager agent or RVTools import | gcp-evaluation.xlsx input
RVTools | All hyperscalers | VMware utility — no agent needed | Cross-validation of all discovery tools

## Slide 5: GATE 1 — Phase 3 cannot start without this
Utilisation data collection period: >=14 days continuous clean data
VM coverage: >=90% of in-scope VMs reporting
CPU data quality: P95 values available for >=90% of VMs
RAM data quality: P95 values available for >=90% of VMs
WHY THE GATE IS HARD:
"Using 6 days of data instead of 14 produces right-sizing recommendations with +-30-50% error. At 500 VMs, that is a £2M–£5M range in the business case — not acceptable at board level."
When customer pushes to skip: quantify the risk in writing → offer interim (share Phase 1 report while data collection continues) → document customer's decision if they override

## Slide 6: Phase 2 — five-dimension scoring model
Composite: 4.0–5.0 = Cloud Ready · 3.0–3.9 = Cloud Friendly · 2.0–2.9 = Cloud Challenged · 1.0–1.9 = Blocked
Dimension | Scale | Low Score Means
Technical Complexity | 1 (complex) – 5 (simple) | Legacy OS, custom middleware, tightly-coupled architecture
Business Criticality | 1 (critical) – 5 (non-critical) | RTO < 4hrs, RPO < 1hr, zero-downtime required
Data Sensitivity | 1 (highly sensitive) – 5 (non-sensitive) | PII, FCA-regulated data, GDPR sovereignty constraints
Dependency Risk | 1 (high) – 5 (low) | Tightly-coupled dependencies, on-prem latency requirements
Licence Risk | 1 (high risk) – 5 (low risk) | Oracle RAC, Oracle EE, IBM ILMT, Windows without AHB, SAP

## Slide 7: Phase 2 — OSS licence risk: the commercial time bomb you must not miss
OSS LICENCE CHANGES (2023–2024) affecting cloud deployments:
Redis OSS (post v7.4): SSPL/RSALv2 — requires paid licence for commercial cloud use
Elasticsearch (post 7.10): SSPL — check if using elastic.co or AWS OpenSearch fork
HashiCorp Vault / Terraform: BSL — commercial use restrictions at scale
MongoDB: SSPL — validate version and applicable managed service
Action trigger: ANY OSS Licence Risk Flag → immediate commercial review in Phase 2 BEFORE TCO is built
A TCO model that does not include OSS re-licensing costs is incomplete and will create budget surprises.
DMG Media UK: 140+ Redis instances identified. OSS flag column in the application inventory exists because of this engagement.

## Slide 8: Phase 3 — 7-layer TCO model: why each layer exists
Template: business-case-tco-roi.xlsx · TCO-Summary tab produces board-level number: 3yr net cost (post-partner funding) vs 3yr on-prem
Layer | Tab Name | Common Mistake
(a) Like-for-Like | L4L-Baseline | Using rounded estimates instead of actual P95 utilisation
(b) Optimised | Optimised-Rightsized | Using P50 (median) instead of P95 — underestimates required size
(c) Delta | Calculated (b-a) | Presenting this as 'the saving' without showing layers d–g
(d) Licensing Overlay | Licensing-Overlay | Omitting Oracle BYOL licensing premium/saving
(e) On-Prem Status Quo | OnPrem-StatusQuo | Using standard depreciation without including hardware refresh cycle
(f) Year 1 Dual-Running | Year1-DualRunning | Omitting parallel environment costs (most common budget shock)
(g) Partner Credits | Partner-Credits | Building the board case without this — largest headline number driver

## Slide 9: Phase 3 — Hyperscaler Decision Matrix: critical validation rules
9 required tabs: Criteria-Weights · Azure-Evaluation · AWS-Evaluation · GCP-Evaluation · Comparative-Matrix · 7Rs-Estate-View · Multi-Cloud-Exceptions · Worked-Example · Instructions
CRITICAL RULES before presenting the recommendation:
1. Criteria weights agreed in WRITING by customer BEFORE any scoring begins
2. All three clouds scored with equal rigour — never eliminate one before matrix is complete
3. Every score has a documented evidence reference — not 'expert judgment'
4. Recommendation slide follows the evidence slides — NEVER precedes them
5. The matrix score and the recommendation are consistent
Evidence-before-recommendation is the most important quality rule in the entire framework.

## Slide 10: Phase 4 — wave sequencing principles
Wave | Characteristics | DO NOT include
Wave 0 (PoC, 8–12 wks) | Non-production · 5–10% of estate · Dev/Test · simple Tier-3 | Tier-1 · SAP · Oracle RAC · business-critical
Wave 1 | Cloud Ready · low dependency · Tier-3 · internal tools | Tightly-coupled dependency clusters
Wave 2 | Cloud Friendly · low-medium complexity · mid-tier | Applications that need Wave 1 to complete first
Wave 3 | Cloud Challenged or medium-high · custom middleware | Tier-1 production before Wave 2 validated
Wave 4 | Tier-1 business-critical · ERP, CRM, core business | Only after waves 1–3 validated in production
Wave 5+ | Retained · Oracle specialist · multi-cloud exceptions | Force Oracle RAC to primary cloud without specialist review

## Slide 11: Nine lessons from a real engagement — embedded in the framework
# | Lesson | What Changed in Framework
1 | Scope variance: 57% more VMs than SoW | Scope variance clause in SoW · confidence scoring in app inventory
2 | CAB not submitted Day 1 → 2-week delay | Phase 1 kickoff checklist — CAB on Day 1
3 | Oracle RAC found Week 5 → Oracle analysis delayed Phase 3 by 6 weeks | Oracle Practice Flag column in application inventory
4 | Redis OSS licence change discovered in Phase 3 → TCO re-work | OSS Licence Risk column in application inventory
5 | AMM not pre-registered at Phase 1 → customer missed funding | AMM registration at Phase 1 kickoff · Alliance Manager on Day 1 call
6 | Utilisation data window shortened → TCO accuracy compromised | Gate 1 hard requirement · written escalation process
7 | Phase 2 not started until Phase 1 complete → 4-week delay | Parallelisation: Phase 2 starts at Phase 1 Week 6
8 | EoL OS not flagged until Phase 3 → ESU costs missed | EoL OS column in infrastructure-profiling · flag in risk register
9 | Recommendation before evidence → customer challenged credibility | Evidence-before-recommendation rule · deck structure validation checklist

## Slide 12: Pre-playback QA checklist — 10 checks before presenting Phase 3
[ ] 1. >=14 days clean utilisation data confirmed for >=90% of VMs
[ ] 2. All 7 TCO layers populated for each cloud — no blank rows
[ ] 3. Pricing validated against calculator source this week
[ ] 4. AHB eligibility confirmed (SA status verified with customer)
[ ] 5. Oracle licensing reviewed by Oracle Practice Lead — email sign-off filed
[ ] 6. OSS licence flags resolved — all modelled in TCO
[ ] 7. Hyperscaler matrix weights agreed in writing by customer
[ ] 8. All three clouds scored with evidence references — no blank evidence fields
[ ] 9. Recommendation slide comes AFTER evidence slides (slide >=13)
[ ] 10. AMM/MAP/PSO registration confirmed by Alliance Manager — email filed
This checklist is not optional. A missing check is a quality failure. If you cannot complete all 10, delay the playback.